## Horas por Semana
DATAPREV-SEFIN-CE v2.0 - HORAS POR SEMANA (ESCOPO BASE - SEM ADD-ONs)
Semana | Fase | Recurso | Papel | Horas/Semana | Taxa R$/Hora | Custo Semana (R$) | Custo Acumulado (R$) | % Projeto
1 | Phase 0 - Discovery Resolution | R01 | Technical Architect | 20 | 879.07 | 17581.4 | 17581.4 | 0.4155%
1 | Phase 0 - Discovery Resolution | R05 | Technical Architect (Phase 0) | 40 | 879.07 | 35162.8 | 52744.2 | 1.247%
1 | Phase 0 - Discovery Resolution | R06 | Project Manager | 30 | 879.07 | 26372.1 | 79116.3 | 1.87%
2 | Phase 0 - Discovery Resolution | R01 | Technical Architect | 20 | 879.07 | 17581.4 | 96697.7 | 2.285%
2 | Phase 0 - Discovery Resolution | R05 | Technical Architect (Phase 0) | 40 | 879.07 | 35162.8 | 131860.5 | 3.116%
2 | Phase 0 - Discovery Resolution | R06 | Project Manager | 30 | 879.07 | 26372.1 | 158232.6 | 3.74%
3 | Phase 0 - Discovery Resolution | R01 | Technical Architect | 20 | 879.07 | 17581.4 | 175814 | 4.155%
3 | Phase 0 - Discovery Resolution | R05 | Technical Architect (Phase 0) | 40 | 879.07 | 35162.8 | 210976.8 | 4.986%
3 | Phase 0 - Discovery Resolution | R06 | Project Manager | 30 | 879.07 | 26372.1 | 237348.9 | 5.609%
4 | Phase 1 - Foundation & ORG Setup | R01 | Technical Architect | 40 | 879.07 | 35162.8 | 272511.7 | 6.44%
4 | Phase 1 - Foundation & ORG Setup | R02 | Technical Consultant | 40 | 715.66 | 28626.4 | 301138.1 | 7.117%
4 | Phase 1 - Foundation & ORG Setup | R03 | Technical Consultant (Security) | 30 | 715.66 | 21469.8 | 322607.9 | 7.624%
4 | Phase 1 - Foundation & ORG Setup | R06 | Project Manager | 20 | 879.07 | 17581.4 | 340189.3 | 8.04%
5 | Phase 1 - Foundation & ORG Setup | R01 | Technical Architect | 40 | 879.07 | 35162.8 | 375352.1 | 8.871%
5 | Phase 1 - Foundation & ORG Setup | R02 | Technical Consultant | 40 | 715.66 | 28626.4 | 403978.5 | 9.547%
5 | Phase 1 - Foundation & ORG Setup | R03 | Technical Consultant (Security) | 30 | 715.66 | 21469.8 | 425448.3 | 10.05%
5 | Phase 1 - Foundation & ORG Setup | R06 | Project Manager | 20 | 879.07 | 17581.4 | 443029.7 | 10.47%
6 | Phase 1 - Foundation & ORG Setup | R01 | Technical Architect | 40 | 879.07 | 35162.8 | 478192.5 | 11.3%
6 | Phase 1 - Foundation & ORG Setup | R02 | Technical Consultant | 40 | 715.66 | 28626.4 | 506818.9 | 11.98%
6 | Phase 1 - Foundation & ORG Setup | R03 | Technical Consultant (Security) | 30 | 715.66 | 21469.8 | 528288.7 | 12.49%
6 | Phase 1 - Foundation & ORG Setup | R06 | Project Manager | 20 | 879.07 | 17581.4 | 545870.1 | 12.9%
7 | Phase 1 - Foundation & ORG Setup | R01 | Technical Architect | 40 | 879.07 | 35162.8 | 581032.9 | 13.73%
7 | Phase 1 - Foundation & ORG Setup | R02 | Technical Consultant | 40 | 715.66 | 28626.4 | 609659.3 | 14.41%
7 | Phase 1 - Foundation & ORG Setup | R03 | Technical Consultant (Security) | 30 | 715.66 | 21469.8 | 631129.1 | 14.92%
7 | Phase 1 - Foundation & ORG Setup | R06 | Project Manager | 20 | 879.07 | 17581.4 | 648710.5 | 15.33%
8 | Phase 2 - Einstein Bot + API Integration | R01 | Technical Architect | 30 | 879.07 | 26372.1 | 675082.6 | 15.95%
8 | Phase 2 - Einstein Bot + API Integration | R02 | Technical Consultant | 40 | 715.66 | 28626.4 | 703709 | 16.63%
8 | Phase 2 - Einstein Bot + API Integration | R03 | Technical Consultant (Security) | 20 | 715.66 | 14313.2 | 718022.2 | 16.97%
8 | Phase 2 - Einstein Bot + API Integration | R06 | Project Manager | 20 | 879.07 | 17581.4 | 735603.6 | 17.38%
9 | Phase 2 - Einstein Bot + API Integration | R01 | Technical Architect | 30 | 879.07 | 26372.1 | 761975.7 | 18.01%
9 | Phase 2 - Einstein Bot + API Integration | R02 | Technical Consultant | 40 | 715.66 | 28626.4 | 790602.1 | 18.68%
9 | Phase 2 - Einstein Bot + API Integration | R03 | Technical Consultant (Security) | 20 | 715.66 | 14313.2 | 804915.3 | 19.02%
9 | Phase 2 - Einstein Bot + API Integration | R06 | Project Manager | 20 | 879.07 | 17581.4 | 822496.7 | 19.44%
10 | Phase 2 - Einstein Bot + API Integration | R01 | Technical Architect | 30 | 879.07 | 26372.1 | 848868.8 | 20.06%
10 | Phase 2 - Einstein Bot + API Integration | R02 | Technical Consultant | 40 | 715.66 | 28626.4 | 877495.2 | 20.74%
10 | Phase 2 - Einstein Bot + API Integration | R03 | Technical Consultant (Security) | 20 | 715.66 | 14313.2 | 891808.4 | 21.08%
10 | Phase 2 - Einstein Bot + API Integration | R06 | Project Manager | 20 | 879.07 | 17581.4 | 909389.8 | 21.49%
11 | Phase 2 - Einstein Bot + API Integration | R01 | Technical Architect | 30 | 879.07 | 26372.1 | 935761.9 | 22.12%
11 | Phase 2 - Einstein Bot + API Integration | R02 | Technical Consultant | 40 | 715.66 | 28626.4 | 964388.3 | 22.79%
11 | Phase 2 - Einstein Bot + API Integration | R03 | Technical Consultant (Security) | 20 | 715.66 | 14313.2 | 978701.5 | 23.13%
11 | Phase 2 - Einstein Bot + API Integration | R06 | Project Manager | 20 | 879.07 | 17581.4 | 996282.9 | 23.55%
12 | Phase 2 - Einstein Bot + API Integration | R01 | Technical Architect | 30 | 879.07 | 26372.1 | 1022655 | 24.17%
12 | Phase 2 - Einstein Bot + API Integration | R02 | Technical Consultant | 40 | 715.66 | 28626.4 | 1051281.4 | 24.85%
12 | Phase 2 - Einstein Bot + API Integration | R03 | Technical Consultant (Security) | 20 | 715.66 | 14313.2 | 1065594.6 | 25.18%
12 | Phase 2 - Einstein Bot + API Integration | R06 | Project Manager | 20 | 879.07 | 17581.4 | 1083176 | 25.6%
13 | Phase 2 - Einstein Bot + API Integration | R01 | Technical Architect | 30 | 879.07 | 26372.1 | 1109548.1 | 26.22%
13 | Phase 2 - Einstein Bot + API Integration | R02 | Technical Consultant | 40 | 715.66 | 28626.4 | 1138174.5 | 26.9%
13 | Phase 2 - Einstein Bot + API Integration | R03 | Technical Consultant (Security) | 20 | 715.66 | 14313.2 | 1152487.7 | 27.24%
13 | Phase 2 - Einstein Bot + API Integration | R06 | Project Manager | 20 | 879.07 | 17581.4 | 1170069.1 | 27.65%
14 | Phase 2 - Einstein Bot + API Integration | R01 | Technical Architect | 30 | 879.07 | 26372.1 | 1196441.2 | 28.28%
14 | Phase 2 - Einstein Bot + API Integration | R02 | Technical Consultant | 40 | 715.66 | 28626.4 | 1225067.6 | 28.95%
14 | Phase 2 - Einstein Bot + API Integration | R03 | Technical Consultant (Security) | 20 | 715.66 | 14313.2 | 1239380.8 | 29.29%
14 | Phase 2 - Einstein Bot + API Integration | R06 | Project Manager | 20 | 879.07 | 17581.4 | 1256962.2 | 29.71%
15 | Phase 2 - Einstein Bot + API Integration | R01 | Technical Architect | 30 | 879.07 | 26372.1 | 1283334.3 | 30.33%
15 | Phase 2 - Einstein Bot + API Integration | R02 | Technical Consultant | 40 | 715.66 | 28626.4 | 1311960.7 | 31.01%
15 | Phase 2 - Einstein Bot + API Integration | R03 | Technical Consultant (Security) | 20 | 715.66 | 14313.2 | 1326273.9 | 31.34%
15 | Phase 2 - Einstein Bot + API Integration | R06 | Project Manager | 20 | 879.07 | 17581.4 | 1343855.3 | 31.76%
16 | Phase 3 - UX Research & Refinement | R01 | Technical Architect | 20 | 879.07 | 17581.4 | 1361436.7 | 32.18%
16 | Phase 3 - UX Research & Refinement | R04 | Experience Architect | 40 | 879.07 | 35162.8 | 1396599.5 | 33.01%
16 | Phase 3 - UX Research & Refinement | R06 | Project Manager | 15 | 879.07 | 13186.05 | 1409785.55 | 33.32%
17 | Phase 3 - UX Research & Refinement | R01 | Technical Architect | 20 | 879.07 | 17581.4 | 1427366.95 | 33.73%
17 | Phase 3 - UX Research & Refinement | R04 | Experience Architect | 40 | 879.07 | 35162.8 | 1462529.75 | 34.56%
17 | Phase 3 - UX Research & Refinement | R06 | Project Manager | 15 | 879.07 | 13186.05 | 1475715.8 | 34.88%
18 | Phase 3 - UX Research & Refinement | R01 | Technical Architect | 20 | 879.07 | 17581.4 | 1493297.2 | 35.29%
18 | Phase 3 - UX Research & Refinement | R04 | Experience Architect | 40 | 879.07 | 35162.8 | 1528460 | 36.12%
18 | Phase 3 - UX Research & Refinement | R06 | Project Manager | 15 | 879.07 | 13186.05 | 1541646.05 | 36.43%
19 | Phase 3 - UX Research & Refinement | R01 | Technical Architect | 20 | 879.07 | 17581.4 | 1559227.45 | 36.85%
19 | Phase 3 - UX Research & Refinement | R04 | Experience Architect | 40 | 879.07 | 35162.8 | 1594390.25 | 37.68%
19 | Phase 3 - UX Research & Refinement | R06 | Project Manager | 15 | 879.07 | 13186.05 | 1607576.3 | 37.99%
20 | Phase 3 - UX Research & Refinement | R01 | Technical Architect | 20 | 879.07 | 17581.4 | 1625157.7 | 38.41%
20 | Phase 3 - UX Research & Refinement | R04 | Experience Architect | 40 | 879.07 | 35162.8 | 1660320.5 | 39.24%
20 | Phase 3 - UX Research & Refinement | R06 | Project Manager | 15 | 879.07 | 13186.05 | 1673506.55 | 39.55%
TOTAL |  |  |  | 2045 |  | 1673506.55

## Resumo por Fase
RESUMO POR FASE - ESCOPO BASE
Fase | Descrição | Semanas | Total Horas | Custo (R$) | % Total
Phase 0 | Discovery Resolution | 3 | 270 | 237348.9 | 5.609%
Phase 1 | Foundation & ORG Setup | 4 | 520 | 411361.6 | 9.722%
Phase 2 | Einstein Bot + API Integration | 8 | 880 | 695144.8 | 16.43%
Phase 3 | UX Research & Refinement | 5 | 375 | 329651.25 | 7.791%
TOTAL |  | 20 | 2045 | 1673506.55

## Planilha1
ROLE | HORAS | RATE | VALOR | VALOR c/ Imp | Semana 1 | Semana 2 | Semana 3 | Semana 4 | Semana 5 | Semana 6 | Semana 7 | Semana 8 | Semana 9 | Semana 10 | Semana 11 | Semana 12 | Semana 13
[5 empty] | Discovery | Discovery | Setup Org | Sprint 1 |  |  | Sprint 2 |  |  | UAT | UAT | Scale | Scale
Technical Consultant | 360 | 668.78 | 240760.8 | 257635.9551 |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 20 | 20 | 20 | 20
Solution Consultant | 440 | 573.98 | 252551.2 | 270252.7555 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 20 | 20 | 20 | 20
Experience Architect | 120 | 789.88 | 94785.6 | 101429.2135 | 20 | 20 | 20 | 20 | 20 | 20
Solution Architect | 240 | 789.88 | 189571.2 | 202858.427 | 40 | 40 | 40 | 20 | 20 | 20 | 20 | 20 | 20
Technical Architect | 240 | 821.49 | 197157.6 | 210976.565 | 40 | 40 | 40 | 20 | 20 | 20 | 20 | 20 | 20
Project Manager | 260 | 789.88 | 205368.8 | 219763.2959 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
Quality Assurance Consultant | 240 | 573.98 | 137755.2 | 147410.5939 |  |  |  | 40 | 40 | 40 | 40 | 40 | 40
| 1900 |  | 1317950.4 | 1410326.8058
13.68%
ROLE | HORAS | RATE | VALOR | VALOR c/ Imp | Semana 1 | Semana 2 | Semana 3 | Semana 4 | Semana 5 | Semana 6 | Semana 10 | Semana 11 | Semana 12 | Semana 13
[5 empty] | Discovery | Discovery | Setup Org | Sprint 1 |  |  | UAT | UAT | Scale | Scale
Technical Consultant | 240 | 668.78 | 160507.2 | 171757.3034 |  |  | 40 | 40 | 40 | 40 | 20 | 20 | 20 | 20
Solution Consultant | 320 | 573.98 | 183673.6 | 196547.4585 | 40 | 40 | 40 | 40 | 40 | 40 | 20 | 20 | 20 | 20
Experience Architect | 120 | 789.88 | 94785.6 | 101429.2135 | 20 | 20 | 20 | 20 | 20 | 20
Solution Architect | 180 | 789.88 | 142178.4 | 152143.8202 | 40 | 40 | 40 | 20 | 20 | 20
Technical Architect | 180 | 821.49 | 147868.2 | 158232.4238 | 40 | 40 | 40 | 20 | 20 | 20
Project Manager | 200 | 789.88 | 157976 | 169048.6891 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
Quality Assurance Consultant | 120 | 573.98 | 68877.6 | 73705.297 |  |  |  | 40 | 40 | 40
| 1360 |  | 955866.6 | 1022864.2055
14.71%
ROLE | HORAS | RATE | VALOR | VALOR c/ Imp | Semana 1 | Semana 2 | Semana 3 | Semana 4 | Semana 5 | Semana 6 | Semana 7 | Semana 8 | Semana 9 | Semana 10 | Semana 13
[5 empty] | Discovery | Discovery | Setup Org | Sprint 1 |  | Sprint 2 |  | UAT | UAT | Scale | Scale
Technical Consultant | 280 | 668.78 | 187258.4 | 200383.5206 |  |  | 40 | 40 | 40 | 40 | 40 | 20 | 20 | 20 | 20
Solution Consultant | 360 | 573.98 | 206632.8 | 221115.8909 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 20 | 20 | 20 | 20
Experience Architect | 140 | 789.88 | 110583.2 | 118334.0824 | 20 | 20 | 20 | 20 | 20 | 20 | 20
Solution Architect | 200 | 789.88 | 157976 | 169048.6891 | 40 | 40 | 40 | 20 | 20 | 20 | 20
Technical Architect | 200 | 821.49 | 164298 | 175813.8042 | 40 | 40 | 40 | 20 | 20 | 20 | 20
Project Manager | 220 | 789.88 | 173773.6 | 185953.5581 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
Quality Assurance Consultant | 160 | 573.98 | 91836.8 | 98273.7293 |  |  |  | 40 | 40 | 40 | 40
| 1560 |  | 1092358.8 | 1168923.2745
14.1%

## Resumo por Recurso
RESUMO POR RECURSO - ESCOPO BASE
ID | Recurso | Taxa R$/Hora | Fases Ativas | Total Horas | Custo Total (R$) | % Total
R01 | Technical Architect | 879.07 | Phase 0, Phase 1, Phase 2, Phase 3 | 560 | 492279.2 | 11.63%
R02 | Technical Consultant | 715.66 | Phase 1, Phase 2 | 480 | 343516.8 | 8.119%
R03 | Technical Consultant (Security) | 715.66 | Phase 1, Phase 2 | 280 | 200384.8 | 4.736%
R04 | Experience Architect | 879.07 | Phase 3 | 200 | 175814 | 4.155%
R05 | Technical Architect (Phase 0) | 879.07 | Phase 0 | 120 | 105488.4 | 2.493%
R06 | Project Manager | 879.07 | Phase 0, Phase 1, Phase 2, Phase 3 | 405 | 356023.35 | 8.414%
TOTAL |  |  |  | 2045 | 1673506.55

## Investimento Total
INVESTIMENTO TOTAL - ESCOPO BASE
Projeto | DATAPREV-SEFIN-CE v2.0
Escopo | Service Cloud + Einstein Bot + WhatsApp (ESCOPO BASE - sem ADD-ONs)
Timeline | 20 semanas (cenário médio)
Total Horas | 2,045 horas
Taxa Architect (R$/hora) | R$ 879.07
Taxa Developer (R$/hora) | R$ 715.66
INVESTIMENTO TOTAL | R$ 1,673,506.55
ROM Referência Low | R$ 1.583.232,00
ROM Referência High | R$ 4.231.269,00
Investimento Calculado | R$ 1,673,506.55
% do ROM High | 39.6%
Observações
Investimento calculado baseado em horas estimadas por fase
ROM considera riscos, complexidade e margem de contingência
ADD-ONs E07 (KB) e E08 (MC) não incluídos neste cálculo
Licenças Salesforce não incluídas (cliente contrata diretamente)