## Epics
Epic ID | Epic Name | Description | Confidence | Depends On
E01 | Posto de Trabalho do Atendente no Slack | O atendente do guichê passa a trabalhar dentro do Slack: canais dedicados por serviço, Canvas fixado com a regra/conhecimento vigente (substitui o conhecimento isolado hoje disperso entre atendentes), e Agentforce disponível em contexto para dúvidas do próprio fluxo de atendimento. | Confirmed
E02 | Escalonamento em Tempo Real (Transbordo via Huddle) | Quando o caso foge do script (falha biométrica, documento divergente, dúvida fora do Canvas), o atendente aciona um huddle Slack com um especialista sem deixar a cadeira — substitui a coordenação hoje feita em grupos pessoais de WhatsApp, fora da governança institucional. | Confirmed | E01
E03 | Roteamento de Capacidade Ociosa Entre Postos | Visibilidade e roteamento de casos entre os 244 postos físicos + 900 totens de autoatendimento, direcionando demanda para onde há capacidade ociosa, sem necessidade de contratar mais atendentes. | Assumed
E04 | Workflow de Contingência (Sistema Fora do Ar) | Workflow Builder dispara aviso automático aos atendentes/postos quando um sistema crítico cai (ex.: sistema do Detran), evitando atendimento sem visibilidade do problema. | Confirmed
E05 | Governança, Adoção e Change Management (Fase 1) | Papéis e responsabilidades, treinamento dos atendentes, política de canais e critérios de adoção do Slack como posto de trabalho — confirmado explicitamente em escopo pelo usuário na sessão de discovery. | Confirmed
E06 | Pré-Atendimento Digital via WhatsApp | A cidadã recebe convite de triagem/pré-atendimento pelo WhatsApp antes do dia marcado no posto, reduzindo o volume de casos que chegam ao balcão sem preparo prévio (Jornada 02 do deck de plataforma). | Assumed
E07 | Validação Remota de Documentos por Atendente Ocioso | Um atendente ocioso em outro posto valida documentos à distância via Slack para acelerar o atendimento presencial em curso em outro balcão (extensão das Jornadas 01/03). | Assumed | E01; E02; E03; E06
E08 | Atendimento Agêntico 24/7 (Human-in-the-Loop) | Um agente de IA atende pelo WhatsApp 24 horas por dia, com supervisão humana, escalando para um atendente humano quando o caso exige (Jornada 04 do deck de plataforma). | Assumed
E09 | Plataforma de Integração MuleSoft (Gov.br, Biometria, Legado, Sistema Semântico, T7) | Camada de integração MuleSoft ligando a Plataforma Salesforce Headless a gov.br, biometria estadual, sistemas legados da Prodesp, 'Sistema Semântico' e 'T7' — confirmada visualmente no diagrama de arquitetura do deck de plataforma. Identidades exatas de Sistema Semântico, 'Atendimento' e T7 permanecem abertas (ver Open Questions no Discovery Brief). | Unknown
E10 | Analytics e Previsibilidade de Atendimento | Cruzamento de dados em tempo real via Data 360, algoritmo preditivo de tempo de espera, e retroalimentação analítica dos agentes de IA para melhoria contínua do atendimento. Os KPIs de exemplo (15/16/17 minutos) são ilustrativos e não validados pelo cliente. | Assumed | E03

## Gap Analysis
Gap ID | Category | Gap/Question | Impact/Notes
G0101 | Missing Requirement | Modelo de propriedade e estrutura de conteúdo do Canvas fixado por canal (quem autora, aprova e mantém a regra/conhecimento vigente; taxonomia de canais por serviço) não está definido. | Bloqueador de design: sem esse modelo, o Canvas corre o risco de reproduzir o mesmo conhecimento disperso e desatualizado que a epic pretende substituir. Já sinalizado como open item no Discovery Brief e como [assumption] nos kb_sources da epic.
G0102 | Potential Risk | As 1.800 licenças Slack Enterprise Plus já validadas cobrem a Sala de Situação (monitoramento digital), não o headcount real de atendentes nos 244 postos físicos + 900 totens de autoatendimento que esta epic pretende colocar no Slack. | Risco direto de dimensionamento e custo de licenciamento incremental; sem esse número, `estimate`/`commercials` não conseguem validar cobertura de licença para o rollout da Fase 1. Confirmado pelo usuário como não dimensionado ainda.
G0103 | Missing Requirement | Escopo real do piloto (qual posto, quantos atendentes, quais serviços) está totalmente aberto — os nomes citados (Ana, Anderson, Felipe, Santo Amaro, CIN) são storyboard do material de venda, não um piloto combinado com a Prodesp. | Sem posto/serviço/headcount definidos, a epic não tem unidade de medida para sizing, sequenciamento de rollout ou critério de sucesso do piloto.
G0104 | Logical Gap | O workflow de 'roteamento de casos para postos com capacidade ociosa' não define o critério de capacidade ociosa (fila, tempo médio de atendimento, disponibilidade do atendente) nem a fonte de dados que alimenta essa decisão. | Sem critério objetivo, o roteamento entre postos vira julgamento manual do atendente, esvaziando o valor de automação citado no objetivo de negócio (visibilidade de capacidade ociosa sem contratar gente nova).
G0105 | Ambiguity | O 'huddle com especialista sem sair da cadeira' não identifica quem é o especialista (outro atendente sênior, back-office Prodesp, suporte de sistema, ou Salesforce) nem o SLA/disponibilidade esperada desse papel. | Sem essa definição, o desenho de escalonamento por huddle não tem persona de destino nem expectativa de tempo de resposta — afeta diretamente a promessa de reduzir o tempo de 'preciso de ajuda' até o cidadão atendido.
G0106 | Logical Gap | O 'workflow de aviso quando um sistema cai' (contingência) não especifica a fonte do sinal de indisponibilidade (monitoramento automático de sistema legado, ou relato manual do atendente) nem o canal/audiência do broadcast. | Sem fonte de sinal definida, o workflow de contingência depende de detecção manual, o que reduz a velocidade de resposta que a epic promete resolver (hoje: atendente levanta, usa celular pessoal ou pede para voltar).
G0107 | Potential Risk | A premissa de design de que nenhum dado biométrico bruto trafegará nos canais de texto do Slack (apenas relato textual do problema) ainda não é um controle implementado — é uma intenção a validar. | Risco de compliance LGPD/segurança se o controle não for tecnicamente reforçado (ex.: DLP, guardrail de Agentforce) e depender apenas de disciplina do atendente. Relevante porque a coordenação institucional em Slack é a proposta de valor central de LGPD desta epic.
G0108 | Missing Requirement | Guardrails formais do agente Agentforce-em-canal (papel, dados acessíveis, ações permitidas, o que ele não deve fazer) ainda não foram definidos para o caso de uso do guichê — o framework de 5 atributos e o risco de 'revelar PII a usuário não autenticado' (padrão nomeado em `knowledge/staar-agentforce-governance-guardrails.md`) ainda não foi aplicado a este agente. | Sem guardrails formais, o agente em contexto de atendimento (dúvidas do próprio fluxo) corre o mesmo risco de vazamento de PII/dados sensíveis nomeado como failure mode padrão da Salesforce PS para agentes Agentforce. [extends: staar-agentforce-governance-guardrails.md]
G0109 | Missing Requirement | Owner de governança de agentes de IA do lado Prodesp ainda não identificado — quem aprova o conteúdo do Canvas, quem monitora o comportamento do Agentforce em canal, quem responde por incidentes de guardrail. | Confirmado pelo usuário como não identificado ainda. Mais crítico à medida que o Agentforce entra em contexto de atendimento real (não apenas monitoramento), mesmo na Fase 1 tática.
G0110 | Missing Requirement | Governança/Centro de Excelência (CoE) ou função de change management para a operação contínua do posto de trabalho Slack — política de canais, ciclo de vida de canais por serviço, versionamento do Canvas — está em escopo desta epic/SOW, ou é responsabilidade do cliente (Prodesp)? | Pergunta de disciplina voltada ao comprador. Governança e adoção (papéis, treinamento, política de canais) já foram confirmadas em escopo pelo usuário no discovery, mas a estrutura operacional contínua (quem mantém depois do go-live) ainda não foi detalhada. Ver `knowledge/staar-agentforce-governance-guardrails.md` (modelo de CoE) como referência, se o cliente optar por trazer isso para dentro do escopo.
G0111 | Missing Requirement | Pesquisa de experiência do usuário / desenho de serviço (UX research / service design) para o novo posto de trabalho do atendente — uma superfície de trabalho diária inteiramente nova, substituindo ferramentas e conhecimento hoje dispersos — está em escopo desta epic, ou o desenho de canais/Canvas/huddle será feito sem validação direta com atendentes reais? | Pergunta de disciplina voltada ao comprador. Sem esse trabalho, o desenho de canais-por-serviço, estrutura de Canvas e fluxo de huddle corre risco de não refletir o comportamento real do atendente no guichê, ameaçando adoção.
G0112 | Ambiguity | Identidade dos sistemas legados citados no diagrama de arquitetura-alvo (T7, Sistema Semântico, 'Atendimento') não está resolvida. O usuário decidiu deprioritizar o fechamento do T7 no discovery, mas sinalizou que seria bom resolver antes do desenho técnico da Fase 1 especificamente. | Ainda que a integração pesada com esses sistemas seja majoritariamente Fase 2 (MuleSoft), o material cita 'T7' como fonte de dúvidas dentro do próprio fluxo de atendimento do guichê (Fase 1) — se o Agentforce-em-canal precisar consultar esse sistema, a identidade não resolvida bloqueia o design técnico, não apenas o discovery.
G0113 | Potential Risk | Champion/patrocinador executivo da Balcão V2 no lado Prodesp ainda não identificado — diferente da Frente A de licenças (que tem Thiago Waltz como ponto de entrada). | Risco de prontidão do cliente: sem patrocinador executivo claro para o piloto tático, decisões de escopo de piloto (posto, serviço, headcount — ver G0103) e adoção de política de canais podem ficar sem dono do lado do cliente.
G0114 | Potential Risk | Documento de posicionamento LGPD/Trust sobre localização de inferência do Agentforce — existência confirmada pelo usuário, mas sem documento/URL específico localizado ou citável; pesquisa web dedicada não encontrou orientação pública substituta. | Se a epic depender de afirmar postura de compliance sobre onde a inferência de IA ocorre (relevante dado que o agente estará em contexto de atendimento real, não apenas monitoramento), esse gap precisa ser fechado com o time de conta antes de qualquer entregável cliente-facing assumir postura de compliance.
G0115 | Logical Gap | O material de venda de origem (BSA) não detalha como o atendente sinaliza start/end de um caso dentro do canal (abertura/fechamento de thread, status do atendimento) — não há modelo de ciclo de vida do 'caso' dentro do canal Slack. | Sem esse modelo, fica ambíguo como medir o objetivo de negócio citado (reduzir tempo do 'preciso de ajuda' até a cidadã ser atendida) — não há evento de início/fim claro a instrumentar.
G0301 | Capability Gap | No real-time capacity signal source has been identified for any of the 244 postos or 900 totens. Discovery describes the desired outcome ("Redirecionamento dinâmico: elimine filas em postos superlotados utilizando a capacidade ociosa de retaguarda de outras unidades") but names no system, feed, or manual process that reports which postos/attendants/totens are idle right now. The epic's kb_sources field already flags this as an assumption — no KB document covers a workforce-availability or queue-state data source for this account. | This is the load-bearing dependency for the entire epic: without a capacity signal, there is nothing to route against. Until a source is named (existing SF/PRODESP system, new instrumentation, or manual self-report in Slack), E03 cannot be designed, sized, or built — it can only be assumed. Should be treated as a pre-build blocker for Fase 1, not a detail to resolve during build. OWNERSHIP RESOLVED in grill 2026-09-22 (user-endorsed, see G0315/G1003): E03 owns building this foundation, not E10. The underlying technical question — whether any occupancy/queue signal already exists anywhere at Prodesp, even outside Salesforce — remains Unknown, pending client confirmation.
G0302 | Potential Risk | If no automated capacity signal exists, the only fallback is attendants self-reporting availability/idle status manually inside Slack (e.g., a status field, a channel post, a Canvas toggle). This turns a systems-integration capability into a change-management and adoption problem, and the signal quality degrades if attendants don't self-report consistently. | Risk to the outcome metric ("sem necessidade de contratar mais atendentes") — a stale or gamed manual signal could route cases to postos that are not actually idle, defeating the purpose. Adoption/governance already confirmed in scope per the discovery brief, but this specific mechanic (manual capacity self-report) has not been named or agreed with the client.
G0303 | Missing Requirement | "Capacidade ociosa" is undefined operationally. Is it: (a) attendant headcount currently unassigned, (b) queue length/wait time per posto, (c) service-type-specific availability (idle for CNH but saturated for CIN), or (d) totem throughput/availability? The epic description bundles postos and totens together but totens are self-service kiosks, not staffed capacity — their role in a "capacity" model is unclear. | Without a definition, there is no way to size the data model, the routing logic, or the UI surface (what an attendant sees when deciding to route a case). Blocks design and estimation.
G0304 | Ambiguity | The two source decks describe two different "idle capacity" mechanics that could both plausibly be what E03 means: Corte 1 (Jackson) describes an idle colleague joining a huddle/conference for specialist escalation at the same case ('o colega ocioso do outro posto' backing up the current attendant); Corte 2 (Vinicius) describes 'Felipe,' an idle attendant elsewhere, pulling entire cases for remote document validation before or instead of an in-person visit. E03's description ('roteamento de casos entre os 244 postos + 900 totens, direcionando demanda para onde há capacidade ociosa') does not specify which of these two mechanics — augment-in-place via huddle, or reassign-the-case-elsewhere — it is building. | These imply materially different technical builds (presence-aware huddle routing vs. case/queue reassignment across postos) and different governance/LGPD handling (case data crossing posto boundaries vs. staying local). Needs client confirmation before design; currently assumed to be case-reassignment based on the epic's own wording ("roteamento de casos"), but that reading conflicts with the Corte 1 huddle framing in the same source material.
G0305 | Logical Gap | The stated business objective — "sem necessidade de contratar mais atendentes" — has no baseline. Current idle-time rate per posto, current overflow/queue-abandonment rate, and current headcount distribution across the 244 postos are all unknown. The discovery brief explicitly flags the cited wait-time KPIs (15/16/17 min) as illustrative and unvalidated by the client. | Without a baseline, the outcome cannot be measured (no before/after), and no metric block can be attached to this capability without inventing numbers. Relevant to `design`/`estimate` sizing and to any success-criteria language in the SOW.
G0306 | Missing Requirement | No decision rule is defined for when a case should be routed to another posto's idle capacity versus handled locally (e.g., distance/travel burden to the citizen if it means physical redirection, service-type match, case complexity threshold, SLA/wait-time trigger). | Needed to scope the routing logic itself; without it, "routing" is a label with no algorithm behind it. Also affects whether this is rules-based (Flow/Omni-Channel-style) or requires a more complex matching/queueing engine.
G0307 | Missing Requirement | The role of the 900 self-service totens in this epic is unspecified. Are totens a demand source that triggers routing (e.g., a totem detects it cannot resolve a case and needs to signal an idle human elsewhere), a capacity sink (idle totens absorb simple cases redirected from crowded counters), both, or neither — with "totens" in the epic description simply inherited from the corrected volumetria figure (244 postos + 900 totens) rather than a deliberate scope choice? | If totens have no real role in this capability, the epic description overstates scope inherited from a volumetria correction (see discovery brief) rather than a discovery finding. Needs a scope-narrowing confirmation or a concrete totem-routing requirement.
G0308 | Missing Requirement | The discovery brief's Open Questions already flag a Slack license sizing gap: 1,800 Slack Enterprise Plus licenses are validated for the Sala de Situação (digital-channel monitoring), not for attendant headcount across the 244 postos. E03's routing mechanic depends on idle attendants being reachable/visible inside Slack across the whole network — but if attendant headcount at the 244 postos exceeds validated licensing, the capability has no user base to route into. | Direct blocker specific to E03 (more so than to other Fase 1 epics, since routing requires network-wide attendant presence, not just single-posto usage). Needs headcount-vs-license reconciliation with the client before Fase 1 design is finalized.
G0309 | Potential Risk | Real-time capacity signaling across 244 physical postos assumes reliable network/device connectivity at each site. No discovery source addresses infrastructure state (connectivity, device availability, uptime) at the counter level across the network. | If connectivity is inconsistent at a meaningful share of postos, a real-time signal (whichever source is eventually named per G0301) may be unreliable exactly where it's most needed (busy/overloaded sites). Worth a discovery question before committing to a real-time (vs. near-real-time/batch) design.
G0310 | Potential Risk | A capacity/idle-time signal that surfaces which attendants are not currently busy is, functionally, individual performance/utilization monitoring data. Combined with the fact that no AI/data governance owner has been identified on the PRODESP side (per the discovery brief's Open Questions) and that current cross-posto coordination is informally described as happening "fora da LGPD," there is a labor-relations and data-governance exposure in formalizing an idle-time signal without an agreed policy on how that data is used, retained, and who sees it. | Could surface as a stakeholder/union sensitivity during rollout even if technically compliant. Should be raised with the client's HR/governance stakeholders before broad deployment, not discovered during pilot.
G0311 | Assumption | The epic assumes routing is achievable without new headcount purely by better visibility/redistribution of existing idle time. This assumes idle time is (a) real and material in volume across the network, and (b) fungible — i.e., an idle attendant at Posto B can actually perform work originating from Posto A's case (same systems access, same service-type training/certification, same authority to act on another unit's citizen record). | If service-type specialization or system-access boundaries prevent cross-posto case handling, the epic's core premise (idle capacity is interchangeable) breaks down regardless of whether a capacity signal exists. Worth validating with an operations stakeholder, not just a technical one.
G0312 | Missing Requirement | Has any experience/service design discipline (UX research, service design, or content design) been engaged to define how a case-routing/reassignment moment is actually experienced by the citizen (if it involves any wait or hand-off) and by the receiving idle attendant (case handoff context, continuity of the citizen's history)? No such discipline signal appears in discovery for this epic. | Routing changes who serves the citizen and how continuity is preserved across a hand-off — a service-design/UX gap here risks a technically-working capability that citizens or attendants experience as confusing or worse than today's workaround (personal WhatsApp groups).
G0313 | Missing Requirement | Who on the PRODESP side owns governance for a cross-posto capacity/routing data model — i.e., a data steward or CoE function accountable for how idle-time/case-routing data is defined, who can see it, and how change requests to the routing logic are governed over time? The discovery brief already notes no AI-governance owner has been identified account-wide; this asks specifically whether a narrower data-stewardship owner exists for this capability's data. | Without a named owner, routing-logic changes and capacity-signal definitions risk drifting informally (mirroring today's ungoverned WhatsApp-group workaround this epic is meant to replace).
G0314 | Logical Gap | E03 is scoped under Fase 1 (tactical, no heavy integration), yet the Fase 2 deck's "Felipe" idle-attendant mechanic — remote document validation triggered by pre-service WhatsApp outreach — depends on the same underlying idle-capacity concept and is explicitly Fase 2 (MuleSoft-integrated) scope per `decisions/0002`. It is not clear whether Fase 1's E03 is meant to build a standalone, lighter version of capacity visibility/routing that Fase 2 later extends, or whether E03's real design only becomes coherent once Fase 2's remote-validation mechanic exists. | Affects roadmap sequencing and whether E03 can be considered complete/valuable on its own in Fase 1, or is really a foundation piece whose payoff only lands in Fase 2. Relevant to `roadmap` and `design` phasing decisions.
G0201 | Missing Requirement | There is no defined specialist directory or routing logic mapping an escalation trigger (biometric failure, document mismatch, out-of-Canvas question) to the correct specialist domain (Detran, IIRGD, Instituto da Identidade, TI, etc.). The epic's own kb_sources tag this as '[assumption: a definir em design]'. | Without this, the huddle mechanism has no way to route a case to the right specialist channel — the attendant either guesses or the design must hard-code a manual channel-per-issue-type mapping before build. Blocks E02 design and any staffing/on-call conversation with the specialist-owning institutions.
G0202 | Missing Requirement | No specialist availability / on-call model is defined. The mechanic assumes a specialist is reachable in real time ("entra em huddle... resolvida em minutos"), but there is no confirmed staffing model, coverage hours, or fallback path for when no specialist answers the huddle request. | If a huddle goes unanswered, the citizen is back to 'volte depois' — the exact failure state the epic claims to fix. Needs a defined SLA + escalation-of-escalation path (e.g., queue, secondary specialist, or supervisor) before this can be presented as reliably faster than today's WhatsApp workaround.
G0203 | Logical Gap | The epic's core value claim is that this replaces WhatsApp coordination that is 'fora da LGPD — sem histórico, sem auditoria' with an auditable, institutional channel. The source material confirms the Slack ticket and channel are logged and auditable, but does not confirm whether the huddle itself (a live voice call) is recorded, transcribed, or otherwise retained. If the specialist's actual guidance is only spoken and not captured, the audit-trail claim holds for 'a request was made and a ticket exists' but not for 'what was actually said/advised.' | This is the load-bearing LGPD claim for the whole epic. If huddle audio isn't retained, the compliance narrative to PRODESP needs to be scoped down to 'auditable request trail,' not 'auditable coordination' — unless Slack huddle recording/transcription is explicitly designed in.
G0204 | Source Conflict | The source material flags that the Flex Credit cost of the ticket/huddle-opening step is 40 Flex if triggered by Agentforce classic, but jumps to a different (200 Flex) measure if the channel 'door' is a Slackbot instead — and the source itself says this ambiguity 'não é medição desta conta' (not yet resolved). It is unresolved which mechanism (Slackbot vs. Agentforce classic) actually opens the ticket/huddle in this design. | This is a build-time and cost-model fork, not just a documentation nuance: Slackbot and Agentforce-classic are different implementation paths with different Flex consumption. Needs resolution before `design`/`estimate` treat E02's automation mechanism as settled.
G0205 | Potential Risk | The discovery brief states a design premise that no raw biometric data should transit Slack text channels — but a huddle is a live voice call, and the walkthrough example has the specialist verbally referencing the citizen's specific case and biometric collection issue in real time. No guardrail is defined for what a specialist may or may not say/ask about the citizen verbally during a huddle. | The text-channel guardrail does not automatically extend to voice; if unaddressed, the epic could introduce a PII/LGPD exposure path in exactly the channel (huddle) it introduces to fix governance. Needs an explicit guardrail statement in design, per the STAAR governance framework's People/Business/Technology/Data lens.
G0206 | Capability Gap | Detran, IIRGD, and Instituto da Identidade are separate government entities from PRODESP, not PRODESP staff. No identity/access model is defined for how their specialists join a huddle inside PRODESP's Slack Enterprise Plus org — as licensed guest users, via Slack Connect, or some other cross-agency provisioning path. | Slack Connect / external-guest provisioning has its own licensing, governance, and security review implications that are absent from any discovery source. This is a capability/architecture gap that affects both E02's design and E05's governance scope, and should be resolved before any pilot posto is chosen.
G0207 | Ambiguity | It is unclear whether the huddle is always manually initiated by the attendant, or whether Agentforce can also proactively suggest/trigger the huddle when its own suggested fixes fail. The Canvas-lookup step and the huddle-open step read as sequential in the walkthrough, but the actual trigger UX (button, slash command, natural-language request) is undefined. | Affects the attendant-facing UX design and the Agentforce action definition (Role/Actions per the 5-attributes framework) — needs to be pinned down in `design`, not left implicit.
G0208 | Missing Requirement | The only concretely described 'foge do script' trigger scenario is the CIN biometric-capture failure (explicitly labeled storyboard). No taxonomy exists yet of the full set of escalation-trigger categories across other Poupatempo service lines (CNH, exames, etc.) that E02's routing table would need to cover. | Without this taxonomy, the specialist-directory/routing design (G0201) can only be scoped for one illustrative service, not sized for the pilot's actual service mix. Needed before `requirements`/`design` can size E02 realistically.
G0209 | Assumption | No validated SLA or target resolution time exists for the huddle escalation path. The deck's framing ('resolvida em minutos') and the 15/16/17-minute wait-time KPIs elsewhere in the material are both explicitly flagged in the discovery brief as illustrative/unvalidated, not a client-confirmed baseline. | Any success metric or before/after claim for E02 in a client-facing artifact must carry the illustrative-KPI caveat already established in the discovery brief; do not let a future `design`/`narratives` pass silently promote these numbers to fact.
G0210 | Missing Requirement | [Experience design discipline gap] Has the citizen-facing experience during an active huddle been mapped? The attendant is on a live voice call with a specialist while the citizen stands at the counter — what does the citizen see/hear, and has the attendant's simultaneous cognitive load (monitoring Canvas + huddle + citizen) been validated through service design or UX research, rather than assumed from the storyboard alone? | Signal only, not a mandate — but the storyboard is explicitly illustrative, so the actual in-huddle citizen and attendant experience is unvalidated. Worth raising to the client as a discovery question before pilot design locks the interaction pattern.
G0211 | Missing Requirement | [Governance discipline gap] Who, on the PRODESP side, owns and maintains the specialist directory and routing rules over time (as specialist orgs, staffing, or regulations change)? The project's own open questions note that no AI-governance owner has been identified yet, and E02's routing logic would need an accountable steward once built, not just a one-time design decision. | Signal only, not a mandate — but without an owner, the routing table designed in E02 has no maintenance path and will drift out of date. Worth raising as a buyer-facing question alongside the broader AI-governance-owner gap already logged in the discovery brief's Open Questions.
G0212 | Potential Risk | The Flex Credit consumption model for the escalation mechanic (40 vs. 200 Flex per request, per G0204) rests partly on an unconfirmed internal committee remark that the account's Flex allocation is 'ilimitado' — the discovery brief explicitly treats that as a hypothesis, not a fact of the Digital Wallet contract. | If huddle/ticket volume scales across 244 postos and the 'unlimited Flex' assumption is wrong, there is a real cost-exposure risk behind this specific automation mechanic. Relevant to `estimate`/`commercials` sizing, not just design.
G0213 | Capability Gap | The walkthrough example has the specialist give verbal, step-by-step device instructions with no screen-share, device-diagnostic, or system-state visibility for the specialist — purely voice-guided. No design decision confirms whether this verbal-only model is sufficient for more complex hardware/system failures beyond the biometric-capture example. | For simple procedural fixes, voice-only may be adequate; for a genuine system outage or hardware fault, it may not be — worth flagging as a design boundary question rather than assuming voice-only huddle covers every escalation case E02 is meant to handle.
G0401 | Source Conflict | The source deck's own visual implies the outage-broadcast workflow is triggered by automated detection of a system going down (Workflow Builder fires on a 'Sistema fora — Ativo' event), but the Discovery Brief commits Phase 1 to 'nenhuma integração pesada nova' — no new integration into Detran, IIRGD, or other backend systems. Without a monitoring integration, nothing exists to auto-detect the outage; the workflow's actual trigger must be a human declaring the outage (e.g., filling a form or posting in a channel), which is a materially different (and less complete) mechanism than the deck depicts. | This is the single most load-bearing ambiguity in E04 — it determines whether the build is a simple manual-trigger Slack workflow (small, no-code) or implies a monitoring/integration dependency that Phase 1 has explicitly ruled out. Must be resolved before design/estimate; if left as-is, the acceptance criteria risk overstating what a no-integration Phase 1 can actually detect.
G0402 | Missing Requirement | No role or permission model is defined for who is authorized to declare a system-down event and activate the contingency broadcast (a supervisor? any attendant? a designated ops channel owner?). Absent this, the workflow has no gate against false or duplicate activations across 244+ postos. | Needed for both the build (who can trigger the Workflow Builder flow) and for adoption/training (E05) — an unrestricted trigger risks alert fatigue or conflicting simultaneous declarations from multiple postos.
G0403 | Ambiguity | The epic description names 'sistema do Detran' only as an example ('ex.:') of a critical system whose outage should trigger the workflow. No enumerated list of which systems qualify (Detran, IIRGD, biometria estadual, Sistema Semântico, T7, 'Atendimento' — several of these identities are themselves still open per the Discovery Brief) exists to scope what this workflow must cover. | Without a confirmed system list, build scope for 'quais sistemas disparam contingência' is undefined — risks scope creep (every system outage expected to trigger this) or under-coverage (a critical system left out).
G0404 | Logical Gap | The deck states today's core pain as 'ninguém sabe se é local ou geral' (nobody knows if an outage is local to one posto or systemwide) — but the described solution broadcasts the same alert to '100% dos postos' unconditionally, regardless of whether the underlying outage is local or general. No design decision confirms whether the workflow needs to scope/segment the broadcast (by região, by service, or by confirmed blast radius) or whether an always-global broadcast is an acceptable answer to the stated problem. | If the real driver is knowing scope of impact, and the design just floods every posto every time, the stated pain may not actually be resolved — worth confirming with the client whether blanket broadcast is sufficient or a targeted/graduated alert is expected.
G0405 | Missing Requirement | The deck states 'postos confirmam a contingência' as a key benefit ('Confirmações em tempo real'), but no UI mechanism is specified (a Slack button, emoji reaction, a form) nor is there any defined escalation or reminder path for a posto that never confirms receipt within a time window. | Without a confirmation mechanic and a non-response escalation path, the claimed 'segundos' reaction-time metric (itself unconfirmed, see G0410) has no operational teeth — a posto could simply never acknowledge and no one would know.
G0406 | Logical Gap | Every source passage describes only the 'system goes down → broadcast alert + contingency plan' half of the flow. No stand-down / resolution step is described — how postos are told the outage is over and to resume normal procedure, and whether that requires the same declaring authority as the original trigger (see G0402). | Without a resolution/stand-down flow, postos have no defined signal to exit contingency mode, risking prolonged unnecessary workaround procedures after the underlying system is actually back up.
G0407 | Source Conflict | Discovery notes explicitly name a sibling initiative, 'Sala de Situação' (Service Cloud, alerting when the citizen-facing channel goes down), as 'outro recorte, outro contrato' — a different scope, different contract from this SOW. Yet both initiatives are fundamentally 'system/channel is down, notify people' mechanics, on different clouds (Slack Workflow Builder here vs. Service Cloud there), for a shared underlying event class (a Prodesp system outage) that could affect both the attendant-facing and citizen-facing sides simultaneously. | Risk of duplicated, uncoordinated, or conflicting outage signals if both initiatives eventually run — worth an explicit boundary statement in the SOW/design (E04 owns attendant-facing broadcast only; Sala de Situação is out of this contract) so the client doesn't expect the two to be integrated with each other.
G0408 | Potential Risk | PRODESP operates 244-246 physical postos; fanning a single outage declaration out to '100% dos postos' via Slack Workflow Builder in 'segundos' has not been validated against Slack Workflow Builder/API throughput or delivery-latency behavior at that fan-out scale. | If the pilot's single-posto proof-of-concept doesn't get load-tested at full-network fan-out before general rollout, the 'segundos' claim (already flagged as a hypothesis, G0410) could fail silently at scale — worth a scale-validation step in the pilot plan.
G0409 | Capability Gap | The deck's benefit panel names 'Monitorar status da contingência...' as an outcome, implying some status view exists — but no source passage describes a backing data object or record (in Slack, Data Cloud, or elsewhere) that would let per-posto confirmation state (per G0405) be queried, aggregated, or reported on. Without one, 'monitorar status' may be nothing more than watching a Slack channel scroll, not an actual status view. | If a real status dashboard is expected (and this ties to E10 Analytics), a data object to persist activation/confirmation events is a build dependency not currently scoped anywhere; if the client is fine with 'watch the Slack channel,' that should be confirmed explicitly rather than assumed.
G0410 | Assumption | The source deck itself states the cited reaction-time and coordination-speed improvements ('segundos', 'tempo de reação... reduzido para segundos') are qualitative hypotheses to be calibrated in the pilot, not confirmed baselines or targets ('Ganhos qualitativos consolidados... os tempos são hipóteses a calibrar no piloto'). | Any acceptance criteria or success metric for E04 must not present these figures as committed SLAs — they are directional claims pending pilot validation, consistent with the project's no-invented-metric discipline.
G0411 | Missing Requirement | [Governance discipline gap] Who, on the PRODESP side, owns and maintains this specific automation once built — authoring and updating the per-system standardized notice and contingency-playbook content the workflow sends, and holding activation/deactivation authority for the workflow itself? E05 (Governança, Adoção e Change Management, Fase 1) covers general Phase 1 governance, but no owner is named specifically for E04's content or operational control. | Signal only, not a mandate — but without a named steward, the contingency playbook text risks going stale (wrong procedure for a system that's since changed) and no one has clear authority to activate or retire the automation. Worth raising as a buyer-facing question, similar in shape to the routing-table ownership gap already logged for E02 (G0211).
G0412 | Missing Requirement | [Experience design discipline gap] No content design or usability validation is described for the standardized outage notice attendants will see and act on mid-transaction, with a citizen still at the counter. Is a plain Slack broadcast message legible and actionable enough in that high-pressure moment, or does the notice need a purpose-built format (a pinned banner, a Canvas state change, a distinct visual treatment) to be noticed and acted on quickly? | Signal only, not a mandate — but the whole value case for E04 rests on attendants noticing and acting on this notice within seconds while serving a citizen; an unvalidated message format is a real risk to the outcome the epic claims. Worth raising as a buyer-facing question before the pilot design is locked.
G0601 | Source Conflict | E06's WhatsApp pre-service triage is not reconciled against the existing 'Poupinha' WhatsApp/Portal channel already doing citizen triage today (~20k conversations/day, 15.1% full self-service completion, NPS 82.24%, per the Discovery Brief's market-context section). It is unclear whether E06 is meant to extend Poupinha, run as a parallel/competing flow, or replace part of it. | Without reconciliation, design risks building a duplicate citizen-facing WhatsApp triage surface instead of extending a channel that already works and is measured. This also affects sizing — extending Poupinha is a materially smaller build than a net-new triage surface.
G0602 | Logical Gap | E06's trigger is 'antes do dia marcado no posto' (before the scheduled day), which presumes an appointment-scheduling system holding the citizen's visit date. No such system is identified anywhere in the discovery sources (Slack-Balcao-BSA, discovery brief, or decisions/0002). | Without identifying the system of record for the appointment date, there is no data source to fire the WhatsApp send at the right lead time — this is a hard technical blocker for design, not just a scheduling nuance.
G0603 | Missing Requirement | Beyond the already-logged 'no pilot/posto/serviço combinado' open item, the specific design inputs needed to move E06 forward are undefined: which service(s) are eligible for pre-service triage, what lead time before the visit the message fires, and what content/questions the triage message actually asks the citizen. | This sharpens the epic-level 'Assumed' confidence into concrete, answerable design questions the client needs to confirm before this capability can be sized or built — currently it is storyboard-level per the epic's own kb_sources.
G0604 | Ambiguity | The epic description says triage 'reduces cases arriving unprepared' but never defines what a completed triage interaction actually produces: does it reschedule/cancel the appointment, flag missing documents to bring, just send a reminder, or something else? | Each outcome implies a very different build (write-back to scheduling vs. a one-way notification) and a different integration surface — this ambiguity has to resolve before T-shirt sizing in `design`.
G0605 | Ambiguity | E06 has no validated success metric. The only wait-time figures in the platform deck (15/16/17 minutes for CNH/CIN/biometria/exame médico) are explicitly flagged in the Discovery Brief as illustrative and not validated by the client — they cannot ground E06's stated outcome ('reducing the volume of unprepared cases at the counter'). | Any capability-intent outcome/metric block authored later for this epic (in `quantum-leap`) would have no real baseline to cite unless the client supplies one; flag now so `design`/`quantum-leap` don't inherit an invented number.
G0606 | Capability Gap | E06 is business-initiated (proactive) outbound WhatsApp contact, not citizen-initiated. Meta's WhatsApp Business Platform requires pre-approved message templates and opt-in for business-initiated conversations — a different technical/compliance path than Poupinha's citizen-initiated reactive flow. No source material addresses this. | If unaddressed, this could block the send mechanism entirely (Meta template rejection) or require a template-approval cycle not currently scoped as design/build effort.
G0607 | Potential Risk | The Discovery Brief's open architecture identities (T7, Sistema Semântico, 'Atendimento,' Biometria) are already logged as unresolved project-wide; for E06 specifically, if the triage flow needs to check appointment or document status against any of these legacy systems, the epic cannot be designed until at least the relevant one is identified. | Escalates a project-wide open question to a direct E06 blocker — design of the triage's data lookups cannot proceed without knowing what legacy system(s) it queries.
G0608 | Logical Gap | E06 (WhatsApp pre-service triage) and E07 (remote document validation by an idle attendant) are described in the epics data as two separate epics, but the deck frames them as sequential journeys (Jornada 02 → Jornada 01/03 extension). No source defines whether a document a citizen submits during E06's triage feeds directly into E07's validation workflow, or whether the two are functionally disconnected. | Risk of either a scope gap (no handoff mechanism ever gets built) or double-counted scope (both epics separately re-solve the same document-intake step) — needs resolution before `design` sizes either epic independently. RESOLVED em grill 2026-09-22 (user-endorsed): tratado como fluxo conectado — o documento triado em E06 alimenta diretamente a validação em E07, não são fluxos independentes. Esta é uma aposta de design a validar com o cliente, não um fato confirmado; ver anotação [assumption:] em `outputs/01-solution.md`.
G0609 | Potential Risk | Business-initiated outbound contact to a citizen before their scheduled visit likely requires a distinct LGPD consent basis from Poupinha's citizen-initiated reactive chats (the citizen didn't start this conversation). No source material addresses how/where this consent is captured or verified. | Given the Discovery Brief already treats LGPD as a first-order design driver (institutional-vs-personal-WhatsApp coordination in Fase 1), the same rigor needs to apply to Fase 2's proactive citizen contact — an unaddressed consent gap here is a compliance risk, not just a UX nicety.
G0610 | Missing Requirement | [Governance discipline gap] Who, on the PRODESP side, will own and maintain the triage script/rules content and the AI-driven outreach decisioning (which citizens get contacted, when, about what) once this capability is live? The project's own Open Questions note no AI-governance owner has been identified yet, and E06 is the first Fase 2 capability that initiates proactive AI-adjacent citizen contact rather than just responding to it. | Signal only, not a mandate — but without a named steward, the triage logic has no maintenance path post-launch and no clear accountable party if the outreach content needs correction or escalation. Worth raising as a buyer-facing question alongside the AI-governance-owner gap already logged in the Discovery Brief.
G0611 | Missing Requirement | [Experience design discipline gap] No user research, service design, or content design work has validated citizen willingness to receive proactive WhatsApp outreach before a scheduled visit, appropriate tone/frequency, accessibility for elderly or low-literacy citizens (a stated population for Poupatempo services), or a defined opt-out flow. | Signal only, not a mandate — but a first-of-kind proactive citizen-contact journey (no LATAM public-sector reference case found per the Discovery Brief's market research) carries real adoption/backlash risk if the outreach feels intrusive or is inaccessible; worth raising as a buyer-facing question before committing to this journey's design.
G0612 | Potential Risk | The citizen may already receive WhatsApp messages from multiple distinct Prodesp/State systems (Poupinha reactive triage, Sala de Situação's Slack-side monitoring, and now this new proactive pre-service outreach). No unified governance for citizen communication frequency/coordination across these channels is named in any source. | Risk of message fatigue, conflicting or duplicate outreach, and citizen confusion about which channel is 'official' — relevant to both adoption (ties to G0611) and to LGPD data-minimization principles if multiple systems independently message the same citizen without coordination.
G0501 | Missing Requirement | No governance owner has been named on the PRODESP side for Agentforce-in-Slack decisions — who is accountable when the agent's suggestion (e.g., biometric-retry guidance in the CIN storyboard) is wrong, and who signs off on the agent's Role/Data/Actions/Channel/Guardrails design before pilot go-live? | Discovery brief explicitly flags this owner as unidentified. The STAAR Agentforce Governance and Guardrails KB frames exactly this as the first design checklist (5 attributes: Role, Data, Actions, Channel, Guardrails) — none of the five has been formally defined for the guichê agent. Without an accountable owner, E05's 'papéis e responsabilidades' deliverable has no counterpart to ratify it on the client side, and go-live risks shipping an agent with no one accountable for its output.
G0502 | Missing Requirement | No executive champion/sponsor has been identified for Balcão V2 (Fase 1 Slack-at-the-counter), distinct from Thiago Waltz, who is the entry point for Frente A (corporate licensing/Approvals) and has no documented involvement in this PS-led design. | Adoption programs for a mandatory new workstation tool (attendants stop calling personal WhatsApp, start using Slack) typically fail without a named executive who can mandate usage across postos. Discovery brief flags this gap explicitly. This is load-bearing for E05's 'critérios de adoção' deliverable — adoption criteria without an enforcement authority behind them are advisory, not operational.
G0503 | Missing Requirement | The training curriculum for attendants has no defined content — does it cover Canvas navigation, huddle-escalation protocol, Agentforce prompt literacy, and LGPD data-handling rules (no raw biometric data in text channels), or only basic Slack onboarding? | The source material's own Nubank/Sammons benchmark cases (cited in the sales deck) emphasize training content as the driver of the '-35% ramp time' and 'produtivo em horas' outcomes — but no analogous curriculum has been drafted for Poupatempo. Without defined content, 'treinamento dos atendentes' in the epic description is a checkbox, not a deliverable that can be estimated or built.
G0504 | Missing Requirement | No channel lifecycle policy exists: who creates/names channels per posto/serviço (e.g. #atendimento-cin), who has channel-admin rights, what the retention/archival period is for LGPD-sensitive channel content, and how case-specific incident channels (e.g. #atendimento-rg-184421 in the storyboard) get closed and audited after resolution. | The 'política de canais' item in the epic description has no operational definition yet. This is a compliance-adjacent gap: the discovery brief treats moving coordination off personal WhatsApp into Slack as the core LGPD win, but that win depends on a real retention/audit policy existing, not just on channels existing.
G0505 | Ambiguity | What quantifies successful adoption of Slack-as-workstation? Candidates in the source material (MTTR, huddle-usage rate, % of cases resolved without the attendant leaving the chair) are all labeled 'hipótese a validar' or storyboard illustration, not committed KPIs. | The epic explicitly names 'critérios de adoção' as a deliverable, but no baseline or target metric has been confirmed by the client — only illustrative numbers (15/16/17-min wait times) that the discovery brief says must not be presented as real baselines. Without a committed metric, adoption criteria will have to be defined during the piloto itself, which should be flagged as a design dependency, not assumed resolved.
G0506 | Potential Risk | Poupatempo attendants are likely to include a high-turnover, terceirizado (outsourced/contracted) workforce — the sales deck's own Sammons Group benchmark ('antídoto ideal para o alto turnover dos terceirizados no Poupatempo') implies this, but the discovery material never confirms actual attendant employment structure or turnover rate for Prodesp/Poupatempo specifically. | If turnover is in fact high, a one-time training rollout decays fast — the role/training program needs to be designed for continuous onboarding (self-service Canvas, repeatable curriculum), not a single launch event. This should be confirmed with the client before E05's training approach is finalized; treating the Sammons analogy as fact for Prodesp would be an unconfirmed assumption.
G0507 | Missing Requirement | No RACI or decision-rights model exists between the Agentforce suggestion, the remote specialist (e.g., Instituto da Identidade, Detran, IIRGD) who joins the huddle, and the attendant who executes the final action on the legacy posto system — who is accountable for the outcome when responsibility crosses these three actors in a single case? | The STAAR Agentforce Governance KB's People/Business/Technology/Data guardrail-crossing method is the applicable structure for this, but it has not been run for the guichê agent's specific human-agent-specialist handoff. This is core to 'papéis e responsabilidades' and currently undefined.
G0508 | Logical Gap | The design intention that 'no raw biometric data should transit Slack text channels' is stated as a LGPD design tese in the discovery brief, but no training content, technical guardrail, or enforcement mechanism has been defined to make attendants actually comply with it in practice. | A stated design principle without an enforcement mechanism (policy vs. a technical control, e.g., Agentforce input filtering or a channel-posting guideline in training) is a gap between intention and operational reality. E05's training and channel-policy deliverables are the natural place to close this, but neither currently addresses it.
G0509 | Missing Requirement | Who authorizes which external specialists (Detran, IIRGD, Instituto da Identidade) to join a huddle, and are those specialists PRODESP employees, third-party agency staff, or another state entity entirely — meaning huddle access/SLA governance may sit outside PRODESP's own Slack org and organizational authority? | If specialists belong to organizations outside PRODESP (e.g., Detran is a separate state entity), E05's 'papéis e responsabilidades' cannot fully resolve this internally — it becomes an inter-agency governance question, which changes who needs to be at the table for this epic's design and could affect timeline/scope if a formal inter-agency agreement is required.
G0510 | Ambiguity | Given decisions/0002 commits both Fase 1 and Fase 2 to the same SOW, should E05's role/governance design get ahead and define the Fase 2 human-in-the-loop supervisor role now (the attendant who validates the 24/7 agentic attendance), or is E05 scoped strictly to Fase 1 attendant/specialist roles with Fase 2 governance deferred to a later iteration? | The epic description as given only names Fase 1 concerns (posto workstation adoption), but the SOW-wide phased-scope decision makes this ambiguous. Left unresolved, either E05 under-scopes (Fase 2 governance surprises later) or the estimate for this epic silently expands to cover work not in its stated description.
G0511 | Potential Risk | Applying the LATAM Agentic Governance Services KB's own discovery questions (Agent Inventory, Data & Compliance, Auditability, Ownership, Cost of Inaction) to PRODESP today returns zero confirmed answers — no governance owner, no confirmed auditability mechanism, no agent inventory beyond this one pilot. | The same KB names '73-74% of enterprises report governance failures in their first year' / 'ungoverned agent deployments fail within 12 months' as the risk this service line exists to prevent. Shipping the Fase 1 pilot without resolving G0501/G0502/G0507 first would put this exact risk pattern into a live government citizen-service deployment — worth surfacing explicitly to the account team, not just folded into training.
G0512 | Missing Requirement | Beyond 'treinamento dos atendentes,' no change-management activity (communication plan to the wider network of 244+ postos, resistance-handling approach, pilot-to-scale rollout sequencing) has been scoped anywhere in the discovery material. | This is exactly the kind of cross-cutting 'how it lands with people' activity that a net-new mandatory workstation change implies — a single-posto pilot succeeding says nothing about whether attendants network-wide will adopt it voluntarily or resist it (the existing WhatsApp-personal-group habit is entrenched). E05's title names 'change management' but the source material gives no communication/rollout plan to build from.
G0513 | Ambiguity | Does the channel policy include an explicit sunset/deprecation mechanism for the existing informal WhatsApp-personal-group coordination, or does official Slack usage simply get added alongside it, leaving both channels live? | The source material itself calls out the confusion of 'two WhatsApps, different rules' (citizen-facing official vs. attendant personal) as the exact problem this project exists to solve. If E05 doesn't define how the old informal channel gets formally retired (not just superseded in theory), adoption could stall at partial usage — attendants keep the old habit as a fallback, undermining both the LGPD win and the adoption metric in G0505.
G0514 | Capability Gap | Does PRODESP have any existing internal audit/compliance capability with experience investigating an AI agent's decision after the fact (e.g., for an LGPD Art. 20-style review, or an internal ombudsman inquiry into a contested attendant/agent interaction), or does that capability not yet exist on the client side at all? | This is a client-side capability gap, not a PS delivery gap — but it directly bounds what E05's 'papéis e responsabilidades' can commit to. If no internal audit capability exists, the epic may need to define a lighter-weight, PS-supported interim auditability process rather than assuming PRODESP already has the muscle to review agent decisions on its own. Relates to the LATAM Agentic Governance KB's 'Continuous Optimization' service line, which exists precisely because most clients lack this capability at launch.
G0515 | Assumption | This gap analysis assumes E05's 'papéis e responsabilidades' scope is limited to human roles directly touching the Fase 1 workflow (attendant, remote specialist, posto coordinator) and does not yet require a formally named 'AI governance owner' role as a deliverable of this epic itself — since the discovery brief treats that owner as an open question to be resolved with the client, not as work E05 is expected to produce unilaterally. | Flagged as an assumption because the epic description doesn't explicitly scope out AI-governance-owner appointment as PS-authored work versus a client-side decision this epic merely surfaces (see G0501/G0511). If the client expects PS to propose and stand up that role as part of E05, the epic's scope is larger than currently described — confirm directly with the client before design/estimate proceeds.
G0701 | Missing Requirement | E07 requires at minimum two postos identified — one with a case in progress and one with an idle attendant — but no pilot posto pair, service, or attendant count has been combined with PRODESP. The only names available (Ana/Anderson/Felipe/Santo Amaro/CIN) are explicitly storyboard, and E07's mechanism (cross-posto idle-capacity pooling) is a superset of E06's already-logged single-posto pilot gap: it needs the whole network's idle-attendant identification method defined, not just one counter. | Without this, E07 cannot be sized or designed — there is no defined 'who is idle, where, and how the system knows it' to build against. Same root cause as E06's pilot gap, but E07 cannot borrow E06's resolution wholesale since it needs a second posto's state, not one.
G0702 | Potential Risk | Per the discovery brief's own architecture walkthrough (IF-08 through IF-10, Felipe/pré-atendimento trilho), remote document validation only becomes real validation — not just conversation — once MuleSoft reaches cadastro, regra, and biometria/gov.br. The brief states plainly: 'Sem MuleSoft até cadastro e regra, Felipe não valida de verdade: ele só conversa.' No APIs are named yet, and which ones enter the piloto is explicitly still open ('Quais APIs nomeadas entram no piloto ainda não foi fechado'). | E07's entire promised outcome (a validated document, not just a reviewed one) is gated on integration scope that doesn't exist yet. This is Fase 2's 'indispensable' MuleSoft dependency landing squarely on this epic — treat as a hard design blocker, not a nice-to-have.
G0703 | Potential Risk | The Discovery Brief's open architecture identities (T7, Sistema Semântico, 'Atendimento,' and the state Biometria system) remain unresolved project-wide. E07's remote attendant needs to check the citizen's document/case status against at least one of these systems to know what to validate — if the lookup target is one of the unnamed systems, E07's design cannot proceed until it's identified. | Escalates the project-wide open item to a direct E07 blocker, same pattern already logged for E06 (G0607) but distinct in that E07's lookup is a validation decision with legal effect, not just a knowledge-base consult.
G0704 | Ambiguity | The brief's LGPD design premise ('sem dado biométrico cru no canal') was stated for E02's text-based huddle escalation (a typed description of a biometric failure). E07's core function is different in kind: an idle attendant visually reviewing a citizen's actual document — a photo ID, a signature, potentially a face photo for matching — from another posto. No source states whether that document image transits Slack directly, a separate secure viewer, or a MuleSoft-mediated preview that never lands in a Slack channel. | This is a first-order compliance question specific to E07, not a restatement of E02's premise — 'no raw biometric text in a channel' does not obviously answer 'is it acceptable to post a document image in a channel.' Needs resolution before design, since the answer changes the build (Slack-native review vs. a bespoke viewing surface).
G0705 | Logical Gap | E06 is framed as Jornada 02 (WhatsApp pre-service triage) and E07 as an 'extensão das Jornadas 01/03.' No source states whether the document E07's idle attendant validates is the same document a citizen submitted during E06's pre-triage (i.e., E07 is the receiving/validation side of E06's intake), or whether E07 operates independently on documents presented in real time at the counter, unconnected to E06 entirely. | Unresolved, this risks either a scope gap (E06 collects a document that nothing downstream ever validates) or duplicated scope (both epics separately build a document-intake/validation step). Related to G0608 already logged under E06, but framed here from E07's validation-side view — resolve once, not twice, in `design`. RESOLVIDO em grill 2026-09-22 (mesma resolução de G0608): fluxo conectado — documento de E06 alimenta E07. Aposta de design, a validar com o cliente.
G0706 | Logical Gap | It is unclear whether E07's remote-validation interaction reuses E02's huddle/ticket escalation UX (specialist joins a huddle on a case) or is a structurally different 'pull a case from a virtual queue' flow — closer to the Jackson deck's move 02 ('Transbordo Inteligente de Demanda Entre Postos') and the Felipe storyboard's 'fila virtual que a rede inteira vê.' If E07 and that cross-posto load-balancing move are the same underlying capability, it is not clear whether that scope lives inside E07, inside E02, or is split/duplicated across both. | Without reconciling this, `design`/`roadmap` risk sizing E02 and E07 as if they were fully independent when they may share (or compete for) the same routing/queue mechanism — a double-count or a silent gap either way. RESOLVIDO em grill 2026-09-22 (user-endorsed): tratado como fluxo conectado — E07 reutiliza/conecta com o padrão de roteamento e escalonamento de huddle de E02, em vez de construir um mecanismo de fila paralelo. Aposta de design a validar com o cliente; ver anotação [assumption:] em `outputs/01-solution.md`.
G0707 | Potential Risk | No source addresses whether a Poupatempo attendant at Posto B is legally authorized to validate/authorize an official document (CIN, CNH, RG) for a citizen physically present at Posto A, nor whether the legado do posto's system of record can record a validation action performed under one attendant's matrícula while the citizen is being served by another. | This is a business-process/legal-authority question, not just a UX question — if cross-posto validation isn't a permitted operating model at PRODESP today, E07 is not buildable as described regardless of technical feasibility. Should be confirmed with PRODESP before design investment.
G0708 | Missing Requirement | [Governance discipline gap] Is governance / CoE / change management in scope for the cross-posto attendant workload and authority questions E07 raises — who decides which idle attendant receives which case, how a wrong remote validation gets escalated or corrected, and how attendant accountability is tracked when the servicing posto and the validating posto differ — or is this assumed handled client-side? | Signal only, not a mandate. No AI-governance owner has been identified on the PRODESP side (per the Discovery Brief's Open Questions), and E07 is the first Fase 2 capability in this SOW where one attendant's remote decision has legal effect on a citizen served by someone else — worth raising alongside the governance-owner gap already logged for E06 (G0610), but sharpened here to the specific cross-posto authority question E07 introduces.
G0709 | Missing Requirement | [Experience design discipline gap] Is UX research / service design in scope for the idle attendant's own remote-validation tooling — how a case appears in the virtual queue, what information the remote attendant needs to make a confident validation decision without the citizen in front of them, and how an incorrect remote call gets surfaced and corrected — or is this assumed to be covered by E01/E02's general attendant-facing design work? | Signal only, not a mandate. E07 is attendant-facing, not citizen-facing, and its interaction pattern (deciding on someone else's case, remotely, from partial information) is materially different from E01/E02's own-counter workflows — it likely needs its own validation, not an assumed extension.
G0710 | Ambiguity | E07 has no validated success metric. The only quantitative wait-time figures in the platform deck (15/16/17 minutes for CNH/CIN/biometria/exame médico) are explicitly flagged in the Discovery Brief as illustrative and not validated by the client, and cannot ground E07's implied outcome (faster resolution of an in-progress presencial case via remote validation). | Same failure mode already logged for E06 (G0605): flag now so a future capability-intent outcome/metric block (in `quantum-leap`) or a story acceptance criterion (in `backlog`) doesn't inherit an invented baseline.
G0711 | Ambiguity | E07's own `kb_sources` are empty/assumption-only ('mesma lacuna de piloto/escopo operacional de E06'). Checking `knowledge/` confirms this is the right call for the specific mechanic: `staar-headless-360-doctrine.md` and `staar-data-360-headless.md` ground the general 'agent operates, human directs, platform governs' pattern and Slack-as-conversational-surface-over-Data-360 pattern, and `staar-agentforce-governance-guardrails.md` grounds the PII/unauthenticated-disclosure guardrail shape — all usable as `[extends: grounded pattern]` context for a future design pass, but none confirms E07's specific remote-document-validation-via-Slack-plus-MuleSoft mechanic as an existing, proven pattern. | No correction needed to the epic's confidence/sourcing — flagging only so downstream work doesn't upgrade E07 from `[assumption:...]` to KB-grounded on the strength of adjacent architecture docs that support the platform doctrine, not this specific workflow.
G0801 | Missing Requirement | The Discovery Brief recommends treating LGPD Art. 20 (right to review of automated decisions) as an explicit architecture principle for E08, not a compliance footnote — since both phases are designed as human-in-the-loop/assistive, the project likely sits outside Art. 20's strict trigger, but this reinforces the need for genuine (not pro forma) human review and explainable routing/triage logic. E08's current description ('supervisão humana, escalando... quando o caso exige') does not yet operationalize what 'genuine review' or 'explainable routing' means as a build requirement. | Without this made explicit, the design risks shipping a human-in-the-loop label with no substantive review step — the exact failure Art. 20 exists to catch, even if the project sits outside its strict legal trigger. This is the single highest-priority open item for E08 per the Discovery Brief.
G0802 | Logical Gap | E08's escalation trigger — 'escalando para um atendente humano quando o caso exige' — is undefined. Neither the epic description nor the Jornada 04 flow (Ana → Agente → Felipe/Anderson) in `.discovery-context.md` specifies what criteria classify a case as requiring escalation (confidence threshold, document mismatch, biometric failure, citizen request, elapsed time, ambiguous intent, etc.). | Without defined escalation criteria, both the guardrail design and the 'genuine human review' principle in G0801 have nothing concrete to implement against — this is a prerequisite for requirements/design work on E08, not a nice-to-have.
G0803 | Ambiguity | The Jornada 04 (Atendimento Agêntico) and Jornada 05 (Gestão Comunicação) diagrams in `.discovery-context.md` show the agent completing citizen requests via backend boxes labeled 'Sistema Semântico,' '"Atendimento",' 'Biometria,' and 'T7' (the last with its own AI agent — 'Utiliza agente do T7 algumas dúvidas') — none of these system identities are resolved. The Discovery Brief's Open Questions already flags this generally; it is now more load-bearing for E08 specifically because this epic is where the agent must actually complete (not just triage) a citizen request end-to-end. | Without resolving these identities, the MuleSoft integration scope behind E08's autonomous request-completion cannot be sized — this blocks `design`/`estimate` for this epic more than for any other Fase 2 epic.
G0804 | Potential Risk | E08 promises 24/7 availability with human-in-the-loop supervision, but no source addresses whether PRODESP staffs human supervisors/specialists around the clock. If escalation only reaches a human during business hours, the '24/7' claim and the 'human-in-the-loop' guardrail may not compose outside those hours — either the agent must act with reduced human backstop overnight, or citizens escalating overnight wait until business hours resume, silently narrowing the 24/7 value proposition. | This is a design decision PRODESP needs to make explicitly (extend supervisor coverage, define an overnight fallback behavior, or scope-limit which case types the agent can conclude unsupervised) — not something the build can resolve on its own.
G0805 | Missing Requirement | No AI-governance owner has been identified on PRODESP's side (confirmed by the user per the Discovery Brief's Open Questions). This is more critical for E08 specifically than for the rest of Fase 2, since E08 is the epic where the agent operates with the least real-time human presence (asynchronous WhatsApp, human review happens after the fact via Slack, per the Jornada 04 diagram's 'Acessa Slack e consulta atendimentos realizados... Valida o atendimento realizado pelo agente' step) — escalation tuning, guardrail maintenance, and audit all need a named accountable party on the client side. | Per `[KB: latam-agentic-governance-services.md]`'s framing, 'ownership' and 'auditability' are two of the top discovery questions for any agentic governance conversation — without a named owner, there is no one to approve guardrail changes or investigate an agent decision after the fact.
G0806 | Potential Risk | No public LATAM reference case exists for public-sector agentic attendance of this kind (confirmed first-of-kind per the Discovery Brief's market research). The closest analogs — Texas DPS ('Agent Sheri') and Thames Valley Police ('Bobbi') — are useful architecture/use-case analogies but not direct proof, and neither is a 24/7 fully agentic completion flow with asynchronous human review; both retain more synchronous human triage than E08's design implies. | Weakens both execution-risk and pricing/timeline anchoring specifically for this capability — position as first-mover/differentiation in any client-facing narrative, never as a proven regional pattern, and treat E08 as the highest-execution-risk epic in Fase 2 for this reason.
G0807 | Missing Requirement | The LGPD/Trust positioning document on Agentforce inference location — confirmed by the user to exist but not yet located or cited — is more load-bearing for E08 than for any other epic in this project, since E08 is the one epic where an AI agent processes citizen PII (identity documents, photos, signatures per the Jornada 04 flow) and makes completion decisions without a human co-present at the moment of interaction. | No deliverable for E08 should assert an LGPD-compliant data-residency/inference-location posture until this document is located and its actual content confirmed — flagging it here ties the existing open item directly to this epic's compliance narrative rather than leaving it as a generic project-level loose end.
G0808 | Potential Risk | Per `[KB: staar-agentforce-governance-guardrails.md]`'s named risk categories, 'Inaccuracy' (hallucination) in a sensitive/public-service context 'could result in denial of services/rights and physical harm' if the agent's output is depended on without a human check. E08's description does not yet specify at what point(s) in the flow a human check occurs when the agent concludes a request autonomously (vs. only when it escalates) — the Jornada 04 diagram shows Slack-side human validation happening after the agent has already 'Finaliza o atendimento,' which may be after-the-fact review rather than a check gating the conclusion itself. | If the human 'validation' step is confirmed to be post-hoc audit rather than a gate on the decision, this reframes E08's human-in-the-loop claim from 'concurrent supervision' to 'sampled audit' — a materially different (and lower) LGPD Art. 20 posture than the epic description implies. This should be confirmed with the client, not assumed either way.
G0809 | Missing Requirement | No guardrail is defined for identity documents/photos/signatures transiting the WhatsApp-to-agent channel in E08 — the Jornada 04 flow explicitly shows the agent requesting 'Foto e assinatura' and validating documentation. This project's Fase 1 design already established a guardrail that no raw biometric data should transit the Slack text channel (IF-01, `.discovery-context.md`), but no equivalent guardrail has been stated for the WhatsApp/agent path in E08, which handles comparable or more sensitive identity artifacts. | Per `[KB: staar-agentforce-governance-guardrails.md]`'s worked example, 'reveal PII... to unauthenticated users' is named as a failure mode to design against explicitly — E08 needs its own version of this guardrail stated, not an inherited assumption from the Fase 1 Slack design.
G0810 | Ambiguity | The relationship between the 'T7' system's own AI agent ('Utiliza agente do T7 algumas dúvidas,' per the Jornada 04/pré-atendimento diagrams) and the Agentforce agent that is the subject of E08 is undefined. It's unclear whether T7's agent is a separate system the citizen or attendant interacts with in parallel, a component E08's agent calls into, or a legacy system E08 is meant to replace. | Left unresolved, this risks either double-building overlapping AI capability or missing a required integration point — the Discovery Brief already flags T7's identity as an open question generally; this entry ties it specifically to E08's scope boundary.
G0811 | Missing Requirement | The E08 epic description names the trigger (inbound WhatsApp) and the escalation behavior (human-in-the-loop) but does not yet define the agent's Role, Data access, Actions, Channel, or Guardrails as a structured set — the 5-attribute checklist `[KB: staar-agentforce-governance-guardrails.md]` prescribes for any Agentforce agent design, nor the 'Agent Monitoring Requirements' the same source calls out as a governance deliverable distinct from a scripted bot's governance. | This is a design-phase deliverable gap, not a scope gap — flagging it now so `design` produces this table explicitly for E08 rather than treating 'human-in-the-loop' as sufficient guardrail language on its own.
G0812 | Missing Requirement | [Governance discipline gap] Is governance / CoE / change management in scope for ongoing AI agent oversight for this specific 24/7 agent — escalation-criteria tuning (see G0802), guardrail maintenance, and audit of agent-concluded cases — or is this assumed to be handled client-side by PRODESP? | Signal only, not a mandate — but E08 is the epic in this project with the least real-time human presence during agent decisioning, so the absence of a named PS-delivered or client-owned governance function is more consequential here than elsewhere in the scope. Ties directly to G0805 (no owner identified) and the LATAM Agentic Governance Services offering `[KB: latam-agentic-governance-services.md]`, which frames exactly this kind of ongoing-oversight gap as a service opportunity, not a given.
G0813 | Missing Requirement | [Experience design discipline gap] Is UX research / service design / conversational design in scope for this AI-driven, 24/7, citizen-facing WhatsApp channel — validating tone, escalation phrasing, accessibility for elderly or low-literacy citizens, and failure/handoff messaging when the agent cannot complete the request — or is this assumed to be handled client-side? | Signal only, not a mandate — but E08 is a first-of-kind (per G0806) autonomous citizen-facing AI interaction with no validated conversational design; unlike E06's pre-service outreach (already flagged as G0611 in `data/gaps.json`), E08's citizen-facing surface is the agent conducting the entire transaction, not just an invitation message, raising the design stakes further.
G0814 | Potential Risk | PL 2338/2023 (Marco Legal da IA) has passed the Senate and is in the Câmara since 17/03/2025 — not yet law as of this discovery (21/09/2026). It is a monitor item, not an active gate, but will bring AI transparency/labeling requirements directly relevant to a 24/7 AI-answering-citizens epic if/when it passes. | E08 should carry this as a tracked risk in any roadmap/contract discussion (e.g. a design principle of building disclosure/labeling capability now rather than retrofitting later) rather than treating the current absence of a passed law as a permanent state.
G0815 | Ambiguity | No ANPD-specific public guidance on biometria or AI governance was found in research conducted for this project (21/09/2026) — this is a research gap, not evidence of absence of applicable guidance. This is most relevant to E08 among all epics, since E08 is the one epic combining AI decisioning with biometric/identity document handling (per G0809) at scale, 24/7. | No deliverable should assert a compliance posture for E08 based on the absence of found guidance — recommend a manual check of the ANPD site and pulling the account team's LGPD/Brazil compliance documentation (ties to G0807) before any client-facing compliance claim about this epic.
G0901 | Ambiguity | T7 is named in the architecture diagram with its own AI agent ("utiliza agente do T7 algumas dúvidas"), and in the diagram's text layout it sits adjacent to the "IA"/"Agentes de IA" cluster rather than the "Atendimento/Biometria/Autenticação/Gov.br" systems cluster. Is T7 (a) a legacy business system that needs a MuleSoft connector like the other four targets, or (b) an AI agent/bot platform that sits at the Agentforce orchestration layer as a peer system, not an integration target MuleSoft calls into? These have completely different implications for E09's connector count and architecture. | User already deprioritized resolving T7 for discovery, but design cannot size E09 without knowing if T7 is inside or outside the MuleSoft integration boundary. If T7 turns out to be agent-to-agent orchestration rather than a system-of-record call, E09's scope shrinks by one integration target but potentially gains an agent-interop requirement instead. RECONFIRMADO em grill 2026-09-22: usuário não tem essa identidade ('eu nao sei a identidade de T7'); permanece gap, a formalizar como pergunta ao cliente no kick-off.
G0902 | Missing Requirement | Biometria estadual has no named vendor/product/API. The Discovery Brief separately notes Prodesp already sells liveness/facial-matching via its own "Portal de APIs." Is that Portal de APIs product the same biometric system referenced in the architecture diagram's "Biometria" box (i.e., the actual MuleSoft integration target), or a different product entirely? Direct client question needed to name the system and confirm whether the existing Portal de APIs is the connector's actual endpoint. | Without this, MuleSoft connector design can't distinguish "call an existing published API" (lower effort) from "integrate with an unpublished internal biometric system requiring discovery of its own" (materially higher effort and risk).
G0903 | Ambiguity | "Sistema Semântico" sits in the architecture diagram's text layout next to "Dados analíticos" and the IA cluster, not clearly grouped with the named legacy/transactional systems (Atendimento, Biometria, Gov.br). Is Sistema Semântico a legacy transactional system MuleSoft must call (a true integration target), or an internal knowledge/semantic-search/NLP capability that would instead feed Agentforce/Data 360 as a grounding source — i.e., not a MuleSoft target at all? | If it's a grounding/knowledge-layer capability rather than a system-of-record, it may belong to a Data 360/Agentforce epic instead of E09, changing E09's true integration count from 5 to 4 named targets.
G0904 | Logical Gap | Is the "Atendimento" box in the architecture diagram the same system as the "sistema do posto"/"legado do guichê" already described in the Fase 1 flow (IF-01, Tela 2 and Tela 5 of the discovery-context use case — where Anderson collects biometrics on "o legado do guichê"), or a distinct fourth legacy system separate from the counter workstation legacy already in scope for Fase 1? | If "Atendimento" and the Fase 1 posto legacy are the same system, E09's distinct-target count drops by one (gov.br, biometria, legado unificado, Sistema Semântico, T7 → 4 distinct systems, not 5) and there may already be a live interface point (IF-01/IF-05) to build from rather than a fresh discovery. This must be resolved before design can count connectors.
G0905 | Missing Requirement | No integration protocol, direction, or volume is specified for any of the five named targets (gov.br, biometria estadual, legado Prodesp, Sistema Semântico, T7). The discovery-context's own interface contract (IF-09/IF-10) explicitly labels this "tese de cano" / "API ainda não nomeada." Per system: is it REST, SOAP, batch file transfer, or real-time synchronous call? What's the expected call volume/frequency (per-transaction, batch nightly, etc.)? | This is the single biggest sizing blocker for E09 — connector pattern (System/Process/Experience API layering), error-handling design, and Mule Credits consumption estimate all depend on protocol and volume per target, none of which exist today for any of the five.
G0906 | Capability Gap | MuleSoft and Data 360 are contracted on the account but "hoje quase não usados por este recorte específico." Is there an existing Anypoint Platform runtime (CloudHub vs. on-premises Mule Runtime/RTF) or any existing API-led layer (System/Process/Experience APIs) built for other Prodesp initiatives that E09 could reuse, or is this greenfield Mule architecture work for all five integration targets? | Reusing an existing System API layer is a materially smaller build than designing System/Process/Experience API tiers from scratch for five new targets — this swings E09's size by more than one T-shirt bracket and needs to be confirmed with Prodesp's integration/platform team, not assumed either way. CONFIRMED em grill 2026-09-22 (basis: conhecimento de conta do usuário — 'o cliente já tem ambiente Mulesoft operando e com alto nível de maturidade'): a Prodesp já roda um ambiente Anypoint maduro. Isto reduz o risco de construir a camada API-led do zero, mas não resolve por si só G0901-G0905 (identidades e protocolos dos 5 sistemas-alvo), que continuam sendo o maior bloqueador de sizing fino de E09.
G0907 | Potential Risk | gov.br and biometria estadual are third-party-owned government APIs outside Prodesp's and Salesforce's operational control. No SLA, rate limit, availability commitment, or error/retry contract has been confirmed for either. What happens to the citizen-facing flow (especially Fase 2's agentic 24/7 attendance) when gov.br or the biometria estadual system is slow, rate-limited, or down? | A citizen-facing agentic flow that silently depends on two external government systems' uptime inherits their outage risk with no fallback/degraded-mode design discussed anywhere in the source material. This is a design-time architecture question (circuit breaker / graceful degradation), not just an SLA negotiation — needs to be raised before Fase 2 technical design, not discovered in production.
G0908 | Missing Requirement | The user confirmed an external Agentforce-inference-location LGPD/Trust positioning document exists, but no document or URL has been located or cited. For E09 specifically: does that document cover where MuleSoft itself runs (Anypoint Cloud region vs. Private Cloud/Runtime Fabric on Prodesp infrastructure), or only where Agentforce inference happens? MuleSoft is the layer literally carrying gov.br and biometria PII across system boundaries — its own residency posture is a distinct question from Agentforce's. | Even once the Agentforce positioning doc is located, it may not answer the MuleSoft-specific residency question this epic needs. Treat as two separate confirmations, not one: (1) locate the Agentforce doc, (2) separately confirm MuleSoft's own deployment/residency model for PII in transit.
G0909 | Missing Requirement | No data steward or decision authority has been identified spanning the (at least) four distinct system owners E09's integration layer crosses: PRODESP legacy/Atendimento, gov.br (federal), biometria estadual, and whoever owns Sistema Semântico/T7. Who approves the field-level data-mapping contract when PII crosses from a state biometric system, through MuleSoft, into Salesforce? Who owns the exception-handling policy when one of these systems is unavailable mid-transaction? | The Discovery Brief's existing open question about an "owner de governança de agentes de IA" is about agent governance broadly; this sharpens it to integration-specific data stewardship. [KB: latam-agentic-governance-services.md] names "Lack of Auditability" and unclear cross-boundary ownership as top-tier enterprise agent-governance risks — this is exactly the governance-assessment conversation that service line is built for, not a detail `design` can quietly assume away. Raise as a discovery question to Prodesp, not an epic to auto-add.
G0910 | Assumption | [extends: staar-headless-360-doctrine.md's framing] The cited KB doctrine describes MuleSoft as part of "shared horizontal agent infrastructure" — a platform-level trust/policy/permissions layer an agent operates across cloud and system boundaries in a single flow of work, not a point-to-point pipe. E09's current description (and the discovery-context's IF-09/IF-10 contract) instead frames MuleSoft narrowly as five separate point-to-point connectors between Salesforce and five named systems. Should E09 be scoped as traditional point-to-point integration, or as the doctrine's broader shared-infrastructure pattern (a MuleSoft-mediated trust/policy layer multiple agents/clouds call into, reusable beyond this one use case)? | The KB doctrine explicitly warns this framing choice "is not just an integration scope question, it is a different commercial conversation" — the two architectures carry materially different cost profiles and reusability. This is currently an unstated assumption (point-to-point) baked into the epic description; flagging it before `design` sizes E09 avoids anchoring on the narrower, possibly wrong, architecture.
G1001 | Missing Requirement | E10's premise is a predictive wait-time algorithm that 'recalcula dinamicamente a estimativa de atendimento' and improves continuously — but the only wait-time figures in any source (15/16/17 min for CNH/CIN/biometria/exame médico) are explicitly confirmed by the client as illustrative, not validated. There is no operational baseline (current average/median wait time per service, per posto, or network-wide) anywhere in discovery. Concrete question for the client: what system today records time-from-check-in-to-called (senha/painel de emissão, legado do posto, or nothing at all)? Without an answer, there is no ground truth to train against, validate against, or claim improvement over — the epic has a build target (an algorithm) but no baseline the algorithm predicts or improves. | This blocks scoping the epic as 'predictive analytics' at all. If no such baseline system exists, the deliverable may need to start with instrumenting/measuring wait time as its own workstream before any predictive model is buildable — a materially different (and likely larger) scope than 'algorithm on top of existing data.' Highest-priority gap on this epic.
G1002 | Potential Risk | The only volumetria this epic could train or size a model against (2024: ~45M presencial/~76M digital, 244-246 units) is flagged in the Discovery Brief as externally unverifiable — 'to verify in Prodesp's internal transparency report,' not citable externally without that caveat. If E10's predictive model design, training-data assumptions, or capacity sizing silently inherit these figures as fact (rather than as a tese to recheck against Prodesp's internal report), the model's calibration inherits an unverified input. | Design/estimate for E10 must explicitly carry the same volumetria caveat the Discovery Brief already applies elsewhere, not treat these numbers as ground truth because they appear in a table. Low effort to fix (a caveat), but easy to lose in translation between discovery and design.
G1003 | Logical Gap | No system of record for real-time per-posto capacity signal has been identified anywhere in discovery. This same absence is flagged as an open assumption on E03 (Roteamento de Capacidade Ociosa Entre Postos: '[assumption: sinal de capacidade em tempo real por posto - sistema/fonte de dados ainda não identificado]'). E10's description claims 'cruzamento de dados em tempo real via Data 360' across 'emissão de senhas, Slack, Sistemas PRODESP' - is E10's analytics layer meant to be the source system that produces the capacity signal E03 consumes, or is E10 a separate downstream consumer of a signal E03 (or some other system) already needs to establish? As scoped, both epics assume the signal exists without either claiming ownership of producing it. | If unresolved, E03 and E10 could each assume the other builds the capacity-signal foundation, and neither does - a real risk of a dropped dependency between two epics that read as independent but aren't. Needs an explicit design-time call on which epic (or a shared foundational piece) owns this.
G1004 | Missing Requirement | The Discovery Brief recommends treating LGPD Art. 20 (right to review of automated decisions) as an explicit architecture principle for E08's agentic/predictive capabilities - human-review/explainability by design, not a compliance footnote. E10 has two components that plausibly need the same treatment and currently have none: (1) the predictive wait-time algorithm surfaced to citizens (an automated estimate presented as fact to a member of the public), and (2) the 'retroalimentação analítica dos agentes de IA' feedback loop (analytics data feeding back into agent behavior - a second-order automated influence on citizen-facing decisions). Should E10 carry the same explainability/human-review-by-design principle documented for E08, and if so, what does 'explainable' mean concretely for a wait-time estimate and for an agent feedback loop (a citable estimate range vs. a point number; a human-reviewed retraining/update step vs. silent continuous adjustment)? | Without this, E10 risks being designed and built as a pure optimization/UX feature while carrying the same automated-decision-adjacent characteristics the brief already flagged as needing architectural treatment elsewhere in the same SOW - an inconsistency across epics in the same contract.
G1005 | Ambiguity | The epic's kb_source cites `staar-data-360-headless.md`'s 'Agent Persona' pattern as sustaining the technical viability of 'retroalimentação analítica.' Read directly, that document grounds the general pattern of agents (in Slack, Claude, etc.) reading Data 360 context headlessly - it does not describe or support a predictive forecasting algorithm, a Calculated-Insights-style model, or an agent-retraining feedback loop. Is the predictive wait-time algorithm meant to be built on a native Data 360/Salesforce forecasting capability (if one exists and applies here), or does it require a custom model/data-science build outside the currently-licensed Agentforce/Data 360 stack? No source in `knowledge/` or discovery answers this. | This directly affects sizing and delivery model: 'native platform configuration' and 'custom ML model build + MLOps' are very different scopes, skill sets, and risk profiles. Left unresolved, the epic could be estimated as a configuration task when it is actually a data-science build, or vice versa.
G1006 | Missing Requirement | E10's 'Cruzamento de Bases em Tempo Real' names three integration sources - 'emissão de senhas' (ticket/queue system), Slack, and 'Sistemas PRODESP' - but only Slack has a known integration path in this project's architecture section (IF-01 through IF-11 in `.discovery-context.md`). The ticket-issuing system's identity and integration path (direct API, via MuleSoft, or via Data 360 ingestion) is not named anywhere, and 'Sistemas PRODESP' is a generic label, not a named system - the same open-identity pattern already flagged for Sistema Semântico, 'Atendimento,' T7, and Biometria (E09, Discovery Brief Open Questions). Which system issues the senha, and how does it reach Data 360 or the analytics layer? | Adds one more unresolved system identity to the list already blocking E09's MuleSoft integration design - worth raising to the client in the same pass as the other open architecture identities rather than as a separate round of questions.
G1007 | Ambiguity | 'Retroalimentação analítica dos agentes de IA para melhoria contínua do atendimento' names an outcome (agents improve continuously from analytics data) without specifying the mechanism. Candidates range widely in cost and risk: a human-reviewed periodic prompt/knowledge-base update informed by a dashboard (low risk, Fase-1-shaped), a scheduled model retraining cycle (higher risk, needs an owner - see G1010), or fully automatic, un-reviewed continuous adjustment (highest risk, directly implicates G1004). Which is intended? | The three candidate mechanisms have materially different build scope, governance need, and LGPD Art. 20 exposure (G1004) - this needs to be pinned down before design, not left as a phrase in the epic description.
G1008 | Ambiguity | Per `decisions/0002`, this SOW commits to both Fase 1 (tactical, Corte 1) and Fase 2 (whole-house, Corte 2) in full, and requirements/design/roadmap must scope epics for both explicitly. E10 is not tagged to either phase (`phase: null` in `data/epics.json`, matching every other epic) and its content straddles both: the internal 'Painel de Indicadores' and Slack/Sistemas-PRODESP data cruzamento reads as Fase-1-adjacent (attendant-facing, no new citizen channel), while 'Transparência para o Cidadão' (informing the citizen of their estimated call time) is a net-new citizen-facing surface that reads as Fase-2-shaped (parallel to the WhatsApp pre-service and agentic-24/7 citizen touchpoints in E06/E08). Should E10 be split into a Fase 1 internal-analytics slice and a Fase 2 citizen-transparency slice, or does the whole epic sit in one phase? | Left as a single unphased epic, roadmap/estimate risk treating a citizen-facing feature with the same phase-1 tactical timeline as the internal indicators panel, understating its scope and risk (new citizen channel, new data exposed externally, LGPD exposure per G1004).
G1009 | Missing Requirement | Is user research / service design / content design in scope for how the predictive wait-time estimate is actually surfaced - to the attendant (as an operational indicator) and, if the 'Transparência para o Cidadão' component proceeds, to the citizen (as a number they'll read literally, e.g. on a totem or WhatsApp message)? No source names an owner for this; it may be assumed to be handled client-side (Prodesp's own UX/communications team), but that assumption is not confirmed anywhere. | A wait-time estimate surfaced without careful design (e.g., a precise-looking '17 min' that's frequently wrong) is a credibility and satisfaction risk for a citizen-facing government service - worth confirming ownership explicitly rather than assuming it's covered.
G1010 | Missing Requirement | Is governance / Center of Excellence / change management in scope for who owns model accuracy monitoring, retraining cadence, and data quality for this predictive/analytics layer on an ongoing basis post-go-live - or is this assumed to be handled client-side? The Discovery Brief already flags 'Owner de governança de agentes de IA do lado Prodesp' as unidentified for the account as a whole, and points to `knowledge/latam-agentic-governance-services.md` for a governance discovery agenda once that owner is found - but E10 specifically needs an owner for model drift/accuracy, not just agent behavior governance generally, and that narrower ownership question is not yet on record anywhere. | A predictive model with no owner for accuracy/retraining degrades silently over time (volumetria changes, service mix changes, new postos open) - without an assigned owner, the 'melhoria contínua' promise in the epic description has no one accountable for keeping it true after go-live.
G1011 | Logical Gap | Existing gap G0409 (on E04, Workflow de Contingência) already notes that 'Monitorar status da contingência' implies a status view with no named backing data object to persist or aggregate cross-posto events. E10's 'Painel de Indicadores' has the identical unresolved dependency at epic level: no source names a data object/store where cross-posto indicators (wait times, contingency status, capacity signals) would be persisted, aggregated, or queried for a panel to render. G0409 and this gap point at the same missing foundational piece from two different epics. | Worth resolving once, as a shared foundational data-model question, rather than twice independently in E04's and E10's design - otherwise there's a real risk of E04 and E10 each building their own ad hoc aggregation store instead of one shared one.
G0116 | Assumption | [assumption: E01] Conteúdo do Canvas fixado no Slack é lastreado em artigos de Salesforce Knowledge (não autoria nativa solta no Canvas), para manter versionamento e auditoria. | Validaria confirmando com a Prodesp o mecanismo exato de sincronização Canvas↔Knowledge desejado (nativo vs. processo manual de cópia). Se a suposição quebrar (cliente quer autoria 100% nativa no Canvas), a arquitetura de governança de conteúdo de E01 muda de 'sincronizado com sistema de registro' para 'processo de revisão manual periódica' — sizing pode subir de M para L pela necessidade de um processo de governança de conteúdo adicional.
G0214 | Assumption | [assumption: E02] Roteamento de escalonamento via Slack User Group estático por especialidade é suficiente para a escala do piloto da Fase 1 (em vez de roteamento decidido por Agentforce). | Validar cobertura real de especialistas por tema/turno com a Prodesp. Se a suposição quebrar (cobertura de especialista insuficiente para roteamento estático), E02 precisa de lógica de roteamento dinâmico já na Fase 1 — sizing sobe de S para M.
G0315 | Assumption | [assumption: E03/E10 — fundação de dados compartilhada] Um sinal de ocupação/fila em tempo real por posto precisa ser construído do zero (provável objeto Data 360 alimentado por check-in/check-out do atendente ou estado de sessão dos totens) — nenhum sistema de registro existente foi identificado no discovery. | Este é o gap de fundação de dados mais carregado do programa: tanto E03 (roteamento de capacidade ociosa) quanto E10 (previsibilidade de atendimento, Fase 2) dependem do mesmo sinal. Validar com a Prodesp se já existe qualquer sistema de fila/ocupação hoje (mesmo que não-Salesforce) antes de desenhar do zero. Se não existir nada, E03 sobe de S para M (precisa instrumentar check-in/check-out) e E10 sobe de M para L (modelo preditivo sem dado de entrada confiável é maior risco/esforço). RESOLVIDO PARCIALMENTE em grill 2026-09-22 (user-endorsed): E03 assume a propriedade de construir essa fundação; E10 passa a ser puro consumidor, não dono. A questão técnica de fundo — se algum sistema de fila/ocupação já existe (mesmo fora do Salesforce) — permanece Unknown, pendente de confirmação com a Prodesp.
G0413 | Assumption | [assumption: E04] Gatilho do workflow de contingência é manual (atendente/operação aciona o Flow) na Fase 1; gatilho automático via integração com o stack de monitoramento da Prodesp é evolução Fase 2+. | Carrega a ambiguidade já registrada em G0401 (automático vs. manual). Se o cliente exigir gatilho automático já na Fase 1, E04 sobe de XS/S para M pela necessidade de integração com monitoramento externo via API/webhook.
G0613 | Assumption | [assumption: E06] Existe um sistema de agendamento de visitas ao Poupatempo capaz de emitir um evento de 'cidadã tem visita agendada' para disparar o pré-atendimento via WhatsApp. | Identificar com a Prodesp qual sistema agenda as visitas hoje e se ele pode emitir esse evento (webhook, polling, arquivo). Se não houver esse gatilho disponível, E06 precisa de uma integração adicional só para obter o sinal de agendamento — sizing sobe de M para L.
G0712 | Assumption | [assumption: E07] Captura e transporte de imagem de documento até a sessão Slack do atendente remoto seguem tratamento de residência/retenção de dados específico para imagens — distinto do caso já resolvido de 'sem biometria bruta em texto' nos canais de coordenação. | Validar com o time de LGPD/Trust da conta se compartilhar imagem de documento (não biometria bruta, mas ainda dado sensível) em thread do Slack é aceitável ou exige um cofre/visualizador dedicado. Se exigir um visualizador dedicado (documento nunca baixado, só visualizado em viewer controlado), E07 sobe de M para L.
G0911 | Assumption | [assumption: E09] A camada de integração MuleSoft segue o padrão API-led connectivity padrão (System/Process/Experience API) independentemente das identidades ainda abertas de Sistema Semântico/"Atendimento"/T7/Biometria — o formato da camada pode ser desenhado antes das identidades serem confirmadas. | Protocolos e mecanismos de autenticação por sistema específico ficam pendentes até as identidades serem confirmadas (G0901-G0910, não resolvidos aqui). E09 já carrega confidence 'Unknown' — é o épico de maior risco do programa; qualquer identidade que exija um protocolo não-REST/não-padrão (ex.: legado com SOAP/arquivo batch, biometria com SDK proprietário) sobe o sizing de L para XL.
G1012 | Assumption | [assumption: E10] Direção de integração do modelo preditivo de espera ainda não confirmada: nativo Salesforce/Data Cloud (Einstein) vs. alimentar uma ferramenta de BI já existente da Prodesp. | Validar com a Prodesp se eles têm uma ferramenta de BI/analytics institucional que espera receber esse dado, ou se aceitam um modelo nativo Salesforce. Depende também da resolução de G0315 (sinal de capacidade compartilhado com E03) — sem esse sinal de entrada, o modelo preditivo não tem dado confiável para treinar. Se a integração precisar exportar para BI externo, E10 sobe de M para L pela integração de saída adicional.

## Estimates
Item ID | Item Type | T-Shirt Size | Size Rationale | Size If Assumption Breaks | Complexity Drivers | Skills Needed | Risks | Solution Approach | Confidence
E01 | epic | M | M — impulsionado pelo agente Agentforce em canal (grounding em Data 360/Knowledge, desenho de tópico/ação); configuração de canais e Canvas é baixa complexidade. |  | Desenho do agente Agentforce (tópico, dados, guardrails); mecanismo de sincronização Canvas↔Knowledge para manter conteúdo auditável. | Agentforce Consultant, Slack Admin, Solution Architect | As 1.800 licenças Slack já validadas cobrem a Sala de Situação, não o headcount real de atendentes nos 244 postos + 900 totens — dimensionamento de licenças pendente com o cliente (não é um driver de tamanho técnico, mas afeta o custo de licenciamento). | Canais Slack por serviço + Canvas lastreado em Salesforce Knowledge + agente Agentforce de tópico único grounded em Data 360/Knowledge, embutido no canal. | Assumed
E02 | epic | S | S — roteamento estático via Slack User Group, sem lógica de decisão automatizada na Fase 1. |  | Nenhum driver de complexidade técnica alto; a incerteza está na cobertura real de especialistas por tema/turno (organizacional, não técnica). | Slack Admin | G0214 — se a cobertura de especialista for insuficiente para roteamento estático por User Group, a Fase 1 precisará de lógica de roteamento dinâmico antes do previsto. | Slack User Groups estáticos por especialidade; atendente aciona huddle diretamente do canal de serviço. | Assumed
E03 | epic | M | M — dimensionado conservadoramente para cima por causa da dimensão Integration ser Unknown (nenhuma fonte de sinal de ocupação identificada); pode subir para L se instrumentação nova (check-in/totem) for necessária. | M; L se exigir instrumentação nova (integração com totens/check-in) para gerar o sinal de ocupação do zero. | G0315 — fundação de dados compartilhada com E10: nenhum sistema de registro de ocupação em tempo real por posto foi identificado; resolver esse sinal uma única vez serve os dois épicos. PROPRIEDADE RESOLVIDA em grill 2026-09-22 (user-endorsed): E03 assume a propriedade de construir esse sinal — E10 é puro consumidor, não constrói nem compartilha o custo de build. | Solution Architect, Integration Developer (contingente à fonte do sinal) | Dimensão de maior incerteza do programa junto com E09 — sem confirmação do que já existe (mesmo fora do Salesforce) para ocupação/fila por posto, o esforço real só se conhece após a validação com a Prodesp. E03 é o dono designado dessa fundação (grill 2026-09-22); E10 depende dela mas não a constrói. | Objeto de sinal de ocupação por posto (fonte a confirmar) alimentando lógica de roteamento entre os 244 postos + 900 totens. | Unknown
E04 | epic | S | S — Flow declarativo de broadcast com gatilho manual; sobe se gatilho automático via integração de monitoramento for exigido. | S; M se gatilho automático via webhook/API do stack de monitoramento da Prodesp for exigido. | G0401/G0413 — ambiguidade sobre gatilho automático vs. manual ainda não resolvida com o cliente. | Salesforce Admin/Flow Developer | Se a Prodesp exigir gatilho automático já na Fase 1, o épico sobe de tamanho pela necessidade de integração com o stack de monitoramento via webhook/API. | Flow de broadcast disparado manualmente por atendente/operação quando um sistema crítico cai. | Assumed
E05 | epic | M | M — tamanho derivado por julgamento de entrega (papéis, treinamento, política de canais, change management), não pelas oito dimensões técnicas, que não se aplicam a este épico não-técnico. O driver é a amplitude do rollout (244 postos + 900 totens), não a complexidade de build. |  | Amplitude organizacional do rollout; múltiplos papéis e políticas a definir e comunicar através de uma rede de atendimento de grande escala. | Change & Adoption Lead, Program Manager | Owner de governança de agentes de IA do lado Prodesp ainda não identificado — mais crítico agora que a Fase 2 (atendimento agêntico 24/7) é escopo confirmado, não visão. | Definição de papéis/responsabilidades, currículo de treinamento de atendentes, política de canais e critérios de adoção do Slack como posto de trabalho, aplicando o checklist de 5 atributos e o framework LATAM de governança agêntica. | Confirmed
E06 | epic | M | M — dois drivers concorrentes no mesmo tier (agente de triagem + integração de gatilho de agendamento); nenhum ainda XL, mas ambos carregam incerteza. | M; L se for necessário construir uma integração dedicada para emitir o evento de gatilho de agendamento. | G0613 — dependência real não é o canal WhatsApp (já disponível), é o evento de gatilho do sistema de agendamento. | Agentforce Consultant, Integration Developer | Se nenhum sistema de agendamento existente puder emitir o evento de gatilho, será necessária uma integração dedicada só para obter esse sinal. | Agente Agentforce de triagem/pré-atendimento pelo WhatsApp, disparado por evento de agendamento, grounded em Data 360 (cadastro/histórico da cidadã). | Unknown
E07 | epic | M | M — driver principal é a dimensão de segurança/compartilhamento pela sensibilidade da imagem de documento; reutiliza a fundação de capacidade de E03 sem custo de integração adicional. | M; L se um visualizador seguro dedicado (sem download nativo do Slack) for exigido para conformidade LGPD. | G0712 — se a LGPD exigir um visualizador seguro dedicado (documento nunca baixado, só visualizado), a complexidade de segurança sobe significativamente. | Solution Architect, Security/Compliance-aware Architect | Terceiro consumidor da mesma fundação de dados de capacidade ociosa (junto com E03 e E10) — depende da resolução de G0315. | Atendente ocioso em outro posto valida documento à distância via Slack, usando o mesmo posto de trabalho de E01, reutilizando o sinal de capacidade ociosa de E03. | Assumed
E08 | epic | L | L — impulsionado pelo agente multi-tópico com escalonamento human-in-the-loop e guardrails de confiança; modelo de dados e volume permanecem baixos. |  | Desenho de tópicos/ações do agente, estratégia de grounding, guardrails (nunca afirmar status de emissão sem confirmação humana; nunca revelar PII), e o mecanismo de handoff para humano. | Agentforce Consultant (sênior), Conversational Designer, Integration Developer | Revisão humana no ponto de escalonamento precisa ser genuína, não pro forma — consistente com a análise de LGPD Art. 20 do Discovery Brief; owner de governança de agentes ainda não identificado (ver E05). | Agente Agentforce multi-tópico atendendo pelo WhatsApp 24/7, com escalonamento human-in-the-loop, seguindo a doutrina 'humanos direcionam, agentes executam, a plataforma governa'. | Assumed
E09 | epic | XL | XL — dimensão de integração é o driver dominante (hub de orquestração multi-sistema); segurança/compliance amplifica ainda mais pela natureza regulada (gov.br, biometria). |  | Identidades de Sistema Semântico, 'Atendimento', T7 e Biometria ainda não confirmadas (G0901-G0910) — o formato da camada (API-led connectivity) pode ser desenhado, mas protocolos/autenticação específicos ficam pendentes. | Integration Architect (MuleSoft), Technical Architect, Security/Compliance-aware Architect | Confiança Unknown herdada de epics.json — o épico de maior risco técnico do programa. Qualquer identidade que exija protocolo não padronizado (SOAP, arquivo batch, SDK proprietário de biometria) eleva ainda mais o esforço além do já dimensionado como XL. Ambiente MuleSoft/Anypoint maduro já confirmado na conta (grill 2026-09-22) reduz o risco de construção da camada do zero, mas não muda o XL enquanto T7/Sistema Semântico/Atendimento/Biometria (G0901-G0904) e protocolo/volume (G0905) permanecerem não confirmados — mantém-se XL até essas identidades serem formalizadas com o cliente no kick-off. | Camada de integração MuleSoft API-led (System/Process/Experience API) ligando a plataforma Salesforce Headless a gov.br, biometria estadual, legado Prodesp, Sistema Semântico e T7. Ambiente Anypoint já maduro na conta (confirmado em grill 2026-09-22) é o ponto de partida — não greenfield. | Unknown
E10 | epic | L | L — impulsionado pela dimensão de Analytics & Insights (modelo preditivo + retroalimentação); dependente da resolução da fundação de dados compartilhada com E03. | L; XL se exigir integração de saída para BI externo da Prodesp além do modelo nativo Salesforce, ou se o sinal de capacidade de E03 não for resolvido a tempo de alimentar o treinamento. | Os KPIs de exemplo (15/16/17 min) são ilustrativos, não uma métrica existente — isto é build novo, não exposição de dado já validado. G1012 — direção de integração (nativo Salesforce vs. BI externo) ainda não confirmada. PROPRIEDADE RESOLVIDA em grill 2026-09-22 (user-endorsed): E03 é dono da construção do sinal de capacidade (ver G0315/estimate E03); E10 permanece puro consumidor — confirmado, sem mudança no tier desta dimensão. | Data Cloud/Data 360 Architect, Einstein/AI Consultant | Sem o sinal de capacidade de E03 resolvido, o modelo preditivo não tem dado de entrada confiável para treinar — dependência direta entre os dois épicos. E10 não constrói essa fundação; a dependência é de dado, não de esforço de build compartilhado. | Data 360 como camada de dados cruzados em tempo real, alimentando um modelo preditivo de tempo de espera com retroalimentação dos agentes de IA. | Assumed

## Roadmap Phases
Phase Number | Phase Name | Duration (Weeks) | Duration Source | Parallel Track | Objectives | Epics Included | Success Criteria | Dependencies | Risks
0 | Resolução de Discovery e Pré-Kickoff |  |  |  | Fechar as lacunas que travam o kick-off técnico antes de qualquer build começar: identidades e protocolos dos 5 sistemas-alvo de E09 (G0901-G0905), fonte do sinal de ocupação/fila por posto que E03/E07/E10 consomem (G0315), sistema de agendamento que dispara E06 (G0613), nomeação do owner de governança de agentes do lado Prodesp (lacuna consolidada em 9 gaps espalhados por 7 épicos), e dimensionamento real de licenças Slack para 244 postos + 900 totens (hoje só as 1.800 licenças da Sala de Situação estão validadas). |  | As 4 lacunas de sistema (T7, Sistema Semântico, Atendimento, Biometria) têm identidade e protocolo confirmados; fonte do sinal de capacidade por posto identificada (existente ou a construir); owner de governança nomeado; licenciamento Slack dimensionado para o headcount real de atendentes. | Nenhuma — é o pré-requisito das demais fases. | Gatilho: 136 gaps / 4 conflitos de fonte no gap analysis — acima do limiar de >15 gaps que recomenda uma fase de resolução dedicada em vez de herdar a incerteza para o build.
1 | Fundação do Posto de Trabalho e Governança |  |  |  | Colocar o atendente para trabalhar dentro do Slack (canais por serviço, Canvas fixado, Agentforce em contexto) com papéis, treinamento e política de canal definidos desde o primeiro dia de rollout — não retrofitados depois. | E01,E05 | Atendente resolve dúvidas de fluxo sem saltar para conhecimento disperso; Canvas lastreado em Salesforce Knowledge; papéis/responsabilidades e critérios de adoção publicados antes do go-live. | Depende da Fase 0 (owner de governança nomeado, licenciamento dimensionado). | Risco carregado do design: as 1.800 licenças já validadas cobrem a Sala de Situação, não o headcount real dos 244 postos + 900 totens.
2 | Operação Tática do Balcão |  |  |  | Escalonamento em tempo real por huddle a partir do posto de trabalho de E01; sinal de ocupação/fila por posto entre 244 postos + 900 totens (a maior incerteza técnica da Fase 1, endereçada com antecedência porque E07 e E10 dependem dela); workflow de contingência para sistema fora do ar. | E02,E03,E04 | Atendente aciona huddle sem sair da cadeira; sinal de capacidade por posto disponível e confiável (fonte confirmada na Fase 0); aviso automático de sistema fora do ar chega antes do boca a boca informal. | depends on: E01 (posto de trabalho onde o huddle é acionado). | E03 é dimensionado com confiança Unknown — pode subir de M para L se exigir instrumentação nova (integração com totens/check-in) para gerar o sinal de ocupação do zero; resolver isso aqui evita que o risco se propague para E07/E10 na Fase 4/5.
3 | Plataforma de Integração MuleSoft |  |  | Yes | Construir a camada de integração API-led ligando a Plataforma Salesforce Headless a gov.br, biometria estadual, legado Prodesp, Sistema Semântico e T7 — o épico de maior risco técnico do programa (XL, confiança Unknown). | E09 | Camadas de API de Sistema/Processo/Experiência entregues para os 5 sistemas-alvo, com protocolos e mecanismos de autenticação confirmados por sistema (não apenas o formato API-led). | Nenhuma dependência de outro épico — corre em paralelo às Fases 2–4 por ter o maior lead time do programa; não bloqueia os épicos baseados em Slack. | Ambiente MuleSoft/Anypoint já maduro na conta (confirmado em grill 2026-09-22) reduz o risco de construção da camada do zero, mas as identidades de T7/Sistema Semântico/Atendimento/Biometria e o protocolo/volume por sistema continuam sendo o bloqueador dominante enquanto não formalizados no kick-off (Fase 0).
4 | Experiência Agêntica Cidadã |  |  |  | Pré-atendimento digital por WhatsApp antes da visita (E06); validação remota de documentos por atendente ocioso, reutilizando o posto de trabalho de E01, o padrão de huddle de E02, o sinal de capacidade de E03 e o intake de documento de E06 como um fluxo conectado (E07); atendimento agêntico 24/7 com escalonamento human-in-the-loop (E08). | E06,E07,E08 | Cidadã recebe triagem antes do dia marcado; atendente ocioso valida documento à distância sem duplicar intake; agente de WhatsApp atende fora do horário e escala genuinamente quando o caso exige. | depends on: E01, E02, E03, E06 (E07 converge as quatro dependências — atraso em qualquer uma atrasa E07). | E06 depende de um evento de gatilho de agendamento ainda não confirmado (G0613, a resolver na Fase 0); E07 carrega risco de LGPD mais alto que o huddle em texto por transportar imagem de documento; E08 é o primeiro fluxo agêntico 24/7 do setor público sem case de referência LATAM — mantido em L sem sensibilidade formal de sizing, por decisão explícita do usuário no grill 2026-09-22.
5 | Analítica e Fechamento |  |  |  | Cruzamento de dados em tempo real via Data 360, modelo preditivo de tempo de espera e retroalimentação analítica dos agentes de IA para melhoria contínua. | E10 | Modelo preditivo de espera treinado com dado real do sinal de capacidade da Fase 2; retroalimentação dos agentes de IA operando. | depends on: E03 (sinal de capacidade por posto — dependência de dado, não de esforço de build compartilhado). | Sem o sinal de capacidade de E03 resolvido a tempo, o modelo preditivo não tem dado de entrada confiável para treinar — por isso sequenciado por último, não em paralelo com E03.

## Roles & Skills
Role ID | Role | Seniority | Location | Count | Side | Phases Active | Allocation | Allocation by Phase | Justification | Rationale | Comments | Suggested Count (opt-in) | Count Source | Multi-disciplinary Note
PS-01 | Program Manager | senior | onshore | 1 | ps | 0-5 | full |  | PM dedicado exigido por decisao de resourcing padrao do projeto (memory.json, 2026-09-21/22) — nao e gap, nem absorvido pelo time existente. Governanca do programa inteiro (6 fases) e coordenacao com stakeholders de setor publico.
PS-02 | Solution Architect | senior | onshore | 1 | ps | 0-5 | full |  | Arquitetura de solucao atravessando Slack + Agentforce + MuleSoft + Data 360 — 4 produtos em escopo exigem um dono unico de coerencia arquitetural do inicio ao fim.
PS-03 | Technical Architect | senior | onshore | 1 | ps | 1-5 | full |  | E09 (MuleSoft, XL/Unknown) e o epico de maior risco tecnico do programa — camada de integracao com 5 sistemas-alvo (T7, Sistema Semantico, Atendimento, Biometria, gov.br) exige supervisao tecnica senior onshore continua.
PS-04 | Functional Consultant | senior | onshore | 1 | ps | 1-3 | full |  | Configuracao de posto de trabalho Slack + huddle/escalonamento (E01, E02, E04) — trabalho tatico do balcao que se beneficia de proximidade onshore com o atendente.
PS-05 | Functional Consultant | regular | offshore | 1 | ps | 2-5 | full |  | Configuracao Data 360/analitica (E03 sinal de capacidade, E10 modelo preditivo) — trabalho de config escalavel offshore, mesmo padrao do roster do DER.
PS-06 | Developer | senior | onshore | 1 | ps | 1-4 | full |  | Build de caminho critico com dado sensivel: E07 (validacao remota de documento, risco de LGPD mais alto que o huddle em texto) e E08 (primeiro fluxo agentico 24/7 do setor publico sem case LATAM) exigem um senior onshore no critical path.
PS-07 | Developer | regular | offshore | 3 | ps | 1-5 | full |  | Pod de build offshore escalado ao volume do programa — configuracao/build de topicos e acoes do Agentforce (E01, E06, E08) e suporte de build da camada MuleSoft (E09). Mesmo dimensionamento do pod offshore validado no DER para escopo Multi-Cloud/Medio comparavel.
PS-08 | QA | senior | onshore | 1 | ps | 1-5 | full |  | QA dedicado exigido por decisao de resourcing padrao do projeto (memory.json, 2026-09-21/22). Risco de LGPD/imagem de documento (E07) e guardrails de escalonamento humano genuino (E08) exigem lideranca de QA senior onshore, nao apenas execucao offshore.
PS-09 | QA | regular | offshore | 2 | ps | 2-5 | full |  | Pod de execucao de teste offshore escalado ao volume do programa (244 postos + 900 totens, rollout por onda) — mesmo padrao de dimensionamento do DER.
PS-10 | Change & Adoption | regular | onshore | 1 | ps | 1-5 | full |  | Curriculo de treinamento (E05), politica de canal e adocao incremental por atendente conforme novos canais entram (E06/E07/E08) — cobertura de adocao continua ate o go-live final.
CL-01 | Product Owner / Decision-maker | regular | onshore | 1 | client | 0-5 | quarter |  | GAP — owner de governanca de agentes de IA do lado Prodesp ainda nao nomeado (risco consolidado da Fase 0/1, ver 02-delivery-plan.md). Linha registrada para tornar o gap visivel no roster, nao para assumir que ja esta staffada.
CL-02 | Functional SME | regular | onshore | 2 | client | 1-4 | half |  | SMEs de processo de atendimento/balcao para validar huddle, contingencia e pre-atendimento digital (E02, E04, E06).
CL-03 | Functional SME | regular | onshore | 1 | client | 3-4 | quarter |  | SME de biometria estadual/identidade federada gov.br — compliance LGPD sobre dado sensivel de cidadao cruzando E07/E08/E09.
CL-04 | Change & Adoption | regular | onshore | 1 | client | 1-5 | half |  | Data steward/coordenador de treinamento do lado Prodesp para os 244 postos + 900 totens — dimensionamento real de licenciamento e rollout por onda dependem de um contraparte nomeado.
CL-05 | Technical Architect | regular | onshore | 1 | client | 0,3 | quarter |  | Coordenacao tecnica com os 5 sistemas-alvo do MuleSoft (T7, Sistema Semantico, Atendimento, Biometria, Legado) — formalizar identidades/protocolos (G0901-G0905) e o bloqueador dominante da Fase 0/3.
CL-06 | QA | regular | onshore | 1 | client | 2-5 | quarter |  | Amostra de UAT do lado Prodesp por posto/totem antes de cada onda de rollout.

## Efficiency
Section | Name | Task-Level Band | Realized Band | Driving / Amplified | Human-Only / Evidence | Sources | Narrative
Headline | Blended project-level | ~30-45% | ~10-18% |  | Assumed | [1]; [2]; [3]; [4]; [5]; [8] | task-level ~30-45% × fator de realização 0.30-0.40, antes da modulação por readiness.
Realization Factor | 0.30-0.40 |  |  | Overlay regulatório LGPD/setor público (biometria estadual, identidade federada gov.br, PII de cidadã); Integração com sistemas legados de confiança Unknown (E09 XL, E03 M, E06 M); Conteúdo real de config/Agentforce (E01, E06, E08) puxando para o meio da faixa |  |  | Puxado para a linha de indústria regulada em vez do mixed-enterprise puro: overlay LGPD/setor público explícito + risco de integração XL/Unknown em E09, parcialmente compensado por conteúdo real de config/Agentforce.
Readiness Signal | AI tooling posture |  |  | score 0/2 | Nenhuma evidência de discovery sobre postura de ferramentas de IA aprovadas para uso interno da Prodesp; owner de governança de agentes de IA do lado Prodesp ainda não identificado (gap consolidado em 9 gaps espalhados por 7 épicos, ver 01-solution.md).
Readiness Signal | Delivery velocity / speed bias |  |  | score 0/2 | Agência de setor público, coordenação entre 5 sistemas-alvo (T7, Sistema Semântico, Atendimento, Biometria, Legado) e overlay regulatório que já adiciona +15% ao teto do benchmark — sinal de ritmo empresarial padrão a lento, não fast-moving.
Readiness Signal | Data & environment hygiene |  |  | score 1/2 | Fundação Salesforce bem especificada em E01 (Slack + Canvas + Knowledge), mas identidades/protocolos dos 5 sistemas-alvo do MuleSoft (G0901-G0905) e a fonte do sinal de capacidade por posto (G0315) permanecem não confirmados — mistura de higiene alta no core e baixa nas integrações.
Readiness Signal | Legal / security / compliance posture |  |  | score 0/2 | Overlay regulatório LGPD/setor público explícito (biometria estadual, identidade federada gov.br, PII de cidadã cruzando E07/E08/E09); nenhuma política de tratamento de dados por IA registrada nas fontes de discovery.
Readiness Scenario | (current) Low readiness |  | ~8-12% | score range 0-2 | Nomear o owner de governança de agentes de IA do lado Prodesp; Confirmar identidades/protocolos dos 5 sistemas-alvo do MuleSoft (G0901-G0905); Publicar postura/política de uso de ferramentas de IA |  | Estado atual do programa — piso da faixa reduzido em ~20%: governança de IA não nomeada, ritmo de decisão de setor público e integrações ainda não confirmadas mantêm o ganho modesto.
Readiness Scenario | Mid readiness |  | ~12-16% | score range 3-5 | Formalizar política de tratamento de dados por IA cobrindo LGPD/biometria; Confirmar fonte do sinal de capacidade por posto (G0315) |  | Com a governança nomeada e as integrações formalizadas na Fase 0, o programa capta o meio da faixa de forma defensável.
Readiness Scenario | High readiness |  | ~20-24% | score range 6-8 |  |  | Condições favorecem o topo da faixa apenas se o setor público remover as travas regulatórias e de governança de IA — cenário não observado hoje neste programa.
Category | Technical Engineering & QA | ~20-35% | ~7-13% | Create Code (realistic enterprise/legacy); Analyze Code & Fix Defects ¦ epics: E09, E03, E06, E08 |  | [1]; [4]; [5]; [8] | A integração MuleSoft de E09 (XL, 5 sistemas-alvo) e os workflows de E03/E06 domin am o esforço técnico; ganho tratado pela linha enterprise/legacy porque os sistemas de destino são legados, não greenfield.
Category | Analysis & Design | ~30-50% | ~10-18% | Discovery Preparation; Agent Topic & Action Design ¦ epics: E01, E06, E08 |  | [2]; [11] | O desenho de tópicos/ações do Agentforce em E01/E06/E08 é o trabalho de design mais repetido do programa, puxando esta categoria para o meio-alto da faixa.
Category | Documentation & Knowledge Management | ~35-55% | ~12-20% | Generate/Update Documentation; Training Curriculum Drafting ¦ epics: E05 |  | [7]; [11] | E05 concentra currículo de treinamento e política de canal — trabalho de documentação denso que historicamente captura o ganho mais alto de qualquer categoria, mesmo sob o overlay regulatório.
Category | Project Management & Operations | ~20-35% | ~7-13% | Status Reporting & Coordination ¦ epics: E09, E05 |  | [7]; [11] | Coordenação entre Prodesp/Slack/MuleSoft/Data 360 e potenciais donos externos dos 5 sistemas-alvo mantém esta categoria no meio da faixa — trabalho de alinhamento multi-organização resiste mais à automação.
Human Barrier | Project Pulse Reports |  | ~0% |  | Trabalho de construção de confiança que a IA pode resumir, mas não facilitar.
Human Barrier | Stakeholder Alignment |  | ~0% |  | Negociação humano-a-humano; a IA rascunha posições, pessoas decidem.
Human Barrier | Conflict Resolution |  | ~0% |  | Julgamento humano.
Human Barrier | Coordenação com os 5 donos de sistema externos de E09 (T7, Sistema Semântico, Atendimento, Biometria, Legado) |  | ~0% |  | Negociação de identidade/protocolo entre organizações — depende de relacionamento e autoridade, não de ferramenta.
Human Barrier | Revisão jurídica/compliance LGPD sobre biometria e identidade federada gov.br |  | ~0% |  | Sign-off regulatório em dado sensível de cidadã permanece humano por desenho.

## Estimate Comparison
Lane | Anchor | Basis | Duration Weeks Range | Indicative Price Low | Indicative Price High | Currency | Roster | Capacity Summary | Delta vs Other Lane | Validated By | Disclaimer Class
traditional |  | derived | {'low': 15, 'high': 30} | [6 empty] | user | input-derived
augmented | yes | derived | {'low': 14, 'high': 25} | [6 empty] | user | input-derived
quantum-leap |  | derived | {'low': 10, 'high': 18} |  |  |  | 1x Program Lead (senior onshore); 1x Intent Architect (senior onshore); 1x Agent Orchestrator (senior onshore); 1x Adoption Architect (regular onshore); 1x Developer (senior onshore); 1x QA (senior onshore); 1x QA (regular offshore) |  |  | user | input-derived