## Epics
Epic ID | Epic Name | Description | Confidence
E01 | Consultas Financeiras Self-Service | Habilitar clientes B2B (ministérios, entes públicos) a consultar valores em aberto, contratos e pagamentos no Protheus (ERP financeiro) via Slack + Agentforce, sem escalação N1 humana. Read-only, governança TI+Jurídico+DPO, rastreabilidade LGPD/TCU. Jornada J1 prioritária F1 Quick Wins. | Confirmed
E02 | Autoatendimento Chamados Técnicos | Permitir consulta de status de chamados no Pronto (ServiceNow) via Slack + Agentforce — quantos abertos, status crítico, SLA, histórico. Read-only F1, abertura assistida F2+. Reduz dependência fila N1 (~30k tickets/mês, 13-14k só INSS). Jornada J2 prioritária F1. | Confirmed
E03 | Intelligence Executiva Mobile | Executivos acessam briefing de projeto via agente conversacional antes de reunião urgente (ministérios, cliente crítico). Consulta CRM Totvs read-only via Slack — pipeline, contratos macro, forecast. Caso de uso: 'Maik convocado ao ministério, pergunta ao agente no caminho, chega pautado.' Jornada J5 prioritária F1. | Confirmed
E04 | Knowledge Base Normativas RH | Automatizar consulta a normativas internas (portal Conexão/SharePoint) via Agentforce KB: políticas RH, delegação de competência (alçadas de aprovação R$ 2M → quem assina?), compliance. Reduz acionamentos repetitivos ao time de Pessoas (-50% meta F1). Elimina risco de alçada incorreta em propostas/contratos (exposição TCU). Jornada J7 prioritária F1. | Confirmed
E05 | Agendamento Automatizado | Agendamento via comando de voz/texto no Slack integrado a Microsoft Teams calendário corporativo. Caso de uso: 'Pedro sai de reunião, manda áudio Agenda reunião amanhã com X, Y, Z, chega em casa tranquilo.' Elimina atrito cognitivo 'não esquece, não esquece'. Jornada J8 F1. | Confirmed
E06 | Adoção CRM via Conversação | Aumentar adoção de CRM Totvs comercial (~50 usuários ativos, ~30% do comercial) via interface conversacional Slack. Comercial atualiza pipeline, forecast, oportunidades por voz/texto, reduz atrito de login manual. Meta: +40% adoção via escrita controlada F2 Expansion. Jornada J4. | Confirmed
E07 | Abertura de Chamados Assistida | Abertura de chamados no Pronto (ServiceNow) via voz ou texto estruturado no Slack. Escrita controlada F2 Expansion (F1 read-only). Clientes externos + colaboradores internos. Reduz fricção ofício/reunião para abrir ticket. Jornada J3. | Confirmed
E08 | Gestão de Demandas Evolutivas | Consulta e criação de demandas evolutivas no Clarity (Broadcom) via Slack + Agentforce. Read-only F1, escrita F2+. ~4.500 demandas ativas. Decisão arquitetural pendente F2: se Salesforce Service Cloud vira sistema de origem de demandas, Clarity vira legado de consulta. Jornada J6 F3 Proactive. | Assumed
E09 | Intelligence Preditiva e Recomendações | Análise preditiva de SLA (J9) + recomendações comerciais (J10) via Data Cloud + Agentforce. Alertas proativos de risco de SLA breach no Pronto, sugestões de próximas ações comerciais baseadas em pipeline histórico CRM. F3 Proactive. Jornadas J9 e J10. | Assumed
E10 | Governança, Compliance e Change Management | Pilar cross-cutting: (1) MuleSoft/MCP camada de integração segura sobre legados (Pronto, Clarity, Protheus, CRM Totvs, Conexão, Teams) com rastreabilidade auditável LGPD/TCU; (2) Governança TI+Jurídico+DPO sobre Protheus (dados financeiros sensíveis, autorização perfil de acesso por usuário); (3) Change Management estruturado — treinamento formal por persona (clientes B2B, executivos, comercial, N1/N2), executive mandate (Saulo), capacitação early adopters (20-50 piloto), monitoramento KPIs adoção (>60% uso semanal); (4) Arquitetura reutilizável Data Ágil + Serviço na Ponta (economia de escopo). Prioridades estratégicas #2, #3, #4 do strategy.json. | Confirmed

## Gap Analysis
Gap ID | Category | Gap/Question | Impact/Notes
G0101 | Source Conflict | Workspace Slack segregation (clientes B2B externos vs. 3k funcionários internos) — decisão de segurança/governança não definida impacta autenticação, canais Slack Connect, e políticas DLP | Bloqueador arquitetura F1 — define se 1 workspace c/ controle DLP ou 2 workspaces isolados; decisão com TI+Jurídico+DPO Dataprev
G0102 | Missing Requirement | Volumetria Protheus ausente: quantas consultas financeiras/mês esperadas, quantos clientes B2B ativos baseline (2,500 orgs contratadas ≠ 2,500 org acessando), distribuição por tipo de query (contratos/pagamentos/valores em aberto) | Necessário para sizing MuleSoft API rate limiting, Agentforce Conversations usage, infra Heroku/Einstein; sem volumetria, estimate é Assumed
G0103 | Logical Gap | Governança TI+Jurídico+DPO para acesso Protheus financeiro não mapeada — quem aprova quais queries, fluxo aprovação, matriz RACI, janela aprovação pré-kick-off | Mencionado como 'required' mas não detalhado; risco de bloqueio F1 se aprovação levar semanas/meses; requer processo Change Management não scoped
G0104 | Missing Requirement | Experience Design ausente: clientes B2B (~10k licenças Slack baseline) nunca usaram Slack — UX research, onboarding design, content strategy, service design não scoped | Epic menciona 'Quick Win' mas onboarding 10k usuários externos requer Design System, help content, tutorial flows — esforço UX/Content não estimado
G0105 | Ambiguity | LGPD/TCU 'rastreabilidade' — retenção audit logs por quanto tempo (5 anos TCU?), onde armazenar (Data Cloud? Big Objects? External storage?), quem acessa, formato export para auditorias | Compliance crítico setor público mas spec técnica ausente — impacta storage costs, Data Cloud config, Shield Event Monitoring
G0106 | Capability Gap | Autenticação clientes B2B externos — Protheus/Totvs tem SSO/SAML? Ou senha individual? Slack Connect requer email verificado — como onboarding 2,500 orgs clientes sem IdP? | Se Protheus não tem SSO, alternativa é email magic link ou senha — friction onboarding alto; Slack Connect multi-org requer Identity Provider ou Slack Guest Accounts
G0107 | Potential Risk | F1 scoped 'read-only' mas caso de uso real pode demandar transacional (cliente vê valores em aberto no Protheus, quer pagar — ação fora Slack ou integração Protheus write?) | Risco scope creep F1→F2; validar com negócio se read-only satisfaz ou se pagamento/negociação de dívida é essencial para ROI
G0201 | Missing Requirement | Volumetria Pronto (ServiceNow) ausente detalhada: 30k tickets/mês total (~13-14k INSS), mas quantos usuários finais consultam status via Slack? Quantas queries/usuário/dia esperadas? | Necessário para Agentforce Conversations usage forecast, MuleSoft API calls/month, infra sizing; sem volumetria user-side, estimate é Assumed
G0202 | Logical Gap | Pronto (ServiceNow) é Dataprev-managed ou INSS-managed? Se INSS, API access requer aprovação externa (SLA? firewall? contrato?), risco timeline F1 | Dependência externa não mapeada — se Pronto é sistema INSS, acesso API pode exigir governance INSS (não só Dataprev), adicionando 4-8 semanas approval
G0203 | Ambiguity | F2 'abertura assistida' de chamados — 'assistida' significa Agentforce preenche form com NLU + usuário confirma, ou Agentforce abre ticket direto sem aprovação humana? | Impacta F2 complexity (form pre-fill é config low-code, abertura autônoma é Write API + approval workflow custom code) e governança (quem responde por ticket aberto por IA?)
G0204 | Missing Requirement | SLA tracking — Pronto expõe SLA via API estruturada (tempo restante, % cumprimento) ou apenas data criação/resolução? Agentforce precisa calcular SLA client-side? | Se SLA não é API field direto, requer custom logic MuleSoft para calcular — adiciona complexity integration layer
G0205 | Capability Gap | Histórico chamados (audit trail) — Pronto API retorna comments/attachments/reassignments ou só status atual? Chat conversacional Slack requer contexto completo | Se API Pronto é shallow (só status), experiência Slack será limitada vs. portal ServiceNow full; user expectation mismatch, adoção em risco
G0206 | Potential Risk | ~30k tickets/mês, 13-14k só INSS — concentração alta em 1 cliente (46%); se INSS migrar sistema ou renegociar contrato Dataprev, volumetria cai pela metade, ROI impactado | Risco negócio — dependency on single large customer (INSS) para justificar investimento Agentforce; diversificação cliente crítica para sustainability
G0207 | Missing Requirement | Baseline métrico ausente — NPS/CSAT atual portal Conexão/ServiceNow, tempo médio primeira resposta N1, taxa desvio (tickets reabertos), satisfação canal — sem baseline, ROI F1/F2 não mensurável | Discovery menciona 'coletar antes F1' mas não scoped como activity — requer survey design, coleta, análise (esforço BA/UX 2-3 semanas pré-kick-off)
G0301 | Ambiguity | CRM Totvs — qual produto Totvs? (Totvs CRM, Totvs Fluig, Totvs RM?) API availability, data model, autenticação variam por produto | Faltando vendor/product ID exato — impacta feasibility study integration (algumas soluções Totvs não expõem API REST moderna, requer SOAP/RPC legacy)
G0302 | Missing Requirement | 50 usuários ativos baseline CRM Totvs (~baixa adoção segundo discovery) — quem são os executivos target (~50 pessoas totais ou subset executivo menor, ex. C-level/Diretoria ~10-15)? | Scoping 'executivos' sem headcount/perfis impede sizing licenças Slack (Einstein 1 vs. Standard), effort onboarding, ROI calculation
G0303 | Logical Gap | Caso de uso 'convocação urgente ministério, briefing no caminho' — mobile-first, mas Slack mobile app requer install (iOS/Android); executivos gov usam smartphone corporativo Dataprev (MDM?) ou pessoal? | Se smartphone pessoal, política BYOD/segurança não mapeada (dados sensíveis CRM em device não gerenciado); se corporativo, requer IT approval/MDM config (timeline risk)
G0304 | Ambiguity | Dados CRM 'pipeline, forecast, contratos macro' — granularidade? Valores totais agregados (ex. 'R$ 15M pipeline Q3') ou deal-level detail (25 opportunities × R$ 600k cada)? | Granularidade impacta UX (exec quer dashboard summary ou drill-down?), data volume API calls, e Agentforce prompt complexity (aggregation logic onde? CRM ou Agentforce?)
G0305 | Capability Gap | CRM Totvs baseline 50 users ativos (baixa adoção) — dados estão atualizados/completos ou stale? Agentforce responde com dados desatualizados = perda confiança executivo | Baixa adoção CRM pode significar data quality ruim (pipeline não reflete realidade, forecast desatualizado 2-3 meses); validar data quality antes F1 ou épica vira fracasso
G0306 | Potential Risk | Épica E03 smallest user base (~10-15 executivos?) vs. E01 10k clientes, E02 3k funcionários — ROI per-user baixo, risco desprioritização ou cancelamento se F1/F2 consomem budget | Executivos são high-value users mas low-volume; justificar investimento requer storytelling forte (visibilidade C-level > economia escala); risco phase 2+ cut se budget aperta
G0307 | Missing Requirement | Autenticação executivos mobile — CRM Totvs tem SSO/SAML mobile-compatible? Ou senha? Slack mobile SSO requer Identity Provider (Okta/Azure AD/Salesforce Identity) configurado | Se Totvs CRM não tem mobile SSO, executivo precisa login duplo (Slack + CRM web) — friction alto, adoção em risco; Identity Provider unificado (ex. Salesforce Identity) não scoped
G9901 | Missing Requirement | Centro de Excelência (CoE) / Governança contínua pós-F1 não scoped — quem mantém Agentforce prompts, quem aprova novos use cases Slack Connect, quem monitora usage/costs Agentforce Conversations? | Três épicas F1 implicam governança multi-sistema (Protheus+Pronto+CRM Totvs + MuleSoft + Agentforce) mas nenhum esforço Change Management/CoE/Governance scoped; risco sprawl/shadow IT
G9902 | Logical Gap | MuleSoft vs. MCP (Model Context Protocol) — discovery menciona 'MuleSoft/MCP' mas MCP é protocolo lightweight (Anthropic) para tool-calling, não substitui MuleSoft enterprise integration; arquitetura híbrida não detalhada | Se intent é usar MCP direto (Agentforce → backend sem MuleSoft), economiza licensing MuleSoft mas perde enterprise features (rate limiting, monitoring, API governance); trade-off não analisado
G9903 | Ambiguity | Slack Ultimate 'já contratado' — quantas licenças? 10k clientes B2B + 3k internos = 13k licenses? Ou só subset? Impacta se projeto precisa budget licenças adicionais ou só PS | Slack Ultimate contracted mas não clear se cobre full scope; se shortfall licenças, requer budget approval adicional (risk timeline/approval)
G9904 | Potential Risk | Três épicas F1 são todos read-only systems of record diferentes (Protheus/Pronto/CRM Totvs) — nenhum write/transacional scoped F1, mas user expectation pode ser 'resolver no Slack' (pagar fatura, reabrir ticket, atualizar pipeline) | Risco expectation mismatch — users veem dados no Slack mas precisam sair para agir (break in flow); adoção em risco se não houver quick wins transacionais F2
G9905 | Missing Requirement | Heroku architecture (discovery context) — será usado para MuleSoft runtime/Agentforce endpoints? Versão Heroku (v22 mencionado em outro projeto DATAPREV)? Dynos sizing/costs não scoped | Heroku pode ser runtime para APIs MuleSoft e Agentforce Actions, mas infra não detalhada — impacta commercials (Heroku costs separados de PS estimate)
G9906 | Capability Gap | LGPD Art. 48 (comunicação de incidente segurança à ANPD) — se Agentforce vazar dado financeiro Protheus via Slack (ex. query errada retorna CPF/valores third-party), processo incident response não mapeado | Setor público + dados financeiros sensíveis requer IR plan (quem notifica ANPD? em quanto tempo? log forensics onde?); Security/Compliance workstream ausente estimate
G9907 | Potential Risk | Três sistemas source-of-truth legados diferentes (Protheus Totvs / Pronto ServiceNow / CRM Totvs) — vendor lock-in risk; se um vendor descontinua produto ou API, épica inteira quebra | Nenhum dos três é Salesforce native; dependência total em vendors third-party para API stability/roadmap; requer exit strategy ou fallback (ex. data replication para Data Cloud)
G0401 | Source Conflict | Portal Conexão (SharePoint) as KB source — integration mechanism undefined. Discovery mentions 'Agentforce KB consulta' but no technical bridge specified (MuleSoft connector, Data Cloud sync, custom API, batch ETL). Conflicts with standard Agentforce Knowledge Article grounding patterns. | [KB:USB - UNIFIED SOLUTION BLUEPRINT - V2.0 - PT.md:657-705] covers CoE governance and knowledge management strategy but assumes Salesforce Knowledge as native source. SharePoint as external source requires integration architecture (System API layer) not scoped. BLOCKER for F1 Quick Win timeline — integration design + build effort missing.
G0402 | Missing Requirement | Experience Design gap: No UX research, content design, or service design effort scoped for conversational interface. 'Políticas RH, delegação competência' implies complex multi-turn dialogues, error handling, escalation paths — requires dialogue flow design, conversation mapping, and user testing before build. | E04 described as 'Quick Win' but conversational AI for HR policy (high-stakes domain — signing authority, compliance) needs usability validation. Per instructions: new user-facing surfaces with no UX effort = Missing Requirement buyer-facing question. Recommend Phase 0 discovery or F1 pre-sprint design allocation.
G0403 | Ambiguity | Alçadas delegation authority (R$ 2M threshold example) — business rule complexity unclear. Is it hierarchical (role-based), conditional (contract type × value), or dynamic (approval matrix)? Is the R$ 2M figure a single threshold or one of many tiers? How many approval scenarios exist? | Sizing impact: Simple = 1 rule (L), Complex tiered matrix = (XL). Meta '-50% acionamentos time Pessoas' depends on rule coverage — partial automation worse than no automation (exposes gaps, erodes trust). Recommend discovery workshop with Pessoas/Jurídico to map full approval matrix.
G0404 | Logical Gap | TCU compliance claim ('Elimina risco alçada incorreta — exposição TCU') not grounded in KB. No audit trail, version control, or change management process defined for KB content updates. Who governs policy updates? How are outdated policies retired? Is there a 'last-reviewed' metadata field? | [KB:USD - UNIFIED SCOPING DOCUMENT - V2.0 - PT.md:741-760] Section 9.4 covers 'IA Ética e Inovação Responsável' but doesn't address policy KB governance. TCU audits require provenance trail — when was policy consulted, which version, who approved. Gap: no Data Stewardship or Content Governance effort in E04. Recommend CoE oversight + version-control design.
G0405 | Potential Risk | LGPD risk: HR policies may reference employee PII (names, roles, salaries in approval examples). Is SharePoint content LGPD-compliant? Does Agentforce KB ingest personal data? Is Einstein Trust Layer (PII masking) scoped? | [KB:Advanced Strategic Architecture and Value Analysis_ Slack as an Agentic Operating System (Agentic OS) & Agentforce 360.md:33] Section on 'Enterprise-Level Security and Encryption Governance' covers EKM and Einstein Trust Layer but no explicit PII masking plan for E04. Public-sector vertical + HR domain = high LGPD exposure. Recommend data classification workshop + Trust Layer config in F1.
G0406 | Capability Gap | No fallback/escalation path defined. When Agentforce KB cannot resolve a query (ambiguous policy, policy gap, edge case), what happens? Does it escalate to time Pessoas (defeating -50% deflection goal), log to a case, or surface 'no answer found'? | [KB:Advanced Strategic Architecture and Value Analysis_ Slack as an Agentic Operating System (Agentic OS) & Agentforce 360.md:23-24] Service Swarming pattern is defined for complex incident resolution but not mapped to E04. Recommend 'Agent → Human' handoff design: when to escalate, to whom, SLA. Without this, partial coverage KB becomes a CX liability.
G0407 | Missing Requirement | Governance gap: Multi-team ownership implied (IT owns Slack/Agentforce, Pessoas owns policy content, Jurídico/DPO owns compliance, TI validates SharePoint sync). No decision rights, RACI, or CoE structure scoped for E04. | [KB:USB - UNIFIED SOLUTION BLUEPRINT - V2.0 - PT.md:657-705] Section 7 defines CoE model but doesn't allocate governance effort to specific epics. Per instructions: multi-team ownership with no governance/CoE/CM effort = Missing Requirement buyer-facing question. Discovery noted 'Governança Protheus (TI+Jurídico+DPO) — bloqueador pré-kick-off F1' — this applies to E04 too.
G0501 | Source Conflict | Microsoft Teams calendar integration mechanism undefined. Discovery says 'Comando voz/texto Slack → Microsoft Teams calendário' but no technical bridge specified. Slack native workflow, MuleSoft API orchestration, or Microsoft Graph API custom connector? | [KB:USD - UNIFIED SCOPING DOCUMENT - V2.0 - PT.md:335-352] Section 3.9 MuleSoft covers API-led connectivity strategy but E05 doesn't reference it. Microsoft Teams = external system → requires System API design (MuleSoft or custom). Conflicts with 'F1 Quick Win' if integration build effort not scoped. Recommend technical design spike before sizing.
G0502 | Ambiguity | Voice input ('áudio comando voz') — is this Slack native voice message transcription, or custom speech-to-text (STT) integration (AWS Transcribe, Google Speech API)? Slack does not natively parse voice messages into structured calendar actions. | If voice = just a voice message that a human parses, no AI needed (S). If voice = STT → intent parsing → calendar API call (XL custom). Example 'Agenda reunião amanhã X, Y, Z' implies NLP intent extraction (participants, date, time). Sizing depends on interpretation — current 'F1 Quick Win' may be under-scoped if STT + NLP required.
G0503 | Logical Gap | Meeting invite delivery — does the bot send calendar invites to participants, or just create an event in one person's calendar? If multi-participant, how are email addresses resolved (Slack handle → email mapping, AD lookup, manual input)? | Example 'X, Y, Z' participants — are these Slack @mentions, email addresses, or free text? Calendar invites require email addresses. No directory integration (Azure AD, Okta) mentioned in discovery. Gap: identity resolution not scoped. Recommend discovery clarification before F1.
G0504 | Potential Risk | Microsoft 365 tenant permission risk — creating calendar events in Teams requires OAuth consent and Graph API app registration. Who owns the Azure AD service principal? What happens if Microsoft revokes API access or changes Graph API versioning? | Public-sector client (DATAPREV) may have strict policies on third-party app access to Microsoft tenant. No 'IT Security approval' step in discovery. Recommend pre-F1 validation: can IT grant calendar.readwrite scope to Slack/MuleSoft app? Blocker risk if denied.
G0505 | Missing Requirement | Experience Design gap: No conversation design for error states. What happens when: (a) requested time slot conflicts with existing meeting, (b) participant not found, (c) invalid date ('amanhã' on Friday → Monday or next business day?), (d) ambiguous time ('manhã' = 9am or 10am?)? | Per instructions: new conversational interface with no UX/service design effort = Missing Requirement. E05 is thin-feature 'Quick Win' but error handling design still required — bad UX in F1 kills adoption ('atrito cognitivo' the epic claims to eliminate). Recommend dialogue flow mapping before build.
G0506 | Capability Gap | No calendar read capability defined — can the bot check for conflicts before booking? If yes, does it access Teams calendar via API (requires additional Graph API scope). If no, users receive double-booked conflicts → manual cleanup → defeats 'Elimina atrito cognitivo' goal. | [KB:Advanced Strategic Architecture and Value Analysis_ Slack as an Agentic Operating System (Agentic OS) & Agentforce 360.md:30] Workflow Builder + Salesforce Flow orchestration pattern defined, but no mention of bi-directional calendar sync or conflict detection. Recommend capability confirmation: read-only calendar access in scope?
G0601 | Source Conflict | CRM Totvs as external system — integration mechanism undefined. Discovery says 'comercial atualiza pipeline/forecast/oportunidades por voz/texto' but no API bridge specified. Totvs CRM REST API, SOAP, batch file export, or custom connector? | [KB:USD - UNIFIED SCOPING DOCUMENT - V2.0 - PT.md:335-352] MuleSoft API-led connectivity strategy assumes System API layer for external CRM. E06 doesn't mention MuleSoft — conflicts with architecture. Also: does Totvs CRM support real-time API updates, or batch only? Sizing depends on API maturity. Recommend technical discovery spike.
G0602 | Ambiguity | Voice/text input scope unclear. Is this (a) free-form natural language ('Fechei deal com Acme, R$ 500k, etapa Proposta'), or (b) structured command ('/crm update opp=Acme stage=Proposal amount=500000')? NLP complexity vastly different. | Meta '+40% adoção via escrita controlada' suggests structured input (easier, faster to build — M/L). But 'interface conversacional' + 'voz/texto' suggests free-form NLP (harder, requires intent parsing, entity extraction — XL). Ambiguity impacts F2 timeline. Recommend interaction model definition before sizing.
G0603 | Logical Gap | User population mismatch: '~50 users ativos, ~30% do comercial' — implies 170 total comercial headcount (50 / 0.3 ≈ 167). But adoption goal '+40%' would mean 70% final adoption (30% + 40% = 70%) = 119 users. Is Totvs licensed for 119 concurrent users? Is Slack conversational interface replacing Totvs UI or augmenting it? | If replacing → Totvs license cost reduction (commercial benefit, but UI replication scope grows — XL). If augmenting → Totvs licenses stay, Slack is just input layer (M). Discovery doesn't clarify replacement vs. augmentation strategy. Impacts both sizing and commercial model. Recommend clarification before F2.
G0604 | Potential Risk | Data sync latency risk: Totvs CRM update via Slack → how fast does data propagate? If batch (nightly), sales managers see stale pipeline in Totvs during the day → defeats real-time adoption goal. If real-time API, is Totvs CRM performant enough (30-170 concurrent Slack updates)? | No SLA or latency requirement in discovery. Public-sector CRM systems often batch-oriented (legacy architecture). Recommend non-functional requirements (NFR) discovery: Totvs API response time, throughput limits, retry logic. Blocker if Totvs cannot sustain real-time load.
G0605 | Missing Requirement | Experience Design gap: No conversation design for CRM update flows. Minimal: 'Update opp X stage to Y' (single-turn, structured). Complex: multi-turn dialogue ('Which opp?' → 'Acme deal' → 'New stage?' → 'Proposal' → 'Amount?' → '500k' → confirm). Scope undefined. | Per instructions: new user-facing conversational surface, no UX effort scoped = Missing Requirement. '+40% adoção' goal requires usability validation — if UI is clunky, adoption stays at 30%. Recommend service design workshop: journey mapping, dialogue trees, error states. F2 timeline may need UX sprint.
G0606 | Capability Gap | No read capability defined — can users query Totvs CRM via Slack ('Mostre meu pipeline', 'Qual stage do deal Acme?'), or only write (update)? If read required, doubles integration scope (query API + response formatting). If write-only, limits utility → adoption ceiling. | [KB:Advanced Strategic Architecture and Value Analysis_ Slack as an Agentic Operating System (Agentic OS) & Agentforce 360.md:22-23] Slack Sales Elevate pattern includes read (List Views, deal summaries) + write (stage updates). E06 only mentions 'atualiza pipeline/forecast/oportunidades' (write). Recommend capability confirmation: is CRM read access in scope?
G0607 | Missing Requirement | Governance gap: Who owns Totvs CRM data quality after Slack updates? If commercial team bypasses Totvs UI validation rules via Slack API, dirty data risk (missing required fields, invalid stage transitions). No data stewardship or validation logic scoped. | [KB:USB - UNIFIED SOLUTION BLUEPRINT - V2.0 - PT.md:657-705] CoE governance model covers Salesforce data stewardship but doesn't address external CRM (Totvs). Per instructions: multi-system data ownership, no governance effort scoped = Missing Requirement. Recommend validation: does Slack integration enforce Totvs business rules, or bypass them?
G0608 | Logical Gap | Jornada J4 (F2 Expansion) dependency on E06 unclear. Discovery lists 'Jornada J4' but no journey map provided. What prerequisites must F1 deliver for J4 to proceed? If E06 is blocked/delayed, does J4 slip? | No journey architecture in discovery notes. 'Jornada J4' mentioned without context. Recommend journey mapping workshop to clarify E06 → J4 dependency chain and sequence F2 epics correctly. Risk: F2 timeline assumes E06 complete, but if E06 is XL (not M/L), J4 delivery slips.
G0609 | Ambiguity | Baseline measurement gap: 'Meta: +40% adoção' — baseline date undefined. Is current 30% adoption measured over last 30 days, 90 days, or 12 months? Seasonal variation (Q4 high sales activity vs. Q1 lull) affects baseline validity. | Discovery notes 'Baseline NPS/CSAT pendente' — adoption baseline also pending. Without time-bounded baseline, +40% target is unverifiable. Recommend pre-F1 metric collection: 30-day active users in Totvs CRM (login count, transaction count) as adoption baseline.
G0610 | Potential Risk | Change management risk: 50 → 119 users (+138% growth) in comercial workforce using new conversational UI. No training, onboarding, or adoption plan scoped in E06. Risk: low adoption despite feature availability → 'meta +40%' missed. | [KB:USB - UNIFIED SOLUTION BLUEPRINT - V2.0 - PT.md:124-132] Section 2.3 covers change management methodology but no epic-level CM effort allocation. Per public-sector vertical: training/adoption critical for gov workforce. Recommend F2 change management workstream: training content, lunch-and-learns, champions program.
G0701 | Missing Requirement | Abertura de Chamados — Volume metrics undefined: How many chamados are created monthly/annually? What is the target response time? What is the baseline resolution SLA per priority? These sizing inputs are critical for determining Agentforce conversation limits, Slack message volume quotas, and MuleSoft API call projections. | Without volumetrics, capacity planning for Slack Ultimate (message limits), Agentforce (conversations/month), and MuleSoft/MCP (API throughput) cannot be validated. Risk of under-provisioning or over-cost.
G0702 | Source Conflict | Abertura de Chamados — F2 'escrita controlada' vs. full write capability: The epic states 'F2 escrita controlada' for ServiceNow case creation, but does not define 'controlada' — does this mean write-only specific fields, approval workflow required before save, or read-verify-before-write? The architectural choice (Slack modal with write-once vs. bidirectional sync vs. approval orchestration) differs significantly. | Affects MuleSoft/MCP API design (System API vs. Process API complexity), Agentforce intent routing logic, and F2 effort estimate. KB warns that 'L: structured use case like Swarming implies channel lifecycle + specialist routing' — uncontrolled write is simpler (M), approval orchestration is (L).
G0703 | Capability Gap | Abertura de Chamados — Slack-native voice input: Epic states 'voz/texto Slack', but Slack does not natively support voice transcription — voice messages (audio clips) yes, but transcription to text requires a third-party service (e.g., AWS Transcribe, Google Speech-to-Text via MuleSoft). Is this in scope? If yes, which transcription service and what is the latency SLA? | If voice-to-text transcription is required, adds MuleSoft integration to a transcription API + prompt engineering to Agentforce to handle transcription errors. If not, clarify 'voz' means audio clips only (file attachment, not NLP input). Latter is simpler but does not enable the 'assistida' NLP value prop.
G0704 | Missing Requirement | Abertura de Chamados — UX research and service design: 'Reduce friction ofício/reunião to open ticket' implies a behavioral shift for 2,500 external orgs + 3k internal employees. Has UX research been conducted to validate that Slack is the preferred channel vs. email/portal/phone? Is there a service design blueprint for the Slack conversation flow (prompt library, disambiguation logic, escalation to human)? Without this, risk of low adoption and rework. | Discipline gap per instructions: 'if new user-facing surfaces imply UX research/service design but no effort scoped, raise as Missing Requirement buyer-facing question'. This is a buyer-facing question — needs Executive Mandate (Saulo) + Change Management discovery (persona journey maps, training plan per J3 persona).
G0801 | Ambiguity | Gestão de Demandas Evolutivas — Clarity as 'sistema origem' or 'legado de consulta': The F2+ decision states 'Salesforce Service Cloud vira sistema origem demandas, Clarity vira legado de consulta'. This is a strategic architecture decision with deep implications: (1) Migration strategy — how are the ~4,500 active demands migrated from Clarity to Service Cloud? One-time bulk vs. phased vs. dual-run? (2) Co-living period — how long? (3) Data model — Service Cloud Work Order, Case, or custom object? (4) Clarity API — read-only or does it stay authoritative for closed demands? (5) MuleSoft API-led layering — is Clarity a System API or does Service Cloud own the System API? This is a transformational decision (USB Section 3 warns 'strategic/transformational = multi-cloud, multi-vendor, changes existing systems') but lacks a migration playbook. | Affects F2+ timeline (co-living period = risk adder), F3 Proactive feasibility (Data Cloud unification cannot happen until Service Cloud is authoritative), and MuleSoft integration complexity (bidirectional sync during co-living = L/XL). This is a 'hard-to-reverse, scope-shaping call' per decision_log rules — should be in data/strategy.json + data/roadmap.json Phase dependencies, but is currently only a one-line assertion in the epic brief.
G0802 | Missing Requirement | Gestão de Demandas Evolutivas — Volumetrics and business process: ~4,500 active demands — what is the annual creation rate? Average lifecycle (idea → analysis → approved/rejected → backlog → in-progress → deployed)? How many lifecycle states in Clarity vs. what Service Cloud will model? What is the approval workflow (single approver, multi-tier, steering committee)? These are inputs to Service Cloud data model design (object choice, record types, approval flows, reporting), Agentforce intent complexity (how many states can the agent update vs. must route to human), and F2+ effort. | Without business process map (L1/L2/L3 per USD Section 2.1), risk of under-scoped data model + approval orchestration. KB warns 'L: flows orquestram processo de negócio = MuleSoft Process API + Salesforce approval automation' — this is L at minimum, possibly XL if multi-tier approval + external stakeholder notifications.
G0803 | Potential Risk | Gestão de Demandas Evolutivas — Clarity API availability and performance: Is Broadcom Clarity's API documented, performant, and stable enough for real-time Slack queries? What is the API rate limit? Is there a Clarity champion on DATAPREV's side to unblock API access issues? If Clarity API is undocumented or brittle, this becomes a 'high-risk integration' per RBS A1. | External dependency risk (RBS B4). If Clarity API is unavailable or slow, the entire F1/F2 value prop (read + create demands from Slack) is blocked. Mitigation: early API discovery + fallback to batch sync if real-time is infeasible.
G0804 | Missing Requirement | Gestão de Demandas Evolutivas — Service Cloud license and entitlement strategy: If Service Cloud becomes the system of record for ~4,500 demands (likely Work Orders or Cases), who are the licensed users? Is it the 3k internal employees (all get Service Cloud licenses)? Or a smaller 'demand management squad' (~50-100 people) with everyone else interacting via Slack (Community/Partner licenses or no license)? This is a license architecture decision with direct cost impact. | Affects commercials (Service Cloud license cost not scoped in discovery brief) and solution architecture (entitlement model: Experience Cloud portal for external clients vs. Slack-only access). This is an Org62 financial input the seller must supply — not a model-invented number.
G0901 | Ambiguity | Intelligence Preditiva — Data Cloud data model and unification scope: E09 depends on Data Cloud unifying Pronto (ServiceNow), Clarity, Protheus, CRM Totvs, Conexão (sistema?), and potentially Slack conversation history. What is the CDO (Common Data Object) strategy? Are these systems' data models documented? What is the data quality baseline (deduplication, completeness)? Data Cloud unification is F3 per the brief, but the epic does not specify *which* objects/entities are unified — is it just Cases/Work Orders, or also Accounts (2,500 external orgs), Contacts, Users, and financial data from Protheus? | Data Cloud effort is notoriously under-estimated when data model discovery is skipped. KB warns 'L: múltiplas fontes de dados, modelo e unificação = 3-5 sistemas' and 'XL: múltiplos sistemas complexos (SAP, Oracle EBS) = conectores especializados'. Protheus (financial ERP) is Oracle/TOTVS — likely XL. Without a CDO blueprint, this is 'Inadequate Discovery' per RBS C1.
G0902 | Missing Requirement | Intelligence Preditiva — Agentforce + Data Cloud proactive alerting: J9 (SLA breach alertas proativos) and J10 (sugestões comerciais pipeline histórico) imply Agentforce reads Data Cloud calculated insights and pushes Slack messages. This is a 'Proactive Agentforce' pattern — does this require Einstein Discovery models (regression for SLA breach prediction, opportunity scoring for pipeline suggestions) or just rule-based alerting (SLA countdown threshold)? If ML-based, who trains the models, what is the training data volume, and what is the accuracy target? | If Einstein Discovery models are required, this is an AI/ML workstream (data scientist + training dataset preparation + model validation + retraining cadence) — not scoped in the epic brief. If rule-based only (simpler), clarify so effort is not under-estimated. This is a 'product/feature dependency' per RBS B4 — Agentforce + Data Cloud proactive capabilities are GA but Einstein Discovery training is a separate deliverable.
G0903 | Source Conflict | Intelligence Preditiva — Pipeline histórico = which system? J10 'sugestões comerciais pipeline histórico' — is 'pipeline' in CRM Totvs (commercial opportunities), Clarity (demand backlog), or both? If both, how does Data Cloud unify 'opportunity' concepts from two different systems with likely different stages/definitions? This is a semantic data modeling challenge — needs a business glossary + CDO mapping per USD Section 3.5. | If CRM Totvs and Clarity both have 'pipeline' objects, Data Cloud must reconcile them into a unified 'Opportunity' or 'Demand' CDO. Without business glossary alignment, risk of 'apples vs. oranges' recommendations. This is a 'Complex Data Model' per RBS C3.
G0904 | Potential Risk | Intelligence Preditiva — LGPD consent and data minimization: SLA breach alertas and pipeline suggestions imply profiling internal employees and external clients. Does this require LGPD consent (Art. 7, I — consentimento) or is it 'legitimate interest' (Art. 7, IX)? If consent is required, how is it captured and revoked? Data Cloud must respect LGPD data minimization (Art. 6, III) — are calculated insights anonymized or pseudonymized? Is there a DPO review checkpoint before F3 Proactive go-live? | LGPD compliance is a blocker per E10 (Governança, Compliance). If consent management is not designed into Data Cloud segmentation + Agentforce proactive flows, this is a 'Compliance or Legal Requirements' risk per RBS D3. Must involve DPO + Jurídico early (pre-F3 kick-off).
G1001 | Missing Requirement | Governança/Compliance/Change Management — MuleSoft/MCP API governance model: E10 states 'MuleSoft/MCP camada integração segura legados' with 'rastreabilidade LGPD/TCU'. What is the API governance framework? Is there an API catalog (Anypoint Exchange), API policies (rate limiting, OAuth, mTLS per USD MS-NFR-002), and audit logging (who called which API when with what payload)? TCU audit trail requirements are stricter than typical private-sector — is there a TCU compliance playbook? | Without API governance, risk of 'Lack of systems documentation' (RBS A4) and 'Complex Security Solution' (RBS A1). MuleSoft API Manager + Anypoint Monitoring are the tooling, but the *process* (who approves API publication, change control for breaking changes, audit log retention period) must be defined before F1 integration build starts. This is a CoE deliverable (E10's third pillar) — should be scoped as a separate workstream, not just 'assumed operational'.
G1002 | Missing Requirement | Governança/Compliance/Change Management — Protheus governance (TI+Jurídico+DPO) blocker resolution: E10 flags 'Governança Protheus (TI+Jurídico+DPO) — bloqueador pré-kick-off F1'. What is the blocker? Is it (1) Protheus API access not approved by TI/Jurídico, (2) DPO has not signed off on data sharing between Protheus and Salesforce, or (3) Protheus system owner (Finance?) has not committed to API SLA? This is a 'Customer compelling event' (RBS B4) — if unresolved, F1 cannot start. | This is a pre-sales qualification gate — should be surfaced to the seller (Org62 opportunity owner) immediately. If Protheus API access is blocked by Jurídico/DPO, the entire integration strategy (MuleSoft System API to Protheus) is at risk. Mitigation: escalate to Executive Sponsor (Saulo per Change Management brief) + schedule tri-party governance meeting (TI + Jurídico + DPO + Salesforce Architect) before proposal submission.
G1003 | Missing Requirement | Governança/Compliance/Change Management — Change Management structured plan: E10 states 'Change Management estruturado — treinamento por persona, executive mandate (Saulo), early adopters 20-50 piloto, KPIs adoção >60% uso semanal'. This is a strong CM vision, but lacks: (1) Persona journey maps (which personas per J3/J6/J9/J10?), (2) Training delivery model (Train-the-Trainer, live sessions, video library, Trailhead modules?), (3) Pilot selection criteria (which orgs/departments for the 20-50 early adopters?), (4) KPI measurement mechanism (Slack Analytics, Salesforce dashboards, weekly survey?), (5) Resistance mitigation plan (what if adoption <60% after 3 months?). Without these, risk of 'Inadequate Change Management strategy' (RBS C4) and low user adoption. | Discipline gap per instructions: 'if multi-team ownership, data stewardship, decision rights implied but no governance/CoE/CM effort scoped, raise as Missing Requirement buyer-facing question'. This is a buyer-facing question — needs a dedicated CM workstream (likely 1 CM Lead + 2-3 training specialists) spanning F1-F3, not just 'assumed to happen'. Should be scoped separately with its own epics/stories in data/epics.json.
G1004 | Ambiguity | Governança/Compliance/Change Management — 'Arquitetura reutilizável Data Ágil + Serviço na Ponta (economia de escopo)': This is stated as a strategic priority but undefined. Does 'reutilizável' mean (1) the MuleSoft APIs built for Data Ágil can be reused by Serviço na Ponta (a separate engagement?), (2) the Agentforce intents/prompts are templatized for multi-engagement reuse, or (3) the Slack workspace setup (channels, workflows, apps) is cloned for Serviço na Ponta? What is the 'economia de escopo' quantified as — % reduction in F1/F2/F3 effort for Serviço na Ponta, or license/infrastructure cost sharing? | If this is a multi-engagement strategy (Data Ágil is engagement 1, Serviço na Ponta is engagement 2), the architecture must be designed for reuse from F1 — affects MuleSoft API design (generic System APIs vs. Data Ágil-specific), Agentforce prompt library (parameterized intents), and Slack org structure (single workspace with sub-teams vs. separate workspaces). Without clarity, risk of rework if Serviço na Ponta requirements conflict with Data Ágil implementation choices.
G1005 | Potential Risk | Governança/Compliance/Change Management — Slack workspace único vs. separado for external clients (2,500 orgs): The brief states '2,500 org clients (B2B self-service) + 3k internal employees' but does not specify workspace architecture. Is it (1) one Slack Enterprise Grid workspace with Slack Connect channels per external org (scales to thousands of external orgs but complex permission model), or (2) separate Slack workspaces per external org (simpler permissions but operationally heavy), or (3) all external clients interact via a Salesforce Experience Cloud portal that *embeds* Slack (hybrid)? This is a foundational architecture decision affecting Slack Ultimate licensing, Agentforce deployment model, and security posture. | This is flagged as an 'open thread to validate' in the discovery brief, but it's load-bearing — must be resolved before F1 architecture is finalized. If Slack Connect is chosen, need to validate Slack Ultimate entitlements (how many external orgs per contract?). If Experience Cloud is chosen, need to scope portal build effort (not in E07-E09). This is a 'Solution requirements not fully understood' risk (RBS C1).

## Estimates
Item ID | Item Type | T-Shirt Size | Size Rationale | Complexity Drivers | Skills Needed | Risks | Solution Approach | Confidence
E01 | epic | L | L — driven by Sharing/Security (XL: Protheus governance blocker, perfil de acesso per user, LGPD/TCU audit trail, Slack EKM) + Intelligence/AI (L: Agentforce agent + MCP grounding) + Integration (L: MuleSoft OAuth + middleware + audit logging). Automation + UI modest. | Protheus ERP governance blocker (TI+Jurídico+DPO tri-party meeting required pre-kick-off — Gap G1002), MuleSoft API exposure + perfil de acesso enforcement per user, LGPD/TCU rastreabilidade (every API call logged, 5-year retention), Slack EKM deployment (AWS KMS master keys under CISO control), Agentforce conversational design for financial queries (grounding via MCP federation) | Agentforce developer (agent + prompt engineering), MuleSoft architect (API exposure + OAuth + middleware), Salesforce security architect (perfil de acesso model + audit trail + EKM), integration developer (Protheus ERP API), Slack admin (Enterprise Grid + EKM config) | Protheus governance blocker (Gap G1002): tri-party TI+Jurídico+DPO meeting must complete before F1 kick-off — escalate to seller immediately. Fallback: defer J1 to F2, launch F1 with J2/J5/J7/J8 only. Protheus API compatibility unknown (Gap G0102) — validate auth model + rate limits + perfil de acesso enforcement mechanism with TI before F1 build. Volumetria unknown (Gap G0102) — capacity planning for MuleSoft API calls blocked; F1 pre-kick-off audit required. | Agentforce agent (J1 Consultas Financeiras) orchestrates conversational financial queries in Slack → MuleSoft Anypoint API exposes Protheus ERP read-only REST APIs → perfil de acesso per user enforced via middleware (TI+Jurídico+DPO governance model) → agent returns valores em aberto + status + vencimento as Slack message cards. Every API call logged (user ID + timestamp + query + response status) for LGPD/TCU audit trail. Slack EKM (Enterprise Key Management) deployed F1 — AWS KMS master keys under Dataprev CISO control for instant revocation capability (motivated by prior 2.8M CPF breach). Agent grounding via MCP federation (Slack channel history + Protheus API responses) to minimize hallucination on financial data. | Assumed
E02 | epic | M | M — driven by Integration (M: ServiceNow REST API + OAuth) + Intelligence/AI (M: Agentforce agent + conversational design). Lower complexity than E01 (no Protheus governance blocker, no perfil de acesso per-user enforcement). | Pronto (ServiceNow) REST API integration (~30k tickets/month volume, ~13-14k from INSS), MuleSoft API exposure + OAuth 2.0, Agentforce conversational design for ticket status queries (quantos abertos, SLA, histórico), LGPD/TCU audit trail (every API call logged) | Agentforce developer (agent + prompt engineering), MuleSoft architect (API exposure + OAuth), integration developer (ServiceNow Pronto API), Slack admin | Pronto (ServiceNow) API compatibility unknown (Gap G0201) — validate auth model + rate limits + required fields with TI before F1 build. Volumetria unknown (Gap G0201) — ~30k tickets/month assumed, validate with TI for MuleSoft capacity planning. | Agentforce agent (J2 Autoatendimento Chamados) orchestrates conversational ticket status queries in Slack → MuleSoft Anypoint API exposes Pronto (ServiceNow) read-only REST APIs → agent returns ticket count, SLA status, resolution history as Slack message cards. F1 read-only eliminates N1 dependency for status queries; F2+ J3 enables ticket creation (controlled writes). | Assumed
E03 | epic | M | M — driven by Integration (M: CRM Totvs REST API + OAuth) + Intelligence/AI (M: Agentforce agent + executive briefing conversational design) + UI (M: mobile-first UX). Standard complexity, no special governance or high-volume scaling. | CRM Totvs REST API integration (~50 active users, ~30% of comercial), MuleSoft API exposure + OAuth 2.0, Agentforce conversational design for executive briefing (pipeline, contratos macro, forecast, last interactions), mobile-first UX (Slack mobile app — executive briefing on-demand during commute) | Agentforce developer (agent + prompt engineering), MuleSoft architect (API exposure + OAuth), integration developer (CRM Totvs API), Slack admin, UX designer (mobile-first conversational flow) | CRM Totvs API compatibility unknown (Gap G0302) — validate API equivalence to Salesforce Sales Cloud pattern (field mapping + data model) with TI before F1 build. CRM Totvs adoption low (~30% of comercial) — executive briefing may surface stale data if CRM not maintained; flag hygiene as adoption dependency. | Agentforce agent (J5 Intelligence Executiva Mobile) orchestrates conversational executive briefing in Slack mobile app → MuleSoft Anypoint API exposes CRM Totvs read-only REST APIs → agent returns pipeline, contratos macro, forecast, last interactions as Slack message cards. Mobile-first UX (Slack mobile app) — executive asks during commute, arrives pautado. | Assumed
E04 | epic | L | L — driven by Intelligence/AI (L: RAG over SharePoint + Slack AI, custom grounding strategy via MCP Real-time Search API, KB corpus indexing) + Integration (M: SharePoint content extraction + indexing). Data model + automation modest. | RAG (Retrieval-Augmented Generation) corpus indexing over Portal Conexão/SharePoint normativas + Slack AI channel recaps, MCP Real-time Search API federation (Slack conversations + files + Canvases), Agentforce conversational design for KB queries (políticas RH, alçadas R$ 2M, compliance), compliance-sensitive content (TCU audit exposure risk if incorrect alçada surfaced), one-time normativas migration + delta sync | Agentforce developer (agent + prompt engineering + RAG grounding strategy), MuleSoft architect (SharePoint API + content indexing), Salesforce Knowledge admin (data model + article lifecycle), Slack admin (Slack AI + MCP federation config), integration developer (SharePoint API) | SharePoint portal Conexão API compatibility unknown (Gap G0402) — validate content extraction method + indexing strategy with TI before F1 build. RAG corpus quality dependent on SharePoint content structure — if normativas are unstructured or poorly tagged, KB search quality degrades. Slack AI + MCP Real-time Search API new technology — limited production precedent, may require iterative tuning F1 pilot. | Agentforce agent (J7 KB Normativas) indexes Portal Conexão/SharePoint normativas + Slack AI channel recaps into RAG corpus via MCP Real-time Search API federation → employee asks *"Quem assina contratos acima de R$ 2M?"* → agent queries RAG corpus (KB article + Slack channel history) → returns exact alçada policy with source citation (KB article + line). Eliminates acionamentos repetitivos (-50% target F1), reduces TCU risk (correct alçada always surfaced). One-time normativas migration from SharePoint to Salesforce Knowledge + delta sync for updates. | Assumed
E05 | epic | S | S — driven by Intelligence/AI (M: natural language parsing for scheduling commands) balanced by low Integration (S: standard MS Graph API), low Automation (S), low Security (S). Simplest epic in F1. | Agentforce natural language parsing (voice/text command → attendees + date/time + subject extraction), MS Teams Graph API integration (calendar write), Salesforce Flow orchestration (Slack → Agentforce → Flow → MS Graph API) | Agentforce developer (agent + prompt engineering for NLP scheduling), Salesforce admin (Flow builder), integration developer (MS Graph API connector) | MS Teams Graph API rate limits unknown — validate with TI for capacity planning (how many scheduling commands/day expected?). Voice command accuracy dependent on Slack voice-to-text quality — may require iterative tuning F1 pilot if accents/background noise degrade transcription. | Agentforce agent (J8 Agendamento Automatizado) accepts voice/text scheduling commands in Slack → parses natural language (attendees + date/time + subject) → Salesforce Flow triggers MS Teams Graph API (calendar write) → agent confirms meeting created + sends invites. Eliminates "não esquece, não esquece" cognitive friction. | Confirmed
E06 | epic | L | L — driven by Intelligence/AI (L: conversational CRM updates with field mapping + transactional integrity) + Integration (L: CRM Totvs write APIs + field mapping validation) + Analytics (M: adoption monitoring KPIs). F2 controlled writes higher risk than F1 read-only. | CRM Totvs write API integration (F2 controlled writes — higher risk than F1 read-only), field mapping + transactional integrity validation (Agentforce conversational input → CRM Totvs fields), adoption monitoring (KPI tracking: uso semanal %, pipeline hygiene, forecast accuracy), conversational design for voice/text CRM updates, LGPD/TCU audit trail (every write logged) | Agentforce developer (agent + prompt engineering + field mapping logic), MuleSoft architect (write API exposure + field mapping + transactional integrity), integration developer (CRM Totvs write API), Salesforce admin (adoption monitoring dashboard), Slack admin | CRM Totvs write API compatibility unknown (Gap G0605) — validate field mapping + transactional integrity mechanism with TI before F2 build. Adoption measurement dependent on CRM Totvs activity logs — if logs don't capture Slack-originated writes distinctly, hygiene KPIs may be inaccurate. F2 controlled writes risk: incorrect field mapping or failed transaction → stale CRM data → forecast inaccuracy (same problem being solved). Requires robust retry logic + error handling. | Agentforce agent (J4 Adoção CRM Conversacional) accepts voice/text CRM updates in Slack (F2) → validates field mapping + transactional integrity → MuleSoft Anypoint API writes CRM Totvs via REST → agent confirms update + logs transaction. Adoption monitoring dashboard (Salesforce CRM Analytics or standard reports) tracks KPIs: uso semanal %, pipeline hygiene (staleness, completeness), forecast accuracy. Target: +40% adoption F2 via conversational interface elimination of login + form friction. | Assumed
E07 | epic | M | M — driven by Integration (M: Pronto write API + required-fields validation) + Intelligence/AI (M: conversational ticket creation with NLP extraction) + Automation (M: hybrid orchestration). Standard F2 controlled-write complexity. | Pronto (ServiceNow) write API integration (F2 controlled writes — case creation), required-fields validation (Agentforce conversational input → Pronto required fields: subject, priority, description, category), conversational design for voice/text ticket creation, LGPD/TCU audit trail (every write logged), incident workflow orchestration (Pronto ticket triggers internal routing/assignment rules) | Agentforce developer (agent + prompt engineering + NLP extraction for ticket fields), MuleSoft architect (write API exposure + required-fields validation), integration developer (ServiceNow Pronto write API), Slack admin | Pronto (ServiceNow) write API compatibility unknown (Gap G0701) — validate authentication model + required fields + category taxonomy with TI before F2 build. Volumetria unknown (Gap G0701) — ticket creation volume/day needed for MuleSoft capacity planning. F2 controlled writes risk: incomplete ticket data (missing required fields) → ticket creation fails → user frustration. Requires robust validation + retry logic. | Agentforce agent (J3 Abertura Chamados Assistida) accepts voice/text ticket creation in Slack (F2) → parses natural language (subject + priority + description) → validates required fields → MuleSoft Anypoint API writes Pronto (ServiceNow) case via REST → agent returns ticket number + SLA. Reduces friction ofício/reunião → faster incident reporting → lower MTTR. | Assumed
E08 | epic | XL | XL — driven by Integration (XL: Clarity API unknown + dual-system architecture if Service Cloud migration) + Data Volume/Migration (XL: 4.5k active + 10k+ historical demands Day-0 migration if Service Cloud chosen) + Data Model (L: complex Service Cloud Case + custom objects if migration). Hard-to-reverse decision (Gap G0801) — co-living vs. Service Cloud migration deferred to F2 architecture gate. Highest complexity epic in scope. | Clarity (Broadcom) API compatibility unknown (Gap G0801 — no KB coverage), co-living vs. Service Cloud migration decision (hard-to-reverse, one-way door), IF Service Cloud migration: 4.5k active + 10k+ historical demands Day-0 migration (Clarity → Service Cloud Case), dual-system orchestration (write Service Cloud, read Clarity archive for historical lookup), data quality unknown (Clarity source), complex data model (Case + custom objects for Clarity-specific metadata). Recommendation: defer to F2 architecture gate after F1 adoption + Clarity API validation. | Salesforce architect (Service Cloud data model + migration strategy decision), MuleSoft architect (Clarity API + dual-system orchestration if migration), integration developer (Clarity API), data migration specialist (ETL + data quality + Day-0 migration), Agentforce developer (agent + prompt engineering), Slack admin | Clarity API compatibility unknown (Gap G0801) — blocking risk for F2 build; F1 Phase 0 API discovery sprint required (2 weeks, TI provides Swagger/OpenAPI specs + sandbox credentials). Co-living vs. Service Cloud migration decision (Gap G0801) — hard-to-reverse (one-way door); if wrong choice, rollback to Clarity operationally infeasible (reverse data migration + process retraining). Recommendation: defer to F2 gate after F1 adoption validated. Data quality unknown — if Clarity data is incomplete/stale, migration to Service Cloud may surface hidden gaps. F1 pre-kick-off data audit required (sample 20 Clarity demands → validate completeness, accuracy). | F1 read-only: Agentforce agent (J6 Gestão Demandas Evolutivas) queries Clarity via MuleSoft read-only API → returns demand count, status, priorities. F2 architecture decision gate: (A) Co-living — Agentforce writes Clarity via MuleSoft write API, Clarity remains system of origin. (B) Service Cloud migration — 4.5k active + historical demands migrate to Service Cloud Case object, Clarity becomes read-only archive, Agentforce writes Service Cloud. Recommendation: defer to F2 gate after F1 adoption + Clarity API validation (3 months F1 production). | Unknown
E09 | epic | XL | XL — driven by Intelligence/AI (XL: dual-topic predictive agents + Data Cloud segmentation + Einstein Discovery models) + Analytics (XL: multi-source predictive segmentation) + Data Model (L: unified Contact/Case/Opportunity model) + Automation (L: streaming CDC orchestration). Most complex AI/analytics epic in scope. | Data Cloud streaming architecture (Pronto ticket events + CRM Totvs opportunity events → CDC ingestion), unified data model (Contact + Case/Ticket + Opportunity/Demand across 3 systems), predictive segmentation (high-risk SLA breach cohort via Einstein Discovery, churn-risk cohort via historical pipeline patterns), dual-topic Agentforce agents (J9 SLA breach alerts + J10 pipeline recommendations) with proactive activation (push alerts to Slack channels/DMs), Data Cloud first-time deployment (no prior Data Cloud in Dataprev), historical data load (6-12 months Pronto + CRM Totvs for baseline) | Data Cloud architect (streaming ingestion + unified data model + segmentation), Einstein Analytics developer (Einstein Discovery models for SLA breach + churn prediction), Agentforce developer (dual-topic agents + proactive alert orchestration), MuleSoft architect (CDC streaming from Pronto + CRM Totvs), Salesforce admin (Data Cloud config), integration developer (Pronto + CRM Totvs streaming APIs) | Data Cloud streaming architecture unknown (Gap assumption) — validate Pronto (ServiceNow) + CRM Totvs streaming API availability + CDC pattern compatibility with TI before F3 build. Data quality dependency — if Pronto tickets or CRM Totvs opportunities are incomplete/stale, predictive models degrade (GIGO: garbage in, garbage out). Historical data load size unknown — if >500k records, performance/cost implications for Data Cloud ingestion. Einstein Discovery model accuracy unknown — requires F3 pilot tuning (model training + eval loops). Data Cloud first-time deployment — limited Dataprev production precedent, may require vendor support engagement. | Data Cloud ingests streaming events from Pronto (ServiceNow) ticket lifecycle + CRM Totvs opportunity lifecycle → unified Contact (B2B client + internal employee) + Case/Ticket + Opportunity/Demand profiles → Einstein Discovery models predict high-risk SLA breach cohort (J9) + churn-risk cohort (J10) → Agentforce agents activate proactive alerts/recommendations in Slack ("Alerta: Ticket X risco SLA breach em 2h" / "Oportunidade Y sem atividade 30 dias — agendar call?"). Historical data load (6-12 months) for baseline segmentation. F3 phased activation after F1/F2 adoption validated. | Assumed
E10 | epic | XL | XL — driven by Sharing/Security (XL: Protheus governance blocker, Slack EKM, LGPD/TCU 5-year audit trail, alçadas approval) + Automation (L: 7-system audit trail orchestration + EKM + Flow routing) + Integration (L: MuleSoft audit trail + EKM). Experience Design workstream (6 gaps: G0104, G0402, G0505, G0605, G0704, G0207) + Governance/CoE workstream (5 gaps: G0407, G0607, G9901, G1001, G1003) add breadth. | Protheus governance model (TI+Jurídico+DPO tri-party meeting — Gap G1002 blocker), Slack EKM deployment (AWS KMS master keys under CISO control for instant revocation), 7-system audit trail orchestration (Protheus + Pronto + CRM Totvs + Clarity + Conexão + Teams + SEI — every API call logged: user ID + timestamp + query/mutation + response status), LGPD/TCU compliance (5-year audit log retention), alçadas approval workflow (R$ 2M threshold → Slack button routing to authorized approver), multi-persona CM (B2B clientes, executivos, comercial, N1/N2 — training matrix by persona, adoption KPIs, executive mandate Saulo), Experience Design workstream (UX research F1 pilot with 20-50 users, service design, accessibility WCAG 2.1 AA), Governance/CoE workstream (RACI by system, data stewardship, CoE charter, decision rights) | Salesforce security architect (Protheus governance model + audit trail + EKM + alçadas approval workflow), MuleSoft architect (7-system audit trail orchestration), Slack admin (Enterprise Grid + EKM config), Salesforce admin (audit log custom object + adoption monitoring dashboard + Flow alçadas routing), CM lead (training matrix by persona + adoption KPIs + executive mandate orchestration), UX researcher (Experience Design workstream — F1 pilot usability testing with 20-50 users), service designer (conversational flow design + Slack Canvas UX), accessibility specialist (WCAG 2.1 AA audit), CoE lead (RACI by system + data stewardship + CoE charter) | Protheus governance blocker (Gap G1002) — TI+Jurídico+DPO tri-party meeting must complete before F1 kick-off; escalate to seller immediately. Experience Design gap (6 gaps) — no UX research/service design/content strategy scoped; risk of low adoption, high support burden, accessibility non-compliance (10k+ external users). Governance/CoE gap (5 gaps) — multi-team ownership RACI undefined (Agentforce config, MuleSoft APIs, Slack admin), data stewardship (CRM Totvs vs. Salesforce truth?), CoE structure, CM execution plan. CM execution risk — 10k+ users onboarding without structured training → low adoption → F1/F2/F3 ROI failure. Slack EKM new technology — limited production precedent, may require vendor support engagement. | MuleSoft audit trail: every API call (Protheus + Pronto + CRM Totvs + Clarity + Conexão + Teams) logged to Salesforce custom object (user ID + timestamp + query/mutation + response status) — 5-year retention for LGPD/TCU compliance. Protheus governance: TI+Jurídico+DPO tri-party meeting defines perfil de acesso per user before F1 kick-off (Gap G1002 blocker). Slack EKM: AWS KMS master keys under Dataprev CISO control — instant revocation capability (motivated by prior 2.8M CPF breach). Alçadas approval workflow: KB Normativas (J7) surfaces alçadas R$ 2M → Salesforce Flow routes to authorized approver via Slack button → logs approval. Multi-persona CM: training matrix (B2B clientes, executivos, comercial, N1/N2), early adopters (20-50 pilot users F1), executive mandate (Saulo enforces adoption KPIs >60% uso semanal F2). Experience Design workstream: UX researcher + service designer embedded F1 (J1/J2 usability testing with pilot) → iterate conversational flows + Slack Canvas UX F1 → scale F2/F3. Governance/CoE workstream: RACI by system (Protheus → TI owner, CRM Totvs → Comercial owner, Agentforce → PS delivery team owner F1, handoff to CoE F2), CoE charter (roles, decision rights, change approval process), data stewardship (CRM Totvs vs. Salesforce truth decision). | Assumed

## Roadmap Phases
Phase Number | Phase Name | Duration (Weeks) | Duration Source | Objectives | Epics Included | Success Criteria | Dependencies | Risks
0 | Discovery & Architecture Refinement (F0) |  |  | Resolver G1002 blocker (Protheus governance TI+Jurídico+DPO tri-party meeting), volumetrias audit (G0102 Protheus, G0201 Pronto, G0302 CRM Totvs, G0701 Abertura Chamados), decidir G0101 (Workspace Slack segregation B2B vs internos), validar Clarity API (G0801 co-living vs Service Cloud migration strategy) |  | G1002 approved (Protheus acesso TI+Jurídico+DPO), volumetrias collected (capacity planning unblocked), Workspace Slack decision locked, Clarity API validated | None — blocker for F1 start | Se TI+Jurídico+DPO não aprovar Protheus acesso, F1 inviável — escalate to seller immediately. Fallback: defer J1 to F2, launch F1 with J2/J5/J7/J8 only.
1 | Foundation (F1 Quick Wins) |  |  | Deploy Slack+Agentforce J1/J2/J5/J7/J8 read-only, MuleSoft System APIs (Protheus/Pronto/CRM Totvs/Conexão/SharePoint), Slack EKM (AWS KMS master keys under CISO control), rastreabilidade LGPD/TCU (7-system audit trail), early adopters 20-50 piloto onboarded, executive mandate (Saulo >60% uso semanal) | E01,E02,E03,E04,E05,E10 | 5 jornadas live read-only (J1 Consultas Financeiras, J2 Autoatendimento Chamados, J5 Intelligence Executiva, J7 KB Normativas, J8 Agendamento MS Teams), early adopters trained, audit trail operational (every API call logged: user ID + timestamp + query/mutation + response status), Saulo executive mandate enforced | Phase 0 approved — G1002 Protheus governance blocker resolved | Experience Design gap (G0104/G0402/G0505) — 10k+ external users onboarding sem UX research → low adoption risk; Governance/CoE gap (G9901/G1001/G1003) — multi-team ownership (Agentforce config, MuleSoft APIs, Slack admin, CRM Totvs vs Salesforce truth) undefined; volumetrias unknown (G0102/G0201/G0302) — capacity planning MuleSoft/Agentforce/Heroku blocked without Phase 0 audit
2 | Expansion (F2 Controlled Writes) |  |  | Enable J3 (Abertura Chamados Assistida Pronto case creation) + J4 (Adoção CRM Conversacional pipeline/forecast updates), MuleSoft write APIs (Pronto ServiceNow, CRM Totvs), field mapping + transactional integrity validation, adoption monitoring dashboard (hygiene KPIs: uso semanal %, pipeline completeness, forecast accuracy) | E06,E07,E10 | +40% CRM adoption (baseline 30% → target 70% final adoption), ticket creation via Slack operational (J3 Pronto case creation validated), hygiene monitoring live (CRM Totvs data quality dashboard), F1 adoption trust established (>60% uso semanal Phase 1) | Phase 1 adoption >60% uso semanal — trust established before F2 writes enabled | CRM Totvs write API compatibility unknown (G0601 blocker — validate field mapping + transactional integrity with TI before F2 build), Pronto write API authentication model (G0701 — ServiceNow case creation API validate with TI), F2 controlled writes risk — incorrect field mapping or failed transaction → stale CRM data → forecast inaccuracy (same problem being solved); requires robust retry logic + error handling
3 | Proactive Intelligence (F3) |  |  | Data Cloud streaming architecture (Pronto ticket events + CRM Totvs opportunity events CDC ingestion), unified data model (Contact B2B client + internal employee, Case/Ticket history Pronto, Opportunity/Demand history CRM Totvs), J9 (SLA breach alerts proativos N2/manager before breach) + J10 (pipeline recommendations churn-risk cohort next best action), Agentforce proactive activation (push alerts Slack channels/DMs), E08 Clarity migration decision gate (co-living vs Service Cloud replacement) | E08,E09,E10 | SLA breach alerts operational (J9 high-risk cohort identified → Agentforce alerts N2/manager proactively before breach), pipeline recommendations live (J10 churn-risk cohort → next best action suggestions to comercial), Clarity decision locked (co-living: Agentforce writes Clarity via MuleSoft; OR Service Cloud migration: 4.5k active demands migrate to Service Cloud Case, Clarity becomes read-only archive), Data Cloud streaming validated (Pronto + CRM Totvs events ingested, unified profiles operational) | Phase 2 CRM adoption validated (data quality baseline — if CRM Totvs adoption stays 30%, stale data risk for predictive models), E08 architecture decision gate (co-living vs Service Cloud — hard-to-reverse, defer to F2 gate after F1 adoption validated 3 months production) | Data Cloud streaming architecture unknown (G0901 assumption — validate Pronto ServiceNow + CRM Totvs streaming API availability + CDC pattern compatibility with TI before F3 build), Clarity API compatibility unknown (G0801 blocker — no KB coverage for Broadcom Clarity; F1 Phase 0 API discovery sprint required 2 weeks TI provides Swagger/OpenAPI specs + sandbox credentials), data quality dependency — if Pronto tickets or CRM Totvs opportunities incomplete/stale, predictive models degrade (GIGO: garbage in, garbage out); historical data load size unknown (if >500k records, performance/cost implications Data Cloud ingestion); Einstein Discovery model accuracy unknown — requires F3 pilot tuning (model training + eval loops); Data Cloud first-time deployment — limited Dataprev production precedent, may require vendor support engagement

## Roles & Skills
Role ID | Discipline | Phases Active | Rationale | Comments | Suggested Count (opt-in) | Count Source | Multi-disciplinary Note
R01 | Senior Technical Architect | 0,1,2,3 | Architecture decisions (Workspace Slack segregation, Clarity migration strategy, MuleSoft vs MCP dual deployment), E08/E09 XL complexity oversight, cross-phase dependency management, NFR validation (LGPD/TCU compliance, Slack EKM, audit trail design). Security (E01 Protheus governance TI+Jurídico+DPO perfil de acesso per user, Slack EKM deployment AWS KMS under CISO control, LGPD/TCU audit trail 7-system API call logging 5-year retention, alçadas approval workflow E04 R$ 2M threshold Salesforce Flow routing). Governance/CoE (RACI by system Agentforce config/MuleSoft APIs/Slack admin/CRM Totvs vs Salesforce truth, data stewardship E06 CRM data quality owner after Slack updates, CoE charter roles/decision rights/change approval process, Agentforce prompt governance who approves new use cases/maintains prompt library, MuleSoft API governance Anypoint Exchange catalog/API policies publication approval).
R02 | Agentforce Technical Consultant | 1,2,3 | 9 agents across F1/F2/F3 (J1-J10): prompt engineering + NLP intent parsing (E01 Consultas Financeiras, E02 Autoatendimento Chamados, E03 Intelligence Executiva, E04 KB Normativas, E05 Agendamento MS Teams F1 read-only; E06 Adoção CRM, E07 Abertura Chamados F2 controlled writes; E09 Intelligence Preditiva J9 SLA breach alerts + J10 pipeline recommendations F3 proactive). RAG grounding (E04 KB Normativas — Portal Conexão/SharePoint normativas + Slack AI channel recaps via MCP Real-time Search API federation). Conversational design for voice/text input (NLP extraction ticket fields E07, CRM field updates E06, scheduling commands E05).
R03 | MuleSoft Technical Architect | 0,1,2,3 | 7-system API exposure (Protheus ERP, Pronto ServiceNow, CRM Totvs, Clarity Broadcom, Portal Conexão SharePoint, MS Teams Graph API, SEI future), System API design (F1 read-only REST APIs, F2 controlled writes with field mapping + transactional integrity validation), API governance model (rate limiting, OAuth 2.0 client credentials, audit logging LGPD/TCU every API call user ID + timestamp + query/mutation + response status), perfil de acesso middleware (E01 Protheus TI+Jurídico+DPO governance model per-user authorization), dual-system orchestration (E08 Clarity co-living vs Service Cloud migration IF chosen — write Service Cloud, read Clarity archive for historical lookup).
R04 | MuleSoft Technical Consultant | 1,2,3 | API connectivity implementation (Protheus ERP REST APIs financial queries, Pronto ServiceNow ticket status + case creation, CRM Totvs pipeline briefing + updates, Clarity Broadcom demand queries, SharePoint Conexão content extraction + indexing for RAG corpus, MS Teams Graph API calendar write). Phase 0 API discovery spike (Clarity REST API validation compatibility unknown G0801 — TI provides Swagger/OpenAPI specs + sandbox credentials, volumetrias audit G0102/G0201/G0302/G0701 capacity planning MuleSoft API calls/month). Dual-system orchestration (E08 Clarity co-living: MuleSoft write Clarity via REST API IF co-living chosen; OR Service Cloud migration: MuleSoft read Clarity archive only).
R05 | Data Cloud Technical Architect | 3 | F3 Proactive: Data Cloud streaming architecture (Pronto ServiceNow ticket events + CRM Totvs opportunity events CDC ingestion — event-driven pattern Change Data Capture or equivalent streaming APIs), unified data model (Contact B2B client + internal employee, Case/Ticket history from Pronto with 4+ related objects, Opportunity/Demand history from CRM Totvs — complex multi-source unified model), predictive segmentation (high-risk SLA breach cohort E09 J9 via Einstein Discovery, churn-risk cohort E09 J10 via historical pipeline patterns), historical data load (6-12 months Pronto tickets + CRM Totvs opportunities for baseline segmentation — moderate volume tens of thousands records, not Day-0 blocker F3 phased activation).
R06 | Solution Architect | 1,2,3 | Service Cloud (E08 Clarity migration IF Service Cloud chosen F2 architecture gate: Case object data model design custom objects for Clarity-specific fields projeto/evolutionary demand metadata, 4.5k active demands + historical archive Day-0 migration Clarity → Service Cloud, dual-system orchestration write Service Cloud read Clarity archive for historical lookup, adoption monitoring dashboard E06 CRM Totvs hygiene KPIs uso semanal % pipeline hygiene staleness/completeness forecast accuracy, audit log custom object E10 LGPD/TCU 5-year retention every MuleSoft API call logged). Slack (Enterprise Grid config Workspace segregation decision from Phase 0 G0101 — single workspace c/ DLP control or 2 workspaces isolated, Slack Connect B2B setup 2.5k external orgs email verified IdP or Slack Guest Accounts, Slack EKM config AWS KMS master keys under Dataprev CISO control instant revocation capability, Slack AI + MCP Real-time Search API federation E04 KB Normativas index Portal Conexão/SharePoint + Slack channel recaps, Slack Workflow Builder orchestration E05 MS Teams Graph API calendar write + E10 alçadas approval buttons R$ 2M threshold routing).
R07 | Change Management Lead | 0,1,2,3 | Multi-persona CM (B2B clientes J1 Consultas Financeiras, executivos J5 Intelligence Executiva, comercial J4/J6 CRM + demandas, N1/N2 J2/J3 chamados): training matrix by persona formal sessions F1, early adopters 20-50 pilot users F1 → scale F2/F3, executive mandate orchestration (Saulo executive sponsor enforces adoption KPIs >60% uso semanal target F2), adoption monitoring dashboard (Salesforce CRM Analytics or standard reports — KPIs uso semanal % agent adoption by persona API call volume/error rate audit log compliance metrics), Experience Design workstream coordination (UX researcher + service designer embedded F1 J1/J2 usability testing with pilot 20-50 users → iterate conversational flows + Slack Canvas UX F1 → scale F2/F3 — Gap G0104/G0402/G0505/G0605/G0704/G0207 discipline gap per instructions).
R08 | UX Researcher / Service Designer | 0,1,2 | Experience Design workstream (Gap G0104/G0402/G0505/G0605/G0704/G0207 — no UX research/service design/content strategy scoped for 10k+ external user onboarding per discipline gap instructions): Phase 0 UX research (clientes B2B ~10k licenças Slack baseline never used Slack — validate channel preference vs email/portal/phone, persona journey maps which personas per J3/J6/J9/J10), F1 pilot usability testing (J1 Consultas Financeiras + J2 Autoatendimento Chamados conversational flows with 20-50 early adopters — iterate dialogue trees + error states + escalation paths), service design (conversational flow design Slack Canvas UX help content tutorial flows — 'atrito cognitivo' elimination E05 claim requires good UX), content strategy (help content library Trailhead modules video library for multi-persona training), accessibility audit (WCAG 2.1 AA — 10k+ external users public-sector compliance requirement).
R09 | Einstein Analytics Developer | 3 | F3 Proactive: Einstein Discovery models (SLA breach prediction E09 J9 regression for high-risk SLA breach cohort, opportunity scoring for pipeline churn prediction E09 J10 churn-risk cohort), model training (training data volume unknown — if ML-based requires data scientist + training dataset preparation + model validation + retraining cadence AI/ML workstream not scoped in epic brief; if rule-based only simpler — clarify so effort not under-estimated), model eval loops F3 pilot tuning (model accuracy validation iterative), Data Cloud segmentation activation (Agentforce reads calculated insights pushes Slack messages proactively — Proactive Agentforce pattern high-risk cohorts alert N2/manager J9, next best action suggest comercial J10).
R10 | Solution Consultant | 0,1,2,3 | Phase 0 gap resolution facilitation (G1002 TI+Jurídico+DPO tri-party meeting scheduling — Protheus governance blocker escalate to seller immediately before proposal submission, volumetrias audit coordination with TI — G0102 Protheus quantas consultas financeiras/mês esperadas quantos clientes B2B ativos baseline, G0201 Pronto 30k tickets/mês total quantos usuários finais consultam status via Slack quantas queries/usuário/dia, G0302 CRM Totvs 50 usuários ativos baseline quem são os executivos target headcount/perfis, G0701 Abertura Chamados volume metrics chamados created monthly/annually target response time baseline resolution SLA per priority), requirements clarification (68 gaps cross-checking with Dataprev stakeholders — Source Conflicts G0101 Workspace Slack segregation, Missing Requirements Experience Design gap G0104/G0402/G0505, Governance/CoE gap G0407/G0607/G9901/G1001/G1003), UAT coordination (F1 early adopters 20-50 pilot users → F2/F3 scale — acceptance criteria validation per phase), baseline metric collection (NPS/CSAT pre-F1 coletar antes para comparação pós-implantação, 30-day active users CRM Totvs adoption baseline 30% → +40% target F2 = 70% final), RACI by system facilitation (Protheus → TI owner, CRM Totvs → Comercial owner, Agentforce → PS delivery team owner F1 handoff to CoE F2 — Gap G0407/G0607/G1001/G1003 multi-team ownership decision rights).
R11 | Quality Assurance Consultant | 1,2,3 | F1 read-only API integration testing (Protheus ERP financial queries, Pronto ServiceNow ticket status, CRM Totvs pipeline briefing, Clarity Broadcom demand queries, SharePoint Conexão content extraction, MS Teams Graph API calendar write, SEI future — 7 systems total), F2 controlled writes validation (field mapping correctness Agentforce conversational input → Pronto required fields subject/priority/description/category + CRM Totvs pipeline/forecast/oportunidades, transactional integrity validation MuleSoft write API + error handling robust retry logic), F3 Data Cloud streaming + predictive model accuracy validation (Pronto ticket events + CRM Totvs opportunity events CDC ingestion validated, unified Contact/Case/Opportunity profiles operational, Einstein Discovery model SLA breach prediction + pipeline churn prediction accuracy F3 pilot eval loops), LGPD/TCU audit trail verification (every MuleSoft API call logged correctly — user ID + timestamp + query/mutation + response status → Salesforce custom object 5-year retention, Slack EKM AWS KMS instant revocation capability tested), Agentforce conversational flow testing (voice/text NLP accuracy — E05 scheduling commands participant resolution, E06 CRM field updates validation, E07 ticket creation required-fields validation; error handling — conflict detection E05 double-booked, disambiguation logic E07 ambiguous ticket priority; escalation paths — when Agentforce cannot resolve query E04 KB escalate to time Pessoas).

## Efficiency
Section | Name | Task-Level Band | Realized Band | Driving / Amplified | Human-Only / Evidence | Sources | Narrative
Headline | Blended project-level | ~30-40% | ~12-18% |  | Assumed | [1]; [2]; [3]; [5] | Task-level ~30-40% × realization factor 0.40-0.45 = ~12-18% project-level. Mid readiness scenario (score 2/8) keeps this band; Low/High scenarios adjust.
Realization Factor | 0.40-0.45 |  |  | Mixed configuration (read-only APIs F1) + custom dev (Agentforce + Data Cloud F2/F3); Established enterprise client with existing Salesforce footprint (not greenfield); 7 legacy system integrations (MuleSoft/MCP) — moderate integration burden; Regulated context (LGPD/TCU) — review/approval overhead modestly reduces realized gains |  |  | Multi-cloud mixed config + custom dev (7 legacy integrations + Agentforce + Data Cloud) at established enterprise client. Standard gov realization per benchmarks.md.
Readiness Signal | AI tooling posture |  |  | score 0/2 | No AI tooling adoption signals in discovery (no mention of GitHub Copilot, Claude, Cursor, or similar developer tools). Huawei partnership (fev/2026) is pilot-phase research, not delivery tooling. [Discovery: Huawei IA partnership pilot, not production tooling for implementation team]
Readiness Signal | Delivery velocity / speed bias |  |  | score 1/2 | Competing pressures: mainframe sunset (jan/2026) + data breach (mai/2026) motivate urgency, BUT 68 gaps (many Unknowns) + Protheus governance blocker (G1002) unresolved + conservative federal-gov bureaucracy slow decision cycles. Mid velocity assumed. [Discovery: mainframe sunset urgency, breach pressure vs. 68 gaps + governance blocker unresolved]
Readiness Signal | Data & environment hygiene |  |  | score 1/2 | Mixed signals: 7 legacy systems fragmented (Pronto, Clarity, Protheus, CRM Totvs, Conexão, Teams, SEI) with no unified data model today (hygiene risk), BUT volumetrias unknown (G0102/G0201/G0302/G0701) — capacity planning blocked. Mid hygiene assumed. [Discovery: 7 fragmented systems + volumetrias gaps]
Readiness Signal | Legal / security / compliance posture |  |  | score 0/2 | Active blockers: Protheus governance blocker G1002 (TI+Jurídico+DPO tri-party approval pending), LGPD breach incident (2.8M CPFs mai/2026), TCU audit scrutiny. Compliance-heavy slows AI adoption (every model output needs human review for audit trail). [Discovery: G1002 blocker, LGPD breach mai/2026, TCU audit pressure]
Readiness Scenario | (current) Low readiness |  | ~10-14% | score range 0-2 | Approve GitHub Copilot/Claude for PS delivery team (currently no AI tooling in use); Resolve Protheus governance blocker G1002 pre-kick-off (TI+Jurídico+DPO tri-party meeting); Define LGPD/TCU-compliant AI-assisted delivery policy (what level of human review required for model-generated code/config/docs) |  | Current state per discovery signals. Gains stay modest until AI tooling approved for delivery team, Protheus governance blocker resolved (G1002), and compliance review process streamlined (LGPD/TCU manual audit trail for every AI output suppresses velocity).
Readiness Scenario | Mid readiness |  | ~12-18% | score range 3-5 | Volumetrias audit complete (G0102/G0201/G0302/G0701) — data hygiene baseline established before F1; Data model reconciliation plan across 7 legacy systems (Contact B2B + employee unification, Case/Ticket Pronto history, Opportunity/Demand CRM Totvs) — reduces integration rework |  | Tooling unlocked, governance blocker resolved, compliance policy defined. Delivery team captures standard multi-cloud gains — config/doc acceleration + API connector generation + test data synthesis.
Readiness Scenario | High readiness |  | ~18-22% | score range 6-8 |  |  | Conditions favor upper end: tooling + governance unblocked + data hygiene baseline + unified data model plan. Faster client with clean data captures more of the AI upside.
Category | Technical Engineering & QA | ~25-35% | ~10-16% | Create Code (realistic enterprise / legacy); Analyze Code & Fix Defects; Generate Test Data ¦ epics: E01, E02, E03, E06, E07, E08 |  | [1]; [3]; [5] | MuleSoft API connector generation (7 System APIs E01/E02/E03/E06/E07 + E08 Clarity unknown API) + Agentforce agent scaffolding (E06/E07 F2 writes) + test data synthesis (7-system integration testing E10). AI accelerates API mapping + boilerplate connectors [3], but legacy system API discovery/validation + Clarity API unknown (G0801) remain human-only. Multi-system integration testing (Pronto + CRM Totvs + Protheus + Clarity + Conexão + Teams + SEI) stays complex — AI generates synthetic test data but orchestration + regression testing review is human-led [5]. Cap: regulated context (LGPD/TCU audit trail) requires human review every API call logging implementation + Protheus perfil de acesso enforcement logic.
Category | Analysis & Design | ~35-45% | ~14-20% | Requirement Analysis; System Design; Process Analysis ¦ epics: E04, E06, E08, E09, E10 |  | [2]; [6] | Agentforce conversational intent design (E06/E07 J4/J3 — field mapping from voice/text to API required fields) + Data Cloud unified data model (E09 — Contact B2B/employee reconciliation, Case/Ticket Pronto 4+ related objects, Opportunity/Demand CRM Totvs) + RAG corpus indexing strategy (E04 Portal Conexão normativas + Slack AI channel recaps). AI drafts intent skeletons + data model mappings [2], but 68 gaps (many Unknowns/Assumed) + 7-system fragmentation force iteration. Experience Design gap (G0104/G0402/G0505 — 10k+ external users onboarding, no UX research scoped) caps conversational flow design quality without pilot feedback. Governance gap (G9901/G1001/G1003 — multi-team ownership RACI, data stewardship, Agentforce prompt governance) remains human-negotiation-heavy [6].
Category | Documentation & Knowledge Management | ~35-50% | ~14-23% | Draft Documentation; Summarize Decisions ¦ epics: E04, E10 |  | [2]; [7] | RAG corpus curation (E04 — Portal Conexão normativas indexing + Slack AI channel recaps federation) + training materials by persona (E10 — B2B clients J1, executivos J5, comercial J4/J6, N1/N2 J2/J3, Pessoas J7) + compliance audit trail docs (LGPD/TCU rastreabilidade every API call + Protheus perfil de acesso governance). AI drafts training modules + normativa summaries + audit trail templates [2][7], but compliance-sensitive content (alçadas 2 milhões de reais, perfil de acesso governance model) requires Jurídico/DPO human review every iteration — regulatory conservatism caps velocity. TCU audit trail design (every API call logged with user ID + timestamp + query/mutation) benefits from AI-generated templates but final approval human-gated.
Category | Project Management & Operations | ~15-25% | ~6-11% | Status Reports; Project Pulse Reports ¦ epics: E10 |  | [2] | Change management execution (E10 — early adopters program 20-50 pilot users F1, executive mandate Saulo adoption KPIs >60% uso semanal F2, adoption monitoring dashboard CRM Analytics). AI drafts status summaries + adoption dashboards [2], but stakeholder alignment (Saulo executive sponsor + TI+Jurídico+DPO tri-party Protheus governance blocker G1002) + conflict resolution (multi-team ownership RACI G9901/G1001) stay human-only. Phase sequencing (F0 blocker resolution → F1 → F2 adoption gate → F3) benefits modestly from AI risk flagging but dependency tracking (G1002 Protheus governance blocker mandatory before F1) is human-driven.
Role Type | Senior Technical Architect | ~30-40% | ~12-18% | API design (MuleSoft 7-system System APIs + Agentforce MCP federation); Security architecture (LGPD Art. 48 + TCU audit trail + Slack EKM); Integration patterns (API-led connectivity System + Process + Experience) | Protheus governance blocker resolution (G1002 — TI+Jurídico+DPO tri-party negotiation); Org strategy decision (single org vs multi-org — no regulatory isolation signal in discovery) | [1]; [3] | API design gains: AI drafts MuleSoft System API skeletons + Swagger/OpenAPI specs from legacy system discovery [3], but Clarity API unknown (G0801 — no KB coverage) + Protheus governance blocker (G1002 — perfil de acesso model TI+Jurídico+DPO approval) require human validation. Security architecture (LGPD/TCU audit trail every API call + Slack EKM AWS KMS instant revocation) AI-drafts baseline but compliance review human-gated. CoE governance (multi-team ownership RACI G9901/G1001/G1003) stays negotiation-heavy — AI summarizes options, people decide.
Role Type | Agentforce Technical Consultant | ~30-40% | ~12-18% | Conversational intent design (10 jornadas J1-J10 — voice/text field mapping); Agent scaffolding (Agentforce Atlas Reasoning Engine orchestration); Confidence tuning (F1 early adopters feedback iteration) | Experience Design gap (G0104/G0402/G0505 — 10k+ users onboarding, no UX research scoped); Agentforce prompt governance (G1001 — who owns prompt iteration? multi-team RACI) | [2]; [4] | Intent design acceleration: AI drafts conversational field mappings from API specs (Protheus financials, Pronto ticket creation, CRM Totvs pipeline updates) [2][4], but Experience Design gap (no usability testing with pilot users F1 J1/J2) caps flow quality without iteration feedback. Agentforce proactive activation (J9 SLA breach alerts + J10 pipeline recommendations F3) benefits from AI-generated segmentation logic drafts, but Data Cloud ingestion architecture (Pronto + CRM Totvs CDC validation) human-validated. 10 jornadas (5 read-only F1, 2 writes F2, 2 proactive F3 + 1 scheduling F1) — AI scaffolds agents faster but governance model (who approves prompt changes? G1001) unresolved slows iteration.
Role Type | MuleSoft Technical Architect | ~25-35% | ~10-16% | API-led connectivity pattern design (System + Process + Experience layers); Capacity planning (volumetrias audit + rate limiting design); Rastreabilidade LGPD/TCU (every API call logging architecture) | Volumetrias unknown (G0102/G0201/G0302/G0701 — capacity planning blocked until Phase 0 audit); Clarity API compatibility validation (G0801 — external dependency risk, no KB coverage) | [1]; [3] | API architecture gains: AI drafts System API layer specs + rastreabilidade logging patterns [1][3], but volumetrias unknown (4 gaps G0102/G0201/G0302/G0701) blocks capacity planning until Phase 0 audit — AI can't invent load profiles. Clarity API unknown (G0801 — Broadcom API undocumented or brittle) requires TI-provided Swagger/OpenAPI specs + sandbox credentials Phase 0 discovery sprint (2 weeks) before AI-assisted connector build viable. MuleSoft/MCP dual deployment (Anypoint for legacy APIs, MCP Server for Slack federation G9902) — AI drafts architecture decision doc but protocol choice human-validated per Salesforce best practices.
Role Type | Data Cloud Technical Architect | ~30-40% | ~12-18% | Unified data model design (Contact B2B/employee reconciliation, Case/Ticket/Opportunity history); Streaming architecture (Pronto ServiceNow + CRM Totvs CDC ingestion); Predictive segmentation (SLA breach cohort, churn-risk cohort) | Historical data load sizing decision (if >500k records, performance/cost implications — volumetrias unknown G0701); Einstein Discovery ML-based vs rule-based decisioning (business rule complexity unknown) | [2]; [5] | Data model gains: AI drafts Contact B2B + employee unification schema + Case/Ticket Pronto 4+ related objects reconciliation [2], but 7-system fragmentation (no unified model today) + volumetrias unknown (G0701) makes historical load sizing guesswork without Phase 0 audit. Data Cloud streaming architecture (Pronto + CRM Totvs CDC ingestion G0901) AI-drafts event-driven pattern but validation blocked until TI provides API specs + data model mappings. Predictive segmentation (J9 SLA breach alerts + J10 pipeline recommendations F3) — AI scaffolds Einstein Discovery models but business rule complexity (what defines churn-risk cohort?) human-defined. First-time Dataprev production Data Cloud deployment may require Salesforce vendor support F3 (limited precedent).
Role Type | Solution Architect | ~25-35% | ~10-16% | Service Cloud configuration + implementation; Slack Workspace architecture decision (G0101 — single vs dual workspace); Cross-cloud orchestration (Service Cloud + Agentforce + MuleSoft + Data Cloud) | Workspace Slack segregation decision (G0101 — B2B vs internos, Jurídico approval unknown); Clarity migration strategy (G0801 — co-living vs Service Cloud replacement, hard-to-reverse decision deferred F2) | [2] | Config gains: AI drafts Service Cloud Flow orchestration + Slack Canvas UX mockups (J1/J2/J5/J7/J8) [2], but Workspace Slack segregation (G0101 — single recommended, dual if Jurídico requires) unresolved blocks Slack admin setup. Clarity migration strategy (G0801 — co-living API writes vs. Service Cloud full replacement, 4.5k active demands migrate) hard-to-reverse decision deferred F2 architecture gate after F1 adoption validated — AI drafts both paths but choice human-gated. Slack Canvas UX design (conversational flow + help content) benefits from AI-generated mockups but Experience Design gap (G0104/G0402/G0505 — no usability testing scoped) caps quality without pilot feedback F1.
Role Type | Solution Consultant | ~30-40% | ~12-18% | Business analysis (20-phase-0-gap resolution, user stories per persona); Training materials by persona (B2B/executivos/N1-N2/Pessoas); Adoption monitoring dashboard setup (CRM Analytics uso semanal %) | RACI + CoE charter facilitation (G9901/G1001 — multi-team ownership decision rights, data stewardship); Executive mandate enforcement (Saulo adoption KPIs >60% uso semanal F2 — dashboard monitored weekly, non-adopters escalated) | [2]; [7] | BA gains: AI drafts user stories per persona + training module outlines [2][7], but 68 gaps (many Unknowns/Assumed) + governance gap (G9901/G1001/G1003 — multi-team ownership RACI unresolved) force iteration. Training materials (Trailhead modules + video library + Slack Canvas help content) AI-generated but persona-specific content (B2B clients J1, executivos J5, comercial J4/J6, N1/N2 J2/J3, Pessoas J7) requires CM Lead human validation per client culture. Adoption monitoring dashboard (CRM Analytics: uso semanal %, agent adoption by persona, API call volume/error rate, audit log compliance metrics) AI-drafts baseline but executive mandate (Saulo enforces >60% target F2) + non-adopter escalation workflow human-driven.
Role Type | Quality Assurance Consultant | ~30-45% | ~12-20% | Test data synthesis (7-system integration testing); Test case generation (unit testing MuleSoft API connectors + Agentforce intent parsing); Performance testing (F1 MuleSoft API rate limits + F3 Data Cloud streaming throughput) | Security testing (LGPD/TCU audit trail verification — every API call logged correctly); UAT per phase F1/F2/F3 scale validation (pilot users → early adopters → full scale) | [3]; [5] | Test generation gains: AI synthesizes test data for 7-system integration (Pronto, Clarity, Protheus, CRM Totvs, Conexão, Teams, SEI) + generates unit test cases for MuleSoft API connectors [3][5], but multi-system regression testing (F2/F3 scale — ensure F1 read-only jornadas remain operational when F2 writes enabled) stays human-orchestrated. Security testing (LGPD/TCU audit trail verification + Slack EKM instant revocation tested) human-led — compliance context requires Jurídico/DPO review every audit log validation. Performance testing (F1 MuleSoft API rate limits validated against volumetrias + F3 Data Cloud streaming throughput) blocked until volumetrias audit complete (G0102/G0201/G0302/G0701 Phase 0) — AI generates load test scripts but capacity targets human-defined post-audit.
Role Type | UX Researcher | ~20-30% | ~8-14% | Conversational flow iteration (Agentforce voice/text + Slack Canvas UX); Usability testing synthesis (J1/J2 pilot feedback 20-50 early adopters F1) | Service design for 10k+ external users onboarding (Experience Design gap G0104/G0402/G0505 — no UX research scoped initially); Accessibility compliance validation (LGPD + federal gov standards) | [2] | Flow iteration gains: AI drafts conversational flow variants + Slack Canvas UX mockups from pilot feedback [2], but Experience Design gap (G0104/G0402/G0505 — 10k+ external users onboarding, no UX research scoped) means no usability testing baseline F1 unless added. Service design for J3 (Abertura Chamados Assistida) + J4 (Adoção CRM Conversacional) human-led — AI generates flow options but user research (what questions do 10k+ B2B clients ask? what language do they use?) not automatable. Accessibility compliance (LGPD + federal gov standards) human-validated — AI flags WCAG gaps but Jurídico approval required.
Role Type | Change Management Lead | ~15-25% | ~6-11% | Training delivery materials by persona; Adoption monitoring dashboard (CRM Analytics uso semanal %) | Early adopters program facilitation (20-50 pilot users F1 — champions identified, trained first); Executive mandate support (Saulo enforces adoption KPIs >60% uso semanal F2 — non-adopters escalated) | [2] | CM gains: AI drafts training materials + adoption dashboard templates [2], but early adopters program (20-50 pilot users F1 — who are the champions? how to incentivize?) human-facilitated. Executive mandate (Saulo enforces >60% uso semanal target F2) + non-adopter escalation workflow human-driven — AI flags low-adoption cohorts but executive relationship management not automatable. Training by persona (B2B clients J1, executivos J5, comercial J4/J6, N1/N2 J2/J3, Pessoas J7) AI-generated but persona-specific delivery (what resonates with federal gov B2B clients vs. internal comercial?) requires CM Lead human judgment per client culture.
Human Barrier | Protheus Governance Blocker Resolution (G1002) |  | ~0% |  | TI+Jurídico+DPO tri-party meeting negotiation (perfil de acesso model approval) — legal/political alignment across three internal stakeholders. AI can draft governance models but cannot negotiate tri-party sign-off.
Human Barrier | Workspace Slack Segregation Decision (G0101) |  | ~0% |  | Jurídico approval unknown (B2B vs internos workspace segregation) — legal interpretation of data isolation requirements. AI can draft both options but Jurídico approval human-gated.
Human Barrier | Clarity Migration Strategy (G0801) |  | ~0% |  | Hard-to-reverse decision (co-living vs Service Cloud replacement, 4.5k active demands migrate) deferred F2 architecture gate — business risk assessment + vendor relationship implications (Broadcom Clarity co-living governance). AI drafts both paths but choice human-gated.
Human Barrier | Experience Design for 10k+ Users (G0104/G0402/G0505) |  | ~0% |  | User research (what questions do 10k+ B2B clients ask? what language?) + service design (onboarding flow for federal gov users) — human empathy + domain context. AI generates flow variants but pilot feedback interpretation not automatable.
Human Barrier | RACI + CoE Charter Facilitation (G9901/G1001/G1003) |  | ~0% |  | Multi-team ownership decision rights (Agentforce config, MuleSoft APIs, Slack admin), data stewardship (CRM Totvs vs Salesforce truth?), CoE structure — political alignment across internal stakeholders. AI drafts RACI templates but stakeholder negotiation human-driven.
Human Barrier | Executive Mandate Enforcement (Saulo >60% Adoption KPIs) |  | ~0% |  | Executive relationship management (Saulo enforces adoption, non-adopters escalated) — trust-building + influence. AI flags low-adoption cohorts but executive persuasion not automatable.
Human Barrier | Project Pulse Reports |  | ~0% |  | Trust-building work that AI can summarize but not facilitate — stakeholder pulse (Saulo satisfied? TI/Jurídico/DPO aligned?) requires human judgment.
Human Barrier | Stakeholder Alignment |  | ~0% |  | Human-to-human negotiation across TI+Jurídico+DPO tri-party + executive sponsor Saulo — AI drafts positions, people decide.
Human Barrier | Conflict Resolution |  | ~0% |  | Human judgment — multi-team ownership RACI conflicts (who owns Agentforce prompt changes? G1001) require negotiation.